Software Project Management (CS615)

1

© Copyright Virtual University of Pakistan

LECTURE # 1

1. Introduction & Fundamentals

1.1 What is Management?

Basically, the management involves the following activities:

􀂐 Planning- deciding what is to be done

􀂐 Organizing- making arrangements

􀂐 Staffing- selecting the right people for the job

􀂐 Directing- giving instructions

􀂐 Monitoring- checking on progress

􀂐 Controlling- taking action to remedy hold-ups

􀂐 Innovating- coming up with new solutions

􀂐 Representing- liaising with users, etc.

1.2 What is Project Management?

Project Management is the art of maximizing the probability that a project

delivers its goals on Time, to Budget and at the required Quality.

The art of planning for the future has always been a human trait. In essence a

project can be captured on paper with a few simple elements: a start date, an end

date, the tasks that have to be carried out and when they should be finished, and

some idea of the resources (people, machines etc) that will be needed during the

course of the project.

Project management is the application of knowledge, skills, tools, and

techniques to project activities to meet project requirements. Project management

is accomplished through the use of the processes such as: initiating, planning,

executing, controlling, and closing. It is important to note that many of the

processes within project management are iterative in nature. This is in part due to

the existence of and the necessity for progressive elaboration in a project

throughout the project life cycle; i.e., the more you know about your project, the

better you are able to manage it.

Project management is also defined as a strategic competency that has successfully been

applied in such high profile projects as the construction of silk root, organizing and managing the

Olympics Games, and the construction of Islamabad-Lahore motorway, just to name a few. If

project management can play a major role in these success stories, just imagine what it might be

able to do for your own organization.

The term project management is sometimes used to describe an organizational

approach to the management of ongoing operations. This approach, more properly

called management by projects, treats many aspects of ongoing operations as

projects to apply project management techniques to them.

Software Project Management (CS615)

2

© Copyright Virtual University of Pakistan

Almost any human activity that involves carrying out a non- repetitive task

can be a project. So we are all project managers! We all practice project

management (PM). But there is a big difference between carrying out a very

simple project involving one or two people and one involving a complex mix of

people, organizations and tasks.

1.3 What is Software Project Management?

When the plan starts to involve different things happening at different times, some

of which are dependent on each other, plus resources required at different times

and in different quantities and perhaps working at different rates, the paper plan

could start to cover a vast area and be unreadable.

Nevertheless, the idea that complex plans could be analyzed by a computer to

allow someone to control a project is the basis of much of the development in

technology that now allows projects of any size and complexity, not only to be

planned, but also modeled to answer 'what if?' questions.

The original programs and computers tended to produce answers long after an

event had taken place. Now, there are many project planning and scheduling

programs that can provide real time information, as well as linking to risk

analysis, time recording, and costing, estimating and other aspects of project

control.

But computer programs are not project management: they are tools for

project managers to use. Project management is all that mix of components of

control, leadership, teamwork, resource management etc that goes into a

successful project.

Project managers can be found in all industries. Their numbers have grown

rapidly as industry and commerce has realized that much of what it does is project

work. And as project-based organizations have started to emerge, project

management is becoming established as both a professional career path and a way

of controlling business.

So opportunities in project management now exist not only in being a project

manager, but also as part of the support team in a project or program office or as a

team leader for part of a project. There are also qualifications that can be attained

through the professional associations.

Software Project Management (CS615)

3

© Copyright Virtual University of Pakistan

1.4 What is a Project?

A project is an activity with specific goals which takes place over a finite

period of time.

“A temporary organization that is needed to produce a unique and pre-defined

outcome or result at a pre-specified time using pre-determined resources”

Projects are often implemented as a means of achieving an organization’s

strategic plan. Operations and projects differ primarily in that operations are

ongoing and repetitive while projects are temporary and unique. A project can

thus be defined in terms of its distinctive characteristics—a project is a temporary

endeavor undertaken to create a unique product or service. Temporary means

that every project has a definite beginning and a definite end. Unique means that

the product or service is different in some distinguishing way from all other

products or services. For many organizations, projects are a means to respond to

those requests that cannot be addressed within the organization’s normal

operational limits.

Projects are undertaken at all levels of the organization. They may involve a

single person or many thousands. Their duration ranges from a few weeks to more

than five years. Projects may involve a single unit of one organization or may

cross organizational boundaries, as in joint ventures and partnering.

Examples of projects include:

• Developing a new product or service.

• Effecting a change in structure, staffing, or style of an organization.

• Designing a new transportation vehicle.

• Developing or acquiring a new or modified information system.

• Constructing a building or facility.

• Building a water system for a community in a developing country.

• Running a campaign for political office.

• Implementing a new business procedure or process.

1. Temporary

Temporary means that every project has a definite beginning and a definite end.

The end is reached when the project’s objectives have been achieved, or it

becomes clear that the project objectives will not or cannot be met, or the need for

the project no longer exists and the project is terminated. Temporary does not

necessarily mean short in duration; many projects last for several years. In every

case, however, the duration of a project is finite; projects are not ongoing efforts.

2. Unique, Product Service or Result

Projects involve creating something that has not been done in exactly the same

way before and which is, therefore, unique and distinct. Projects create:

Software Project Management (CS615)

4

© Copyright Virtual University of Pakistan

• A product or artifact that is produced, is quantifiable and can be either an

end item in itself or a component item

• A capability to perform a service, such as business functions supporting

production or distribution

• A result, such as new knowledge. For example, a research and

development project develops knowledge that can be used to determine

whether or not a trend is present or a new process will benefit society.

The presence of repetitive elements does not change the fundamental uniqueness

of the project work. For example:

• A project to develop a new commercial airliner may require multiple

proto-types.

• A project to bring a new drug to market may require thousands of doses of

the drug to support clinical trials.

• A real estate development project may include hundreds of individual

units.

• A development project (e.g., water and sanitation) may be implemented in

five geographic areas.

3. Aims/Tasks/Purpose

The projects are designed to achieve specific targets defined in terms of aims,

tasks or a purpose. The nature and size of the project depends upon

complexity of the task, realization of the aims and scope of the purpose any

organization wants to achieve. In short project has to be aimed for achieving

certain tasks in a given time frame.

4. Limited Time Scale

The projects are always designed considering time constraints. Extension to

the project completion dead lines are always discouraged as time overrun,

costs extra and in some cases opportunity cost for not completing a project is

too high.

􀀔 Progressive, Elaboration

Progressive elaboration is a characteristic of projects that accompanies the

concepts of temporary and unique. “Progressively” means developing thoroughly

in steps, and continuing steadily by increments while elaborated means “worked

out with care and detail; developed thoroughly”

For example, the project scope will be broadly described early in the project, and

made more explicit and detailed as the project team develops a better and more

complete understanding of the objectives and deliverables.

Progressive elaboration of project specifications must be carefully coordinated

with proper project scope definition, particularly if the project is performed under

contract. When properly defined, the scope of the project—the work to be done—

Software Project Management (CS615)

5

© Copyright Virtual University of Pakistan

should be controlled as the project and product specifications are progressively

elaborated.

The following examples illustrate progressive elaboration in two different

application areas.

􀀹 Example 1. Development of a chemical processing plant begins with process

engineering to define the characteristics of the process. These characteristics are

used to design the major processing units. This information becomes the basis for

engineering design, which defines both the detail plant layout and the mechanical

characteristics of the process units and ancillary facilities. All of this results in

design drawings that are elaborated to produce fabrication and construction

drawings. During construction, interpretations and adaptations are made as

needed and subject to proper approval. This further elaboration of the deliverables

is captured in as-built drawings, and final operating adjustments are made during

testing and turnover.

􀀹 Example 2. The product of an economic development project may initially be

defined as: “Improve the quality of life of the lowest income residents of

community X.” As the project proceeds, the products may be described more

specifically as, for example: “Provide access to food and water to 500 low income

residents in community X.” The next round of progressive elaboration might

focus exclusively on increasing agriculture production and marketing, with

provision of water deemed to be a secondary priority to be initiated once the

agricultural component is well under way.

Software Project Management (CS615)

6

© Copyright Virtual University of Pakistan

LECTURE # 2

1. Introduction & Fundamentals

1.5 Goals of Project management

Project management is the discipline of defining and achieving a set of goals

while optimizing the use of allocated resources (time, money, people, space,

etc). This includes planning, scheduling and maintaining progress of the

activities that comprise the project. Project management is normally reserved for

focused, non-repetitive, time-limited activities with some degree of risk and that

are beyond the usual scope of program (operational) activities for which the

organization is responsible.

Project management software describes the tools to efficiently coordinate and

automate the various project management component processes. Project

management software generally offers extensive reporting features, such as dayto-

day status updates of project progress, scheduling and dependency trees, and

system-generated alerts when schedules slip beyond pre-set tolerances. Most

project management tools include web-accessible interfaces so that employees

can access features of the software relevant to their needs, and functionality to

allow managers to share resource pools without overbooking.

1.6 Project Characteristics

1. Temporary

Temporary means that every project has a definite beginning and a definite end.

The end is reached when the project’s objectives have been achieved, or it

becomes clear that the project objectives will not or cannot be met, or the need for

the project no longer exists and the project is terminated. Temporary does not

necessarily mean short in duration; many projects last for several years. In every

case, however, the duration of a project is finite; projects are not ongoing efforts.

2. Unique, Product Service or Result

Projects involve creating something that has not been done in exactly the same

way before and which is, therefore, unique and distinct. Projects create:

• A product or artifact that is produced, is quantifiable and can be either an

end item in itself or a component item

• A capability to perform a service, such as business functions supporting

production or distribution

Software Project Management (CS615)

7

© Copyright Virtual University of Pakistan

• A result, such as new knowledge. For example, a research and

development project develops knowledge that can be used to determine

whether or not a trend is present or a new process will benefit society.

The presence of repetitive elements does not change the fundamental uniqueness

of the project work. For example:

• A project to develop a new commercial airliner may require multiple

proto-types.

• A project to bring a new drug to market may require thousands of doses of

the drug to support clinical trials.

• A real estate development project may include hundreds of individual

units.

• A development project (e.g., water and sanitation) may be implemented in

five geographic areas.

5. Aims/Tasks/Purpose

The projects are designed to achieve specific targets defined in terms of aims,

tasks or a purpose. The nature and size of the project depends upon

complexity of the task, realization of the aims and scope of the purpose any

organization wants to achieve. In short project has to be aimed for achieving

certain tasks in a given time frame.

6. Limited Time Scale

The projects are always designed considering time constraints. Extension to

the project completion dead lines are always discouraged as time overrun,

costs extra and in some cases opportunity cost for not completing a project is

too high.

1.7 Four Project Dimensions

Software project management is an umbrella activity within software engineering.

It begins before any technical activity is initiated and continues throughout the

definition, development, and support of computer software.

Four P's have a substantial influence on software project management- people,

product, process, and project.

• People must be organized into effective teams, motivated to do high-quality

software work, and coordinated to achieve effective communication.

• The product requirements must be communicated from customer to

developer, partitioned (decomposed) into their constituent parts, and

positioned for work by the software team.

• The process must be adapted to the people and the problem. A common

process framework is selected, an appropriate software engineering paradigm

is applied, and a set of work tasks is chosen to get the job done.

Software Project Management (CS615)

8

© Copyright Virtual University of Pakistan

• The project must be organized in a manner that enables the software team to

succeed.

Effective software project management focuses on the four P’s: people, product,

process, and project. The order is not arbitrary. The manager who forgets that

software engineering work is an intensely human endeavor will never have

Success in project management. A manager who fails to encourage

comprehensive customer communication early in the evolution of a project risks

building an elegant solution for the wrong problem. The manager who pays little

attention to the process runs the risk of inserting competent technical methods and

tools into a vacuum. The manager who embarks without a solid project plan

jeopardizes the success of the product.

⇒ People

In a study published by the IEEE, the engineering vice presidents of three

major technology companies were asked the most important contributor to a

successful software project. They answered in the following way:

VP 1: I guess if you had to pick one thing out that is most important in our

environment. I’d say it’s not the tools that we use, it’s the people.

VP 2: The most important ingredient that was successful on this project was

having smart people…very little else matters in my opinion....The most

important thing you do for a project is selecting the staff...The success of the

software development organization is very, very much associated with the

ability to recruit good people.

VP 3: The only rule I have in management is to ensure I have good people –

real good people-and that I grow good people – and that I provide an

environment in which good people can produce.

Indeed, this is a compelling testimonial on the importance of people in the

software engineering process. And yet, all of us, from senior engineering vice

presidents to the lowliest practitioner, often take people for granted. Managers

argue (as the preceding group had) that people are primary, but their actions

sometimes belie their words. In this section we examine the players who

participate in the software process and the manner in which they are organized

to perform effective software engineering.

1. The Players

The software process (and every software project) is populated by players

who can be categorized into one of five constituencies:

1. Senior managers who define the business issues that often have

significant influence on the project.

Software Project Management (CS615)

9

© Copyright Virtual University of Pakistan

2. Project (technical) managers who must plan, motivate, organize,

and control the practitioners who do software work.

3. Practitioners who deliver the technical skills that are necessary to

engineer a product or application.

4. Customers who specify the requirements for the software to be

engineered and other stakeholders who have a peripheral interest in

the outcome.

2. End-users

Who interact with the software once it is released for production use.

Every software project is populated by people who fall within this

taxonomy. To be effective, the project team must be organized in a way

that maximizes each person’s skills and abilities. And that’s the job of the

team leader.

3. Team Leaders

Project management is a people-intensive activity, and for this reason,

competent practitioners often make poor team leaders. They simply don’t

have the right mix of people skills. And yet, as Edgemon states:

“unfortunately and all too frequently it seems, individuals just fall into a

project manager role and become accidental project managers.” [EDG95].

The cultivation of motivated, highly skilled software people has been

discussed since the 1960s (e.g., [COUBO] [WIT94} [DEM9B]). In fact,

the “people factor’ is so important that the Software Engineering Institute

has developed a people management capability maturity model (PMCMM),

“to enhance the readiness of software organizations to undertake

increasingly complex applications by helping to attract, grow, motivate,

deploy, and retain the talent needed to improve their software

development capability” [CUR94].

The people management maturity model defines the following key

practice areas for software people: recruiting, selection, performance

management, training, compensation, career development, organization

and work design, and team/culture development. Organizations that

achieve high levels of maturity in the people management area have a

higher likelihood of implementing effective software engineering

practices.

The PM-CMM is a companion to the software capability maturity model

that guides organizations in the creation of a mature software process.

⇒ The Process

Software Project Management (CS615)

10

© Copyright Virtual University of Pakistan

In a fascinating book that provides an economist’s view of software and

software engineering, Howard Baetjer. Jr, comments on the software process:

Software development is a social learning process. The process is a dialogue

in which the knowledge that must become the software is brought together and

embodied in the software. The process provides interaction between users and

designers: between users and evolving tools, and between designers and

evolving tools [technology] It is an iterative process in which the evolving tool

itself serves as the medium for communication, with each new round of the

dialogue eliciting more useful knowledge from the people involved.

When you build a product or system, it’s important to go through a series of

predictable steps – a road map that helps you create a timely, high-quality

result, The road map that you follow is called a ‘software process’ .

Software engineers and their managers adapt the process to their needs and

then follow it. In addition, the people who have ties defined by the process

requested the software play a role in the software process.

At a detailed level, the process that you adopt depends on the software you’re

building. One process might be appropriate for creating software for an

aircraft avionics system, while an entirely different process would be

indicated for the creation of a web site.

From the point of view of a software engineer, the work products are the

programs, documents and data produces as a consequence of the software

engineering activities defined by the process.

A software process provides the framework from which a comprehensive plan

for software development can be established.

A small number of framework activities are applicable to all software projects,

regardless of their size or complexity.

A number of different task sets-tasks, milestones, work products and; quality

assurance points-enable the framework activities to be adapted to the

characteristics of the software project and the requirements of the project

team.

Finally, umbrella activities – such as software quality assurance, software

configuration management, and measurement – overlay the process model.

Umbrella activities are independent of anyone framework activity and occur

throughout the process.

Software Project Management (CS615)

11

© Copyright Virtual University of Pakistan

LECTURE # 3

1. Introduction & Fundamentals

1.8 Project Dimensions

⇒ Product and Technology

– The 80:20, rule was originated by Vilfredo Pareto, an Italian economist who

studies the distribution of wealth in a variety of countries around 1900. He

discovered a common phenomenon: about 80% of the wealth in most countries

was controlled by a consistent minority -- about 20% of the people. Pareto called

this a "predictable imbalance." His observation eventually became known as

either the "80:20 rule" or "Pareto's Principle."

The credit for adapting Pareto's economic observations to business goes to the

"Father of Total Quality Management," service quality consultant Joseph M.

Juran. In 1950, he published "The Quality Control Handbook," which first

recognized the applicability of the Pareto principle in the context of inventory

management, e.g.:

• 20% of the repair parts normally account for 80 percent of the total

inventory

• 80% of production volume usually comes from 20% of the producers

He subsequently recognized that this rule of thumb was universally applicable

across fields of endeavor. As a credit to Pareto's work, Juran named his finding

the Pareto Principle. This universal management theory became generalized as

"the 80-20 Rule":

The "80:20 rule" has become one of the best known "leadership shorthand terms"

reflecting the notion that most of the results (of a life, of a program, of a financial

campaign) come from a minority of effort (or people, or input).

The Rule, states that a small number of causes (20%) is responsible for a large

percentage (80%) of the effect. It means that in anything a few (20 percent) are

vital and many (80 percent) are trivial.

There is an inherent imbalance between cause and effect, effort and reward, inputs

and outputs, etc; and that imbalance tends to the ratio of 80:20. So, if we know

which 20% of our work produces 80% of our income, we can do more of it and

our income will increase proportionately!

Software Project Management (CS615)

12

© Copyright Virtual University of Pakistan

You know 20 percent of you stock takes up 80 percent of your warehouse space

and that 80 percent of your stock comes from 20 percent of your suppliers. Also

80 percent of your sales will come from 20 percent of your sales staff. 20 percent

of your staff will cause 80 percent of your problems, but another 20 percent of

your staff will provide 80 percent of your production. It works both ways.

Some Sample 80/20 Rule Applications

80% of process defects arise from 20% of the process issues.

20% of your sales force produces 80% of your company revenues.

80% of delays in schedule arise from 20% of the possible causes of the delays.

80% of customer complaints arise from 20% of your products or services.

How It Can Help You

– The value of the Pareto Principle for a manager is that it reminds you to focus on

the 20 percent that matters. Of the things you do during your day, only 20 percent

really matter. Those 20 percent produce 80 percent of your results. Identify and

Characteristic

focus on those things. When the fire drills of the day begin to sap your time,

remind yourself of the 20 percent you need to focus on. If something in the

schedule has to slip, if something isn't going to get done, make sure it's not part of

that 20 percent.

Pareto's Principle, the 80/20 Rule, should serve as a daily reminder to focus 80

percent of your time and energy on the 20 percent of you work that is really

important. Don't just "work smart", work smart on the right things.

– Size

The larger product, there will be more requirements and features to deliver,

eventually it will take more time in its production. So if you cut the size of the

produce to half it will save you 60% of the effort.

– Characteristic

– Development Tools

Software Project Management (CS615)

13

© Copyright Virtual University of Pakistan

Customer delivered value

1.9 Project Phases

Organizations performing projects will usually divide each project into several

Project phases to improve management control and provide for links to the

ongoing operations of the performing organization.

Collectively, the project phases are known as the project life cycle. Software

development, just like most other activities, has a beginning, middle and an end.

The end of one development activity is sometimes perceived as being linked to

the beginning of a new development activity thus producing a cycle of beginningmiddle-

end, link, beginning-middle-end, link, and so forth.

This view of software development is referred to as the software development

life cycle.

A project has five phases. Here's a brief summary of each:

⇒ Initiation

Articulate your vision for the project, establish goals, assemble your team,

and define expectations and the scope of your project.

⇒ Planning

Refine the scope, identify specific tasks and activities to be completed,

and develop a schedule and budget.

⇒ Executing

Accomplish your goals by leading your team, solving problems, and

building your project.

Value of products

Value of services

Financial cost

Personal value

Psychical cost

Image value

Time cost

Real value to

the customer

Total value

Total costs

Energy cost

+

-

Software Project Management (CS615)

14

© Copyright Virtual University of Pakistan

⇒ Controlling

Monitor changes to the project make corrections, adjust your schedule to

respond to problems, or adjust your expectations and goals.

⇒ Closing

Deliver your project to your audience, acknowledge results, and assess its

success. Take the time to compose a written evaluation of the project and

the development effort.

The middle three phases are not sequential. You will find that you are constantly

planning, executing, and controlling your project as necessary.

Aren't these phases really just common sense? In many ways, yes, but keep in

mind that software development, whether a few Web pages or a complex CDROM,

is a complex, unpredictable process.

Most software projects (something like 80 percent) are delivered late,

substantially over budget, and incomplete. The more effort you put into managing

your project, the more you increase your chances of success.

– Characteristics of Project Phases

Each project phase is marked by completion of one or more deliverables. A

deliverable is a tangible, verifiable work product such as a feasibility study, a

detail design, or a working prototype. The deliverables, and hence the phases, are

part of a generally sequential logic designed to ensure proper definition of the

product of the project.

The conclusion of a project phase is generally marked by a review of both key

deliverables and project performance to date, to a) determine if the project should

continue into its next phase and b) detect and correct errors cost effectively. These

phase-end reviews are often called phase exits, stage gates, or kill points.

Each project phase normally includes a set of defined deliverables designed to

establish the desired level of management control. The majority of these items are

related to the primary phase deliverable, and the phases typically take their names

from these items: requirements, design, build, test, startup, turnover, and others,

as appropriate.

– Characteristics of the Project Life Cycle

The project life cycle serves to define the beginning and the end of a project. For

example, when an organization identifies an opportunity to which it would like to

respond, it will often authorize a needs assessment and/or a feasibility study to

decide if it should undertake a project. The project life-cycle definition will

determine whether the feasibility study is treated as the first project phase or as a

separate, standalone project.

Software Project Management (CS615)

15

© Copyright Virtual University of Pakistan

The project life-cycle definition will also determine which transitional actions at

the beginning and the end of the project are included and which are not. In this

manner, the project life-cycle definition can be used to link the project to the

ongoing operations of the performing organization.

The phase sequence defined by most project life cycles generally involves some

form of technology transfer or handoff such as requirements to design,

construction to operations, or design to manufacturing. Deliverables from the

preceding phase are usually approved before work starts on the next phase.

However, a subsequent phase is sometimes begun prior to approval of the

previous phase deliverables when the risks involved are deemed acceptable. This

practice of overlapping phases is often called fast tracking.

Project life cycles generally define:

􀂃 What technical work should be done in each phase (e.g., is the work of the

architect part of the definition phase or part of the execution phase?).

􀂃 Who should be involved in each phase (e.g., implementers who need to be

involved with requirements and design).

􀂃 Project life-cycle descriptions may be very general or very detailed. Highly

detailed descriptions may have numerous forms, charts, and checklists to

provide structure and consistency. Such detailed approaches are often called

project management methodologies.

􀂃 Most project life-cycle descriptions share a number of common

characteristics:

􀂃 Cost and staffing levels are low at the start, higher toward the end, and drop

rapidly as the project draws to a conclusion.

􀂃 The probability of successfully completing the project is lowest, and hence

risk and uncertainty are highest, at the start of the project. The probability of

successful completion generally gets progressively higher as the project

continues.

􀂃 The ability of the stakeholders to influence the final characteristics of the

project’s product and the final cost of the project is highest at the start and

gets progressively lower as the project continues. A major contributor to this

phenomenon is that the cost of changes and error correction generally

increases as the project continues.

Care should be taken to distinguish the project life cycle from the product life

cycle. For example, a project undertaken to bring a new desktop computer to

market is but one phase or stage of the product life cycle.

Although many project life cycles have similar phase names with similar

deliverables required, few are identical. Most have four or five phases, but some

Software Project Management (CS615)

16

© Copyright Virtual University of Pakistan

have nine or more. Even within a single application area, there can be significant

variations.

One organization’s software development life cycle may have a single design

phase while another’s has separate phases for functional and detail design.

Subprojects within projects may also have distinct project life cycles. For

example, an architectural firm hired to design a new office building is first

involved in the owner’s definition phase when doing the design, and in the

owner’s implementation phase when supporting the construction effort. The

architect’s design project, however, will have its own series of phases from

conceptual development through definition and implementation to closure. The

architect may even treat designing the facility and supporting the construction as

separate projects with their own distinct phases.

– Project Life Cycle includes the following Phases and activities:

A. Concept Phase

1. User Need

2. Initial Investigation

3. User Review

4. System Performance Design

5. Candidate Review

6. Study Phase Report

B. Requirements Phase

1. The software requirements specification document

2. The project development plan

3. The software test plan

C. Design Phase

1. General System Review

2. Processing Requirements Identification

3. Data Base Design

4. Control Requirements

5. Output Design

6. Input Design

7. Software Selection

8. Equipment Selection/Acquisition

9. People

10. Reference Manual Identification

11. Plans

12. Design Specifications Preparation

13. Design Phase Report Preparation

D. Development Phase

Software Project Management (CS615)

17

© Copyright Virtual University of Pakistan

1. Implementation Planning

2. Computer Program Design

3. User Review

4. Equipment Acquisition and Installation

5. Coding and Debugging

6. Computer Program Testing

7. System Testing

8. Reference Manual Preparation

9. Personnel Training

10. Changeover Plan Preparation

11. Development Phase Report Preparation

12. User Acceptance Review

E. Operation Phase

1. System Changeover

2. Routine Operation

3. System Performance Evaluation

4. System Changes/Enhancements

1.10 Software Development Lifecycle

⇒ Water Fall Theme

Software development, just like most other activities, has a beginning, middle and

an end. The end of one development activity is sometimes perceived as being

linked to the beginning of a new development activity thus producing a cycle of

beginning-middle-end, link, beginning-middle-end, link, and so forth. This view

of software development is referred to as the software development life cycle.

There are many variations of the software development life cycle. Figure 1

presents a simple life cycle that was common during the first few decades of

software development. In those early days of software development, the

programmer would create programs by iterating from code to fix then back to

code, and then to fix again, until something acceptable was (hopefully) produced.

At the start of the cycle, there was usually no clear concept of what was required,

and the basic development procedure was a form of 'let's see what we can do'

approach.

The software development method represented by the development cycle in Fig.1

is often referred to as the code and fix method (for obvious reasons). Software

development methodologies have come a long way since the days of code and fix,

though it is surprising how much software is still being developed this way.

Successful management of any project, especially software projects, requires

planning, and planning is impossible with code and fix, which is totally

unpredictable. Management of software development within an engineering

Software Project Management (CS615)

18

© Copyright Virtual University of Pakistan

discipline is based on a much more orderly set of development phases. These

phases are not implemented solely by programmers; they require software

engineers. In fact, programming has become a relatively small part of the modern

software development cycle, as is evident from Table 1.

The numbers in Table 1 are derived from the general shift in emphasis to software

planning (requirements and design) and testing. Commercial data processing

systems, with some exceptions, still spend a significant amount of development

time in the programming and unit testing phase. Real-time systems are often more

complex, and may include extensive hardware software integration. This usually

requires more planning and more integration and testing.

Figure 1: the code and fix method

Table 1 Estimated percentage of time spent in each major software development phase

Planning Code and unit test Integration and test

Commercial data processing 25% 40% 35%

Real-time systems 35% 25% 40%

Military systems 40% 20% 40%

Military systems require high reliability and are usually closely supervised by the

customer, leading to a significant increase in the time spent in planning.

The data in Table 1, of course, represents a generalization; commercial data

processing systems can be just as complex as a real-time system.

Figure 2 presents the basic phased model of a software development cycle. This

model, called the Waterfall model, gets its name from the way in which each

phase cascades into the next (due to overlapping), as demonstrated in Fig. 3.

Some interpretations of the Waterfall model, like the one that follows, combine

the top level design and the detailed design phases into a single design phase, and

the integration and test phases into a single phase. In fact, there are many

variations of the classic Waterfall model, but they are all based upon a systematic

transition from one development phase to the next, until the project is complete.

Concept Code Fix

Maintain

Software Project Management (CS615)

19

© Copyright Virtual University of Pakistan

Conception

Maintenance Software

Requirements

Test

Top level

Design

Integration Detailed

Design

Implementation

Figure 2: The phased model of the software development life cycle

Conception

Software requirements

Top level" design

Detailed design

Implementation

Integration

Test

Maintenance

T

Figure 3: The Waterfall model of the software development life cycle

⇒ Rapid prototyping There are other development methodologies that do not move

from one phase to the next like the Waterfall model. Rapid prototyping, for

Software Project Management (CS615)

20

© Copyright Virtual University of Pakistan

instance, iterates in a mini-development phase until a system prototype is

developed (see Fig. 4). After the prototype is complete, the Waterfall approach

can then be implemented to complete the full system. Rapid prototyping is

particularly helpful in projects where the requirements are difficult to specify. The

prototype can be used as a tool for analyzing and determining what the

requirements should be.

⇒ The Spiral model, described by Boehm (1988), is another development method

that iterates between the requirements, design and implementation phases.

However, the Spiral model continues iterating until the final system is complete.

Within each, iteration, the Spiral model follows a phased approach similar to the

Waterfall model.

Different models maybe suitable for different software projects or for different

software development organizations However, a good model must include certain

fundamental features. Some of these basic requirements are discussed in IEEE

Standard (IEEE 1993) Standard for Software Life Cycle Processes. This standard

describes the processes that are mandatory for the development of software and

specifies the activities that must be included in the life cycle model.

Most modern software development models, and certainly those following IEEE

Standard 1074, include some form of the basic phased model. It is therefore

important to understand the different phases and how they relate to one another.

Concept Prototype Requirements Design Implementation Test

The rapid prototyping cycle

Figure 4: Rapid prototyping followed by the phase method.

Software Project Management (CS615)

21

© Copyright Virtual University of Pakistan

LECTURE # 4

1. Introduction & Fundamentals

1.11 Costs and Cost Management

Project Cost Management includes the processes required to ensure that the

project is completed within the approved budget.

⇒ Resource Planning—determining what resources (people, equipment,

materials and what quantities of each should be used to perform project

activities.

⇒ Cost Estimating—developing an approximation (estimate) of the costs of

the resources needed to complete project activities.

⇒ Cost Budgeting—allocating the overall cost estimate to individual work

activities.

⇒ Cost Control—controlling changes to the project budget.

These processes interact with each other and with the processes in the other

knowledge areas as well.

Each process may involve effort from one or more individuals or groups of

individuals, based on the needs of the project.

Each process generally occurs at least once in every project phase.

Although the processes are presented here as discrete elements with well-defined

interfaces, in practice they may overlap and interact in ways not detailed here.

Project cost management is primarily concerned with the cost of the resources

needed to complete project activities.

However, project cost management should also consider the effect of project

decisions on the cost of using the project’s product.

For example, limiting the number of design reviews may reduce the cost of the

project at the expense of an increase in the customer’s operating costs. This

broader view of project cost management is often called life-cycle costing. Lifecycle

costing together with Value Engineering techniques are used to reduce cost

and time, improve quality and performance, and optimize the decision-making.

In many application areas, predicting and analyzing the prospective financial

performance of the project’s product is done outside the project.

Software Project Management (CS615)

22

© Copyright Virtual University of Pakistan

In others (e.g., capital facilities projects), project cost management also includes

this work. When such predictions and analyses are included, project cost

management will include additional processes and numerous general management

techniques such as return on investment, discounted cash flow, payback analysis,

and others.

Project cost management should consider the information needs of the project

stakeholders—different stakeholders may measure project costs in different ways

and at different times. For example, the cost of a procurement item may be

measured when committed, ordered, delivered, incurred, or recorded for

accounting purposes.

1.12 Project vs. Program Management

⇒ What is a Program?

“A coordinated portfolio of projects that change organizations to achieve benefits

of strategic importance”

Program management is the process of managing multiple on

going projects. An example would be that of designing, manufacturing and

providing support infrastructure for an automobile make.

It can be argued that Program Management has evolved from the complexities of

the more intricate aspects of Project Management.

As projects became larger; more interrelated; complex and multidimensional, the

need arose to have an approach that controlled Project Management whilst

remaining focused on the strategic objectives of the business. Whilst Project

Management focused on technical delivery, Program Management engaged on

relating design concepts to the business strategic vision of the future.

It is very important that you understand the concept of Program Management as a

method. Approaches may vary but definitions are relatively common. It is

appropriate to understand the ‘mission, goals and objectives’ of Program

Management and then relate these to the Program you propose to develop.

Definitions will fall within each of these headings and it is possible to develop

your own template which fits your organizational program. For example:

– Mission:

To co-ordinate a portfolio of projects to harmonize communications in

order to achieve a set of stated business objectives: Provision of strategy

alignment, with design objectives, in order to maintain control over a

Software Project Management (CS615)

23

© Copyright Virtual University of Pakistan

multiple project environment; ensuring quality end deliverables which

meet business operational needs.

The above is a fairly complex mission statement but provides a framework

to develop an intricate set of goals in order to utilize Program

Management. It is possible to develop an extensive list of goals,

depending upon the level of detail you wish to acquire. The following are

offered as suggestions:

– Goals:

1. Clearly defined roles and responsibilities

2. Established baselines and Terms of Reference statement

3. Type of program defined

4. Future business blueprint

5. Recognition of business transformation procedures

6. Defined structure of the Program

7. Route Map

8. Visible end deliverables — vision of the future

9. Identification of future benefits

10. Risk

11. Contingency planning

Software Project Management (CS615)

24

© Copyright Virtual University of Pakistan

Each of the goals would then be analyzed for providing objectives. For example:

• Managing a program embraces functions, risks and strategies outside of what a

project manager does.

• A program has goals beyond those of a project or group of projects. Program

outcomes are usually service delivery focused whereas a project is more likely

to be focused on the delivery of a 'product'.

• A program is more than a grouping of projects (that's just a program of works).

• The coordinated management of a portfolio of projects to achieve a set of

business objectives

• There are many more meanings of the term program management. Here are the

more common meanings:

– The Multi-Project Organization:

Program Management is the directing of a portfolio of projects that benefit

from a consolidated approach.

Jobbing engineering companies; software houses contracting for work; and

many other types of organization; run many simultaneous projects each of

which may or not contribute towards the corporate goals.

Typically the result of such a project is a deliverable which is eventually

delivered to a client for payment. After many delays the payment arrives and

Software Project Management (CS615)

25

© Copyright Virtual University of Pakistan

gets paid into the company’s bank account thereby increasing cash flow which

is achieving one of the company’s objectives.

Sometimes the projects are much more directly aimed at corporate goals -

opening a new factory or launching a new product - spring to mind.

The common elements of the projects are that they run simultaneously or at

least overlap with each other, they share resources and are supposed to

generate some income. One project being cancelled does not necessarily

change the organization’s general direction. These types of programs run for

ever and need have no end date. The projects are separate in that there need

not be logical links between projects. Whilst they share the same resources,

delays in one project need not cause delays in others.

– The Mega Project

The management of a portfolio of projects towards one specific objective;

Program management can also mean one very large project.

The USA’s Man on the Moon Project was such a program. In this sense the

term program indicates one very large project which is made up from a

number of components. Within the Apollo program there were many projects:

the Lunar Lander, the Orbiter, the Launcher and the Control Systems were all

projects which were large, complex and interesting. Polaris and the

Manhattan project (which resulted in the nuclear bomb) are other famous

projects large enough to be called programs. Therefore, particularly in USA,

the word program refers to a series of projects which make up one large

project.

The program is usually reflected in the management structure as there will be

a program manager to whom the project managers will report. Said program

manager or sometimes program director will concern himself with recruiting

and maintaining his project management teams and on integrating the

deliverables of each project into one overall program. In this meaning of

program management there is likely to be one physical deliverable.

These sorts of programs end. There will be a time when the overall objective

has been achieved and the program and all of its constituent projects are over.

The projects within this type of program are often linked. Delays with one

project often cause knock on effects with others due to logical links between

tasks in both projects.

For example if the moon rocket launch pad project was delayed, it would

delay the testing of the moon rocket itself. The Beirut Shopping Mall will be

of little use without the water treatment plant and the new sewer scheme. Such

Software Project Management (CS615)

26

© Copyright Virtual University of Pakistan

projects may not share the same resources but there are almost certain to be

linked through their logic.

1.13 Project Success

Project success is correlated with thorough analyses of the need for project

deliverables. Our research has shown that when a project results in deliverables

that are designed to meet a thoroughly documented need, then there is a greater

likelihood of project success. So managers should insist that there is a

documented business need for the project before they agree to consume

organizational resources in completing it.

We conduct planned and controlled software projects for one primary reason - it

is the only known way to manage complexity. And yet, we still struggle. In 1998,

industry data indicated that 26 percent of software projects failed outright and 46

percent experienced cost and schedule overruns [REE99].

Although the success rate for software projects has improved somewhat, our

project failure rate remains higher than it should be.

In order to avoid project failure, a software project manager and the software

engineers who build the product must avoid a set of common warning signs,

understand the critical success factors that lead to good project management, and

develop a common sense approach for planning, monitoring and controlling the

project.

In order to manage a successful software project, we must understand what can go

wrong (so that problems can be avoided) and how to do it right. In an excellent

paper on software projects, John Reel [REE99] defines ten signs that indicate that

an information systems project is in jeopardy:

1. Software people don't understand their customer's needs.

2. The product scope is poorly defined.

3. Changes are managed poorly.

4. The chosen technology changes.

5. Business needs change (or are ill-defined)

6. Deadlines are unrealistic.

7. Users are resistant.

8. Sponsorship is lost [or was never properly obtained).

9. The project team lacks people with appropriate skills.

10. Managers [and practitioners) avoid best practices and lessons learned.

Jaded industry professionals often refer to the 90-90 rule when discussing

particularly difficult software projects: The first 90 percent of a system absorbs 90

percent of the allotted effort and time. The last 10 percent takes the other 90

Software Project Management (CS615)

27

© Copyright Virtual University of Pakistan

percent of the allotted effort and time [ZAH94]. The seeds that lead to the 90-90

rule are contained in the signs noted in the preceding list.

But enough negativity! How does a manager act to avoid the problems just noted?

Reel [REE99] suggests a five-part commonsense approach to software projects:

1. Start on the right foot. This is accomplished by working hard (very hard)

to understand the problem that is to be solved and then setting realistic

objects and expectations for everyone who will be involved in the project.

It is reinforced by building the right team (Section 3.2.3) and giving the

team the autonomy, authority, and technology needed to do the job.

2. Maintain momentum. Many projects get off to a good start and then

slowly disintegrate. To maintain momentum, the project manager must

provide incentives to keep turnover of personnel to an absolute minimum,

the team should emphasize quality in every task it performs, and senior

management should do everything possible to stay out of (the team's way.

3. Track progress. For a software project, progress is tracked as work

products (e.g., specifications, source code, sets of test cases) are produced

and approved (using formal technical reviews) as part of a quality

assurance activation, software process and project measures can be

collected and used to assess progress against averages developed for the

software development organization.

4. Make smart decisions. In essence, the decisions of the project manager

and the software team should be to "keep it simple.” Whenever possible,

decide to use commercial off-the-shelf software or existing software

components, decide to avoid custom interfaces when standard approaches

are available, decide to identify and then avoid obvious risks, and decide

to allocate more time than you think is needed to complex or risky tasks

(you'll need every minute).

5. Conduct a postmortem analysis. Establish a consistent mechanism for

extracting lessons learned for each project. Evaluate the planned and

actual schedules, collect and analyze software project metrics, get

feedback from team members and customers, and record findings in

written form.

– Projects and Strategy

Projects are a means of organizing activities that cannot be addressed

within the organization’s normal operational limits.

Projects are therefore often utilized as a means of achieving an

organization’s strategic plan, whether the project team is employed by the

organization or is a contracted service provider.

Projects are typically authorized as a result of one or more of the

following strategic considerations:

Software Project Management (CS615)

28

© Copyright Virtual University of Pakistan

􀂃 A market demand (e.g., an oil company authorizes a project to build a

new refinery in response to chronic gasoline shortages)

􀂃 A business need (e.g., a training company authorizes a project to create a

new course in order to increase its revenues)

􀂃 A customer request (e.g., an electric utility authorizes a project to build a

new substation to serve a new industrial park)

􀂃 A technological advance (e.g., an electronics firm authorizes a new

project to develop a new generation of video game player after the

introduction of the corresponding new game format)

􀂃 A legal requirement (e.g., a paint manufacturer authorizes a project to

establish guidelines for the handling of a new toxic material).

No project ever goes 100% as planned, so project managers must learn to adapt to

change. There are many things that can go wrong with project management.

These are commonly called barriers. Here are some possible barriers:

1. Poor Communication

– Many times a project may fail because the project team does not

know exactly what to get done or what's already been done.

2. Disagreement

– Project must meet all elements in a contract.

– Customer and project manager must agree on numerous

elements.

– Failure to comply with standards and regulations.

– Inclement weather.

– Union strikes.

– Personality conflicts.

– Poor management

3. Poorly defined project goals

1.14 Trade-Off Triangle

Good project management deals with three factors: time, cost and

performance.

Projects are successful if they are completed on time, within budget, and to

performance requirements. In order to bring the many components of a large

project into control there is a large toolkit of techniques, methodologies, and

tools.

Software Project Management (CS615)

29

© Copyright Virtual University of Pakistan

These techniques provide the tools for managing different components

involved in a project: planning and scheduling, developing a product;

managing financial and capital resources, and monitoring progress. However

the success of a project will always rest on the abilities of a project manager

and the team members.

In managing competing project requirements Project managers often talk of a

triple constraint:

– Project scope

– Time and

– Cost

Project quality is affected by balancing these three factors.

High quality projects deliver the required product or service within scope, on

time and within budget.

The relationship among these factors is such that if any one of the three

factors changes, at least one other factor must change.

Simply put: project success means completing all project deliverables on time,

within budget, and to a level of quality that is acceptable to sponsors and

stakeholders.

The project manager must keep the team's attention focused on achieving

these broad goals. Most people still want their projects to be on time, meet

quality objectives, and not cost more than the budget. These form the classic

time, quality, cost triangle.

In fact if you have an unlimited budget and unlimited time, project

management becomes rather easy. For most people, however, time and money

are critical and that is what makes project management so important today.

Project management is often summarized in a triangle. The three most

important factors are time, cost and scope. These form the vertices with

quality as a central theme.

Software Project Management (CS615)

30

© Copyright Virtual University of Pakistan

1. Projects must be delivered on time.

2. Projects must be within cost

3. Projects must be within scope

4. Projects must meet customer quality requirements

More recently, this has given way to a project management diamond, with

time, cost, scope and quality the four vertices and customer expectations as a

central theme. No two customers' expectations are the same so you must ask

what their expectations are.

A project goes through four phases during its life:

1. Project Definition: Defining the goals, objectives and critical success

factors for the project

2. Project Initiation: Everything that is needed to set-up the project before

work can start

3. Project Control: Ensuring that a project stays on track and taking

appropriate action to ensure it does

4. Project Closure: Disbanding of all the elements that were required to run

the project

Software Project Management (CS615)

31

© Copyright Virtual University of Pakistan

1.15 Project Management Skills

The role of the Leader in project management is one of great responsibility.

It's the project manager's job to direct and supervise the project from

beginning to end. Here are some other roles:

(a) Leadership

(b) Communications

(c) Problem Solving

(d) Negotiating

(e) Influencing the Organization

(f) Mentoring

(g) Process and technical expertise

(a) Leadership

Leadership is a complex phenomenon involving the leader, the followers,

and the situation. Perhaps the best way for you to begin to understand the

complexities of leadership is to see some of the ways leadership has been

defined. Leadership researchers have defined leadership in the following

different ways:

􀂃 The creative and directive force of morale. (Munson, 1921)

􀂃 The process by which an agent induces a subordinate to behave in a

desired manner. (Bennis, 1959)

􀂃 The presence of a particular influence relationship between two or

more persons. (Hollander & Julian, 1969)

􀂃 Directing and coordinating the work of group members. (Fiedler,

1967) An interpersonal relation in which others comply because they

want to, not because they have to. (Merton, 1969; Hogan, Curphy, &

Hogan, 1994)

􀂃 Transforming followers, creating visions of the goals that may be

attained, and articulating for the followers the ways to attain those

goals. (Bass, 1985; Fichy & Devanna, 1986)

􀂃 The process of influencing an organized group toward accomplishing

its goals. (Roach & Behling, 1984)

􀂃 Actions that focus resources to create desirable opportunities.

(Campbell, 1991)

Software Project Management (CS615)

32

© Copyright Virtual University of Pakistan

􀂃 The leader's job is to create conditions for the team to be effective.

(Ginnett, 1996)

Leading and managing are both essential management skills: one

without the other is likely to produce poor results. Managing is primarily

concerned with “consistently producing key results expected by

stakeholders,” while leading involves:

􀂃 Establishing direction—developing both a vision of the future and

strategies for producing the changes needed to achieve that vision.

􀂃 Aligning people—communicating the vision by words and deeds to

all those, whose cooperation may be needed to achieve the vision.

􀂃 Motivating and inspiring—helping people energize themselves to

overcome political, bureaucratic, and resource barriers to change.

On a project, particularly a larger project, the project manager is generally

expected to be the project’s leader as well.

Leadership is not, however, limited to the project manager: it may be

demonstrated by many different individuals at many different times during

the project.

Leadership must be demonstrated at all levels of the project (project

leadership, technical leadership, and team leadership).

(b) Communicating

Communicating involves the exchange of information and the ability to

transmit and receive information with a high probability that the intended

message is passed from sender to receiver.

The sender is responsible for making the information clear, unambiguous,

and complete so that the receiver can receive it correctly. The receiver is

responsible for making sure that the information is received in its entirety

and understood correctly.

Few skills are more vital to leadership. Studies show that good leaders

communicate feelings and ideas, actively solicit new ideas from others,

and effectively articulate arguments, advocate positions, and persuade

others.

The quality of a Leader’s communication is positively correlated with

subordinate satisfaction as well as with productivity and quality of

services rendered.

Software Project Management (CS615)

33

© Copyright Virtual University of Pakistan

Effective communication skills are also important because they provide

leaders and followers with greater access to information relevant to

important organizational decisions.

Communicating has many dimensions:

– Written and oral, listening and speaking

– Internal (within the project) and external (to the customer, the

media, the public, etc.).

– Formal (reports, briefings, etc.) and informal (memos, ad hoc

conversations, etc.)

– Vertical (up and down the organization) and horizontal (with peers

and partner organization)

The general management skill of communicating is related to, but not the

same as, Project Communications Management.

Communicating is the broader subject and involves a substantial body of

knowledge that is not unique to the project context, for example:

– Sender-receiver models—feedback loops, barriers to

communications, etc.

– Choice of media—when to communicate in writing, when to

communicate orally, when to write an informal memo, when to

write a formal report, etc.

– Writing style—active versus passive voice, sentence structure,

word choice, etc.

– Presentation techniques—body language, design of visual aids,

etc.

– Meeting management techniques—preparing an agenda, dealing

with conflict, etc.

Project Communications Management is the application of these broad

concepts to the specific needs of a project—for example, deciding how;

when; in what form; and to whom to report project performance.

(c) Negotiating

Negotiating involves conferring with others to come to terms with them or

reach an agreement.

Agreements may be negotiated directly or with assistance; mediation and

arbitration are two types of assisted negotiation.

Negotiation is an approach that may help resolve some conflicts. Some

important tips on negotiation include; preparing for a negotiation session;

Software Project Management (CS615)

34

© Copyright Virtual University of Pakistan

keeping people and problems separate; focusing on issues, not positions

and seeking win-win outcomes.

Negotiations occur around many issues, at many times, and at many levels

of the project.

During the course of a typical project, project staff is likely to negotiate

for any or all of the following:

• Scope, cost, and schedule objectives.

• Changes to scope, cost, or schedule.

• Contract terms and conditions.

• Assignments.

• Resources.

(d) Problem Solving

There are three steps involved in this important leadership role; identifying

problem; analyzing its cause; and solving the problem.

Problem solving involves a combination of problem definition and

decision-making.

Problem definition requires distinguishing between causes and symptoms.

Problems may be:

– Internal (a key employee is reassigned to another project)

– External (a permit required to begin work is delayed).

– Technical (differences of opinion about the best way to design a

product)

– Managerial (a functional group is not producing according to

plan) or

– Interpersonal (personality or style clashes).

(e) Decision-making

Decision-making includes analyzing the problem to identify viable

solutions, and then making a choice from among them.

Decisions can be made or obtained (from the customer, from the team, or

from a functional manager).

Once made, decisions must be implemented.

Decisions also have a time element to them—the “right” decision may not

be the “best” decision if it is made too early or too late.

Software Project Management (CS615)

35

© Copyright Virtual University of Pakistan

(f) Influencing the Organization

Influencing the organization involves the ability to “get things done.”

It requires an understanding of both the formal and informal structures of

all the organizations involved—the performing organization, customer,

partners, contractors, and numerous others, as appropriate.

Influencing the organization also requires an understanding of the

mechanics of power and politics.

Both power and politics are used here in their positive senses.

Power is “the potential ability to influence behavior, to change the course

of events, to overcome resistance, and to get people to do things that they

would not otherwise do.”

In similar fashion, “politics is about getting collective action from a group

of people who may have quite different interests. It is about being willing

to use conflict and disorder creatively.

The negative sense, of course, derives from the fact that attempts to

reconcile these interests result in power struggles and organizational

games that can sometimes take on a thoroughly unproductive life of their

own.”

Influence can be exercised in a: variety of ways. It may be the 'bridge to

engine room' approach, where the leader commands and controls. Or the

influence can be exercised by guiding and facilitating the group's behavior

so that the goal is accomplished.

Finally, leadership implies that a leader motivates the group to spend

energy in attaining the goals of the group.

Influence without change or movement isn’t influence. Leaders make

change happen, a difficult but vitally important task.

(g) Mentoring

Mentoring or being a Transformational leadership is more concerned with

engagement between leaders and followers.

Leaders attempt to engage the full person of the subordinate and enthuse

them. They arouse in their subordinates a heightened awareness of the key

issues for the group or the organization. They seek to concern subordinates

with achievement, growth and development.

Software Project Management (CS615)

36

© Copyright Virtual University of Pakistan

Creating a new vision is something that almost all writers on

transformational leadership emphasize.

The vision points the way to a new state of affairs. It is an appealing

picture of a more desirable future. It inspires people to believe that the

future is worth the upheaval of undoing the present.

A vision needs to be a source of self-esteem and a common purpose for

members of the organization.

(h) Technical Skills:

A project manager must have technical skills. This relates to financial

planning, contract management, and managing creative thinking and

problem solving techniques are promoted.

Software Project Management (CS615)

37

© Copyright Virtual University of Pakistan

LECTURE # 5

1. Introduction & Fundamentals

1.16 PM’s nine Knowledge Areas

1. Project Integration Management

Project Integration Management includes the processes required to ensure that the

various elements of the project are properly coordinated. It involves making

tradeoffs among competing objectives and alternatives to meet or exceed stakeholder

needs.

These processes interact with each other and with the processes in the other

knowledge areas as well. Each process may involve effort from one or more

individuals or groups of individuals, based on the needs of the project. Each

process generally occurs at least once in every project phase.

Project integration management comes into play when a cost estimate is needed

for a contingency plan, or when risks associated with various staffing alternatives

must be identified. However, for a project to be completed successfully,

integration must also occur in a number of other areas as well. For example:

􀂃 The work of the project must be integrated with the ongoing operations of the

performing organization.

􀂃 Product scope and project scope must be integrated.

One of the techniques used to both integrate the various processes and to measure

the performance of the project as it moves from initiation through to completion is

Earned Value Management (EVM).

• Earned value is the amount of work completed, measured according to the

budgeted effort that the work was supposed to consume.

• It is also called the budgeted cost of work performed.

• As each task is completed, the number of person-months originally planned

for that task is added to the earned value of the project.

– Earned value charts: An earned value chart has three curves:

• The budgeted cost of the work scheduled.

• The earned value.

• The actual cost of the work performed so far.

2. Project Scope Management

Software Project Management (CS615)

38

© Copyright Virtual University of Pakistan

Project Scope Management includes the processes required to ensure that the

project includes all the work required, and only the work required, to complete the

project successfully. It is primarily concerned with defining and controlling what

is or is not included in the project.

The processes, tools, and techniques used to manage product scope vary by

application area and are usually defined as part of the project life cycle

A project generally results in a single product, but that product may include

subsidiary components, each with its own separate but interdependent product

scopes. For example, a new telephone system would generally include four

subsidiary components—hardware, software, training, and implementation.

Completion of the project scope is measured against the project plan, but

completion of the product scope is measured against the product requirements.

Both types of scope management must be well integrated to ensure that the work

of the project will result in delivery of the specified product.

3. Project Time Management

Project Time Management includes the processes required to ensure timely

completion of the project. The followings are major processes in developing the

project time schedule:

(a) Activity Definition—identifying the specific activities that must be

performed to produce the various project deliverables.

(b) Activity Sequencing—identifying and documenting interactivity

dependencies.

(c) Activity Duration Estimating—estimating the number of work periods that

will be needed to complete individual activities.

(d) Schedule Development—analyzing activity sequences, activity durations,

and resource requirements to create the project schedule.

(e) Schedule Control—controlling changes to the project schedule.

These processes interact with each other and with the processes in the other

knowledge areas as well. Each process may involve effort from one or more

individuals or groups of individuals, based on the needs of the project. Each

process generally occurs at least once in every project phase.

4. Project Cost Management

Software Project Management (CS615)

39

© Copyright Virtual University of Pakistan

Project Cost Management includes the processes required to ensure that the

project is completed within the approved budget.

Resource Planning—determining what resources (people, equipment, materials)

and what quantities of each should be used to perform project activities.

Cost Estimating—developing an approximation (estimate) of the costs of the

resources needed to complete project activities.

Cost Budgeting—allocating the overall cost estimate to individual work

activities.

Cost Control—controlling changes to the project budget.

These processes interact with each other and with the processes in the other

knowledge areas as well. Each process may involve effort from one or more

individuals or groups of individuals, based on the needs of the project. Each

process generally occurs at least once in every project phase.

5. Project Quality Management

Project Quality Management includes the processes required to ensure that the

project will satisfy the needs for which it was undertaken. It includes “all

activities of the overall management function that determine the quality policy,

objectives, and responsibilities and implements them by means such as quality

planning, quality assurance, quality control, and quality improvement, within the

quality system.

These processes interact with each other and with the processes in the other

knowledge areas as well. Each process may involve effort from one or more

individuals or groups of individuals, based on the needs of the project. Each

process generally occurs at least once in every project phase.

Project quality management must address both the management of the project and

the product of the project. The generic term product is occasionally used, in

literature regarding quality, to refer to both goods and services.

6. Project Human Resource Management

Project Human Resource Management includes the processes required to make

the most effective use of the people involved with the project. It includes all the

project stakeholders—sponsors, customers, partners, and individual contributors

Following are some major processes:

Software Project Management (CS615)

40

© Copyright Virtual University of Pakistan

􀂃 Organizational Planning—identifying, documenting, and assigning project

roles, responsibilities, and reporting relationships.

􀂃 Staff Acquisition—getting the human resources needed assigned to and

working on the project.

􀂃 Team Development—developing individual and group competencies to

enhance project performance.

These processes interact with each other and with the processes in the other

knowledge areas as well. Each process may involve effort from one or more

individuals or groups of individuals, based on the needs of the project.

There is a substantial body of literature about dealing with people in an

operational, ongoing context. Some of the many topics include:

􀂃 Leading, communicating, negotiating, etc.

Key General Management Skills:

􀂃 Delegating, motivating, coaching, mentoring, and other subjects related to

dealing with individuals.

􀂃 Team building, dealing with conflict, and other subjects related to dealing

with groups.

􀂃 Performance appraisal, recruitment, retention, labor relations, health and

safety regulations, and other subjects related to administering the human

resource function.

Most of this material is directly applicable to leading and managing people on

projects, and the project manager and project management team should be

familiar with it. However, they must also be sensitive as to how this knowledge is

applied on the project. For example:

Project Human Resource Management includes the processes required to make

the most effective use of the people involved with the project. It includes all the

project stakeholders—sponsors, customers, partners, and individual contributors.

Major processes include:

􀂃 Organizational Planning—identifying, documenting, and assigning project

roles, responsibilities, and reporting relationships.

􀂃 Staff Acquisition—getting the human resources needed assigned to and

working on the project.

􀂃 Team Development—developing individual and group competencies to

enhance project performance.

Software Project Management (CS615)

41

© Copyright Virtual University of Pakistan

These processes interact with each other and with the processes in the other

knowledge areas as well. Each process may involve effort from one or more

individuals or groups of individuals, based on the needs of the project.

7. Project Communications Management

Project Communications Management includes the processes required to ensure

timely and appropriate generation, collection, dissemination, storage, and ultimate

disposition of project information. It provides the critical links among people,

ideas, and information that are necessary for success. Everyone involved in the

project must be prepared to send and receive communications, and must

understand how the communications in which they are involved as individuals

affect the project as a whole.

Major processes include:

􀂃 Communications Planning—determining the information and

communications needs of the stakeholders: who needs what information,

when they will need it, and how it will be given to them.

􀂃 Information Distribution—making needed information available to project

stakeholders in a timely manner.

􀂃 Performance Reporting—collecting and disseminating performance

information. This includes status reporting, progress measurement, and

forecasting.

􀂃 Administrative Closure—generating, gathering, and disseminating

information to formalize a phase or project completion.

These processes interact with each other and with the processes in the other

knowledge areas as well. Each process may involve effort from one or more

individuals or groups of individuals, based on the needs of the project. Each

process generally occurs at least once in every project phase.

Communicating is a broader subject and involves a substantial body of knowledge

that is not unique to the project context. For example:

􀂃 Sender-receiver models—feedback loops, barriers to communications, etc.

􀂃 Choice of media—when to communicate in writing versus when to

communicate orally, when to write an informal memo versus when to write a

formal report, etc.

􀂃 Writing style—active versus passive voice, sentence structure, word choice,

etc.

􀂃 Presentation techniques—body language, design of visual aids, etc.

􀂃 Meeting management techniques—preparing an agenda, dealing with

conflict, etc.

Software Project Management (CS615)

42

© Copyright Virtual University of Pakistan

8. Project Risk management

Project Risk management is the systematic process of identifying, analyzing, and

responding to project risk. It includes maximizing the probability and

consequences of positive events and minimizing the probability and consequences

of adverse events to project objectives.

􀂃 Risk Management Planning—deciding how to approach and plan the risk

management activities for a project.

􀂃 Risk Identification—determining which risks might affect the project and

documenting their characteristics.

􀂃 Qualitative Risk Analysis—performing a qualitative analysis of risks and

conditions to prioritize their effects on project objectives.

􀂃 Quantitative Risk Analysis—measuring the probability and consequences of

risks and estimating their implications for project objectives.

􀂃 Risk Response Planning—developing procedures and techniques to enhance

opportunities and reduce threats to the project’s objectives.

􀂃 Risk Monitoring and Control—monitoring residual risks, identifying new

risks, executing risk reduction plans, and evaluating their effectiveness

throughout the project life cycle.

These processes interact with each other and with the processes in the other

knowledge areas. Each process generally occurs at least once in every project.

9. Project Procurement Management

Project Procurement Management includes the processes required to acquire

goods and services, to attain project scope, from outside the performing

organization. For simplicity, goods and services, whether one or many, will

generally be referred to as a product.

An overview of the major processes includes:

􀂃 Procurement Planning—determining what to procure and when.

􀂃 Solicitation Planning—documenting product requirements and identifying

potential sources.

􀂃 Solicitation—obtaining quotations, bids, offers, or proposals, as appropriate.

􀂃 Source Selection—choosing from among potential sellers.

􀂃 Contract Administration—managing the relationship with the seller.

􀂃 Contract Closeout—completion and settlement of the contract, including

resolution of any open items.

These processes interact with each other and with the processes in the other

knowledge areas as well. Each process may involve effort from one or more

individuals or groups of individuals, based on the needs of the project

Software Project Management (CS615)

43

© Copyright Virtual University of Pakistan

Project Procurement Management is discussed from the perspective of the buyer

in the buyer-seller relationship. The buyer-seller relationship can exist at many

levels on one project. Depending on the application area, the seller may be called

a subcontractor, a vendor, or a supplier.

The seller will typically manage its work as a project. In such cases:

􀂃 The buyer becomes the customer, and is thus a key stakeholder for the seller.

􀂃 The seller’s project management team must be concerned with all the

processes of project management, not just with those of this knowledge area.

􀂃 The terms and conditions of the contract become a key input to many of the

seller’s processes. The contract may actually contain the input (e.g., major

deliverables, key milestones, cost objectives), or it may limit the project

team’s options (e.g., buyer approval of staffing decisions is often required on

design projects).

Software Project Management (CS615)

44

© Copyright Virtual University of Pakistan

LECTURE # 6

1. Introduction & Fundamentals

1.17 Team leader

Most definitions of leadership involve three components: influence group and

goal. First, leaders are individuals who influence the behavior of others. These

others are usually referred to as sub ordinates or followers. Second, leadership is

usually examined in the context of a group, especially work groups such as

managers and their teams or foremen and their subordinates. Third, research on

leadership stresses a group goal that has to be accomplished. So a definition is:

Leadership is the process in which an individual influences the group

members towards the attainment of group or organization goals.

Note that the influence can be exercised in a: variety of ways. It may be the

'bridge to engine room' approach, where the leader commands and controls. Or

the influence can be exercised by guiding and facilitating the group's behavior so

that the goal is accomplished. The notion of reciprocity is also part of man

definitions. Influencing is often two ways. Leaders may influence followers, but

followers influence leaders to lead in one way rather than another. An influencing

style appropriate for checkout assistant in a supermarket may be different from

that appropriate for rock scientists. The choice is open to the leader of how to

influence is one of the key aspects investigated by leadership researchers.

Another aspect of leadership is that the right to lead is often voluntarily conferred

on the leader by some or all members of the group. A group of friends may

recognize one, of their group as the leader, in the sense that she influences the

group more than any of the other members. There also may be informal leader.

While the nominal head of a department may have the formal leadership position,

the real leadership may be exercised by someone lower down the hierarchy who

influences the group towards goals that may not be those that the organization

whishes to be pursue.

Finally, leadership implies that a leader motivates the group to spend energy

in attaining the goals of the group. Influence without change or movement isn’t

influence. Leaders make change happen, a difficult but vitally important task.

1.18 Leaders and Managers

Although it is common to use the terms 'leader' and 'manager' interchangeably,

nowadays many writers point to a difference between the two.

Software Project Management (CS615)

45

© Copyright Virtual University of Pakistan

The difference is that to function as a leader, a person must exercise influence

over another person in the attainment of organizational goals, as described in the

definition above. Managerial ' functions of organizing, planning, scheduling,

processing information, communicating, and so on, do not necessarily involve

leadership. Some managers perform both types of function and can be described

as leaders, but others do not. There is no automatic link between the two concepts.

Note, too, that leaders are not necessarily just at the top of organizations.

Influence can be exerted in most job functions and at levels of seniority or

hierarchy. The distinction between managers and leaders was, developed by

Bennis and Nanus (1985) in their influential book Leaders. In it they put forward

the view that:

Leadership is path finding

Management is path following

Management is about doing things right

Leadership is about doing the right things

What they meant by this is that leadership is about having a vision. It involves

having a strategy or thinking strategically; it means having a view of where the

organization should go or be or do; it means deciding what is important for the

success of the organization; it involves envisaging the future, A leader's

responsibility is to think what are the key criteria for success of his or her part of

the business and not just now but for the future.

Managers, on the other hand, are more concerned with implementing others

strategies and plans, They are concerned with running their part of the

organization, making sure that the accounts get prepared, that invoices are sent

out, that the service is sold, that the traffic is directed, that the research paper is

written, or whatever the task that needs to be done.

A very similar view is put forward by Kotter (1990). He argues that management

is concerned with activities which are designed to produce 'consistency and order',

whereas leadership is concerned with, 'constructive or adaptive change'. Kotter

says there are four major ways that management and leadership differ:

1. Planning and budgeting versus establishing direction. Management

involves making detailed steps and timetables for achieving results, then

marshalling resources to make it happen. Leadership means developing a

vision of the future and strategies for achieving that vision.

2. Organizing and staffing versus aligning people. Management comprises the

allocation of tasks in line with plans, staffing them appropriately, delegating

responsibility and monitoring implementation. Leadership involves

communicating the vision so that others understand and agree with it.

3. Controlling and problem-solving versus motivating and inspiring.

Management involves monitoring results of a plan, identifying problems with

the plan and then solving them. Leadership involves 'energizing people'

Software Project Management (CS615)

46

© Copyright Virtual University of Pakistan

towards the vision. It means appealing to their needs and values so that they

overcome barriers to change.

4. Outcomes: predictability and order, or change. Management produces

predictability and order so that others, such as customers or shareholders can

rely on consistent results. Leadership produces change that is often a quantum

leap, such as new products or new approaches to managing people, that makes

the organization more competitive.

Kirkpatrick and Locke (1991) suggest that the following traits distinguish

leaders from non-leaders:

• Drive (achievement. ambition, energy, tenacity, initiative);

• Leadership motivation (personalized or socialized); .honesty and

integrity;

• Self-confidence (including emotional stability);

• Cognitive ability (the ability to marshal and interpret a wide variety

of information);

• Knowledge of the business

They point out, though, that there is much more to being an effective leader than

merely possessing a list of traits. While the traits may provide people with the

potential for leadership, it is the capacity to create a vision and implement it that

turns the potential into reality.

Strong leadership motivation may sound an obvious trait for a leader. After all,

only those who want the weighty responsibilities and grueling pressures of

leadership are likely to strive for it. McClelland (1985) distinguishes between two

types of power motivation. On the one hand, leaders may be interested in

personalized power, which describes the motivation of leaders who "seek power

for its own sake, who wish to dominate others and are often concerned with the

status and trappings of power. The late Robert Maxwell, former owner of the

Mirror Group allegedly displayed such traits. On the other hand, leaders who

show socialized power motivation are more interested in cooperating with others

to achieve desired goals. They work with others rather than attempting to

dominate or control them. From the point of view of subordinates and the

organization as a whole, the leader motivated by socialized power is obviously

preferable. On the question of cognitive ability; leaders must be able to gather,

integrate and interpret large amounts of information. Many

Many researchers have pointed out that it is not necessary to be brilliant, though;

leadership effectiveness is helped by above average intelligence, not genius. Of

Kirkpatrick and Locke’s six characteristics, some would argue that drive and

persistence are much more important than intelligence.

In conclusion, the trait approach has undergone a revival. Recent research

suggests that traits do matter. Yet the research shows that there are only a handful

Software Project Management (CS615)

47

© Copyright Virtual University of Pakistan

of traits which distinguish leaders from others, and a clear distinction between

effective and ineffective leaders has not yet emerged.

In an excellent book of technical leadership, Jerry Weinberg suggests a MOI

model of leadership:

Motivation: The ability to encourage (by "push or pull") technical people to

produce to their best ability.

Organization: The ability to mold existing processes (or invent new ones) that

will enable the initial concept to be translated into a final product.

Ideas or innovation: The ability to encourage people to create and feel creative

even when they must work within bounds established for a particular soft- ware

product or application.

Weinberg suggests that successful project leaders apply a problem solving

management style. That is, a software project manager should concentrate on

understanding the problem to be solved, managing the flow of ideas, and at the

same time, letting everyone on the team know (by words and, far more important,

by actions) that quality counts and that it will not be compromised.

Another view [EDG95] of the characteristics that define an effective project

manager emphasizes four key traits:

Problem solving An effective software project manager can diagnose the

technical and organizational issues that are most relevant, systematically structure

a solution or properly motivate other practitioners to develop the solution, apply

lessons learned from past projects to new situations, and remain flexible enough

to change direction if initial attempts at problem solution are fruitless.

Managerial identity

A good project manager must take charge of the project. She must have the

confidence to assume control when necessary and the assurance to allow good

technical people to follow their instincts.

Achievement

To optimize the productivity of a project team, a manager must reward initiative

and accomplishment and demonstrate through his own actions that controlled risk

taking will not be punished.

Influence and team building

An effective project manager must be able to "read" people; she must be able to

understand verbal and nonverbal signals and react to the needs of the people

sending these signals. The manager must remain under control in high-stress

situations.

Software Project Management (CS615)

48

© Copyright Virtual University of Pakistan

1.19 Project Organization

People are managed through an organizational structure. This hierarchical

structure is based on the four cornerstones of management: delegation,

authority, responsibility and supervision (see Fig.1). Delegation bestows

authority, and authority produces (and requires) responsibility. Both

authority and responsibility require supervision, and effective supervision

requires a suitable organizational structure:

Most projects are organized as teams, with each team assigned specific

functions within the project, Different types of project require different

types of team structure, as for example a team of junior programmers

requires a technical team leader while a team of experts may require only

an administrative team leader. It is the project manager's responsibility to

select the structure best suited for the project.

Basically an organization is a group of people intentionally organized to

accomplish an overall, common goal or set of goals. Business

organizations can range in size from two people to tens of thousands.

Figure 1: The four cornerstones of management

There are many ways to organize a software project. The larger the project

the more critical the organizational structure becomes. Badly organized

projects breed confusion, and confusion leads to project failure. Figure 2

describes the basic structure of a project in which below the project

manager are just two general functions: development and support. This

very basic software project structure was not uncommon in the 1950s and

1960s. It is still a valid project structure for very small projects (up to five

developers), though occasionally it can still be found today in larger

projects.

Delegation

1

Supervision

2

Authority

3

Responsibility

4

Software Project Management (CS615)

49

© Copyright Virtual University of Pakistan

Figure 2: Basic structure of a development project

Figure 3: Software project organizational chart

Project

Project

development

Project

support

Project

manager

Deputy

project

manager

System

engineer

Independent

test group

Secretary

Quality

assurance

Configuration

control

Development

team 1

Development

team 2

Development

team 3

Software Project Management (CS615)

50

© Copyright Virtual University of Pakistan

Project

manager

Deputy project

manager

Integration

Group

Independent

Group

Secretary

Quality

assurance

Configuration

control

SW sub-project

Manager 1

SW sub-project

Manager 2

SW sub-project

Manager 3

Team 1

Team 2

Team 3

Team 1

Team 2

Team 1

Team 2

Team 3

Figure 4: Large hardware/software project organizational chart

Project managers are just two general functions: development and support. This very

basic software project structure was not uncommon in the 1950s and 1960s. It is a project

structure for very small projects (up to five developers). Though occasionally, it can still

be found today in larger projects.

Figure 3 describes a detailed organizational chart including all major support functions.

This organizational structure is suitable for large projects (with a staff exceeding 20).

Smaller projects may not require a deputy project manager or separate configuration

control and quality assurance groups.

Very large projects (exceeding a staff of 40) can often be managed more easily by

dividing the project into sub-projects. Figure 4 presents the organizational chart for a

large project. This chart includes both software and hardware development teams, and an

integration group that is responsible for hardware/software integration as well as

integration within each group.

As an example, consider the organization of a large satellite project. The project manager

is in fact responsible for a number of projects: the ground control station, the rocket and

the satellite itself. The software for all of these sub-projects is managed within a single

project office. Each sub-project is then managed by a sub-project manager. An

organizational chart similar to the one described in Fig. 4 can be applied to the satellite

project; the resulting chart is described in Fig. 5.

Software Project Management (CS615)

51

© Copyright Virtual University of Pakistan

Satellite

PM

Sub-project

Coordinator

Scientific

Engineer

Integration

Team

Secretary

Quality assurance Ground control

Station sub-project

Rocket

Development

Sub-project

Satellite

Sub-project

Team 1

Team 2

Team 3

Team

1

Team

2

Team

1

Team

2

Team

3

Quality

Assurance

Independent

Group

Configuration

Control

Figure 5: Satellite project organizational chart

Clearly the project's organizational structure is dependent on the type of project being

developed. Some of the issues that must be considered are:

– Project size: the larger the project, the more important the organization. Large

projects have significant human communications and coordination overhead, and

therefore require more support functions.

– Hardware/software development projects. The simultaneous development of

hardware and software is not easy. Planning, integration and testing are much

more complicated, and require dedicated support groups.

– High reliability systems. Any system that is sensitive to issues of reliability (such

as military or life-saving systems) requires a major effort in quality assurance.

Quality is also an important consideration in many marketable software products

(e.g. communications packages). These types of project require a separate quality

assurance organization.

Software Project Management (CS615)

52

© Copyright Virtual University of Pakistan

􀀔 The Organizational structure

The organization's structure, or design, is the overall arrangement of the

organization's various roles, processes and their relationships in the organization.

The design of an organization is a means to accomplishing the organization's

overall goal -- the structure is not an end in itself. In systems theory terms, the

design ensures that the appropriate inputs go through the necessary processes to

produce the required outputs to produce the intended outcomes.

The structure of the performing organization often constrains the availability of or

terms under which resources become available to the project. Organizational

structures can be characterized as spanning a spectrum from functional to

projectized, with a variety of matrix structures in between.

⇒ Corporate structure: The project's organization is largely dependent on the overall

structure of the company within which the project is being developed. Many of the

project support functions can be provided by centralized groups within the company.

In fact, basic services, such as financial, secretarial and legal services, are commonly

provided by the parent or corporate organization.

Corporate structure usually dictates one of two basic types of project organization:

matrix or pyramid. Figure 5 describes the structure of a matrix organization (compare

this to the pyramid structure in Fig. 4). Within a corporate matrix organization, the

project manager manages the technical activities of the project staff, while his or her

involvement in non-technical personnel issues (e.g. salary reviews, promotion, and

training) is minimal.

⇒ Matrix Structure

Think of the functional structure. Imagine if you took someone from each of the

major functions in the functional structure (the boxes along the bottom of the

organization chart), e.g., people from sales, engineering, etc., and organized them into

a separate group intended to produce and sell one certain kind of product or service.

Members of this group stay together until that product is produced or they continue to

sell and service it. This overall structure (made up of a functional structure that also

has groups assigned to products) is a matrix structure. This structure is useful because

it focuses highly skilled people from across the organization to work on a complex

product or service. It can be difficult though, because each person essentially reports

to two supervisors: the supervisor of the functional area (e.g., engineering) and the

product manager, as well. When the organization needs constant coordination of its

functional activities, then lateral relations do not provide sufficient integration.

Consider the matrix structure. To adopt the matrix structure effectively, the

organization should modify many traditional management practices.

Matrix organizations are a blend of functional and projectized characteristics. Weak

matrices maintain many of the characteristics of a functional organization, and the

Software Project Management (CS615)

53

© Copyright Virtual University of Pakistan

project manager role is more that of a coordinator or expediter than that of a manager.

In similar fashion, strong matrices have many of the characteristics of the projectized

organization—full-time project managers with considerable authority and full-time

project administrative staff.

Most modern organizations involve all these structures at various levels. For example,

even a fundamentally functional organization may create a special project team to

handle a critical project. Such a team may have many of the characteristics of a

project in a projectized organization. The team may include full-time staff from

different functional departments, it may develop its own set of operating procedures,

and it may operate outside the standard, formalized reporting structure.

Matrix Organizations are a blend of functional and projectized characteristics. Weak

matrices maintain many of the characteristics of a functional organization, and the

project manager role is more that of a coordinator or expediter than that of a manager.

In similar fashion, strong matrices have many of the characteristics of the projectized

organization—full-time project managers with considerable authority and full-time

project administrative staff.

Most modern organizations involve all these structures at various levels. For example,

even a fundamentally functional organization may create a special project team to

handle a critical project. Such a team may have many of the characteristics of a

project in a projectized organization. The team may include full-time staff from

different functional departments, it may develop its own set of operating procedures,

and it may operate outside the standard, formalized reporting structure.

• The advantages of a matrix organization are:

– More expertise: a matrix organization can maintain experts in specific fields

(communications, data bases, graphics etc.) who are then assigned to different

projects. A single project cannot always afford the luxury of maintaining

experts in all fields.

– Flexibility: it is easier to move people around from one project to another.

This results in better utilization of the available expertise.

– Emphasis on managing the project: the project manager is freed of many of

the staff management tasks, leaving more time to concentrate on the technical

aspects of the project.

However, matrix organizations also have significant disadvantages:

– Fewer management measures. One of the primary tools for generating

motivation, promotion, is taken out of the hands of the project manager. The

manager has little influence on the developer's salary and professional role in

the organization.

Software Project Management (CS615)

54

© Copyright Virtual University of Pakistan

– Lower staff loyalty. All employees like to know exactly who their superior is.

In a matrix organization, an employee has more than one superior. This causes

a division of loyalty, and a weaker bond between employee and manager.

These disadvantages often outweigh the advantages of the corporate matrix

organization.

Motivation is a major factor in the success of a project, and anything that

undermines motivation is usually contrary to the best interests of the project.

Unfortunately, the best interests of the project do not always completely coincide

with the best interests of the company.

Pyramid organizations provide a clear, well-defined hierarchy in which all

individuals know their own position and the positions of those above and below

them. When promotion and status play a major role in generating motivation (and

they often do), then the pyramid organization is most effective. Many other

factors generate motivation; Sense of achievement, praise and peer esteem, are

just a few.

Though promotion and status are not always the most effective motivators, a

project manager should rarely relinquish any effective management tool.

Therefore, from the perspective of a single project, the pyramid organization is

often the best.

⇒ Functional Structure

Most business organizations start out with a functional structure, or a small

variation of this structure. This is the basic "building block" for other structures.

In this structure, there is a central office which oversees various departments or

major functions, e.g., human resources, finances, sales, marketing, engineering,

etc. Think of a picture that has a box at the top labeled "Central Office". Think of

a row of boxes underneath the top box. Each box is labeled, e.g., sales,

engineering, human resources, etc. Connect the boxes with lines coming down

from the top box to each of the boxes below. Use functional structures when the

organization is small, geographically centralized, and provides few goods and

services. When the organization experiences bottlenecks in decision making and

difficulties in coordination, it has outgrown its functional structure.

The classic functional organization is a hierarchy where each employee has one

clear superior. Staff members are grouped by specialty, such as production,

marketing, engineering, and accounting at the top level, with engineering further

subdivided into functional organizations that support the business of the larger

organization (e.g., mechanical and electrical). Functional organizations still have

projects, but the perceived scope of the project is limited to the boundaries of the

function: the engineering department in a functional organization will do its work

Software Project Management (CS615)

55

© Copyright Virtual University of Pakistan

independent of the manufacturing or marketing departments. For example, when a

new product development is undertaken in a purely functional organization, the

design phase is often called a design project and includes only engineering

department staff. If questions about manufacturing arise, they are passed up the

hierarchy to the department head, who consults with the head of the

manufacturing department. The engineering department head then passes the

answer back down the hierarchy to the engineering project manager.

⇒ Project Structure

In this structure, there is a centralized corporate office and under it, are various

divisions each of which is dedicated to producing and / or selling a certain type of

business or product, e.g., product 1, product 2, etc. Each division that is dedicated

to a certain business or product is, in turn, is organized as its own functional

structure. So, for example, the division dedicated to making product 1 has its own

sales department, human resources, etc. Basically, project structure is a bunch of

functional structures each of which reports to one central office. Use a divisional

structure when the organization is relatively large, geographically dispersed,

and/or produces wide range of goods/services.

In a projectized organization, team members are often collocated. Most of the

organization’s resources are involved in project work, and project managers have

a great deal of independence and authority. Projectized organizations often have

organizational units called departments, but these groups either report directly to

the project manager or provide support services to the various projects.

􀀔 Structural dimensions:

􀂃 Centralization -the extent to which functions are dispersed in the

organization, either in terms of integration with other functions or

geographically

􀂃 Formalization - regarding the extent of policies and procedures in the

organization

􀂃 Hierarchy - regarding the extent and configuration of levels in the

structure

􀂃 Routinization - regarding the extent that organizational processes are

standardized

􀂃 Specialization - regarding the extent to which activities are refined

􀂃 Training - regarding the extent of activities to equip organization

members with knowledge and skills to carry out their roles

􀀔 Contextual Dimensions:

􀂃 Culture - the values and beliefs shared by all (note that culture is often

discerned by examining norms or observable behaviors in the workplace)

Software Project Management (CS615)

56

© Copyright Virtual University of Pakistan

􀂃 Environment - the nature of external influences and activities in the

political, technical, social and economic arenas

􀂃 Goals - unique overall priorities and desired end-states of the organization

􀂃 Size - number of people and resources and their span in the organization

􀂃 Technology - the often unique activities needed to reach organizational

goals, including nature of activities, specialization, type of

equipment/facilities needed, etc.

􀀔 Role and responsibility assignments

Project roles (who do what) and responsibilities (who decide what) must be

assigned to the appropriate project stakeholders. Roles and responsibilities may

vary over time. Most roles and responsibilities will be assigned to stakeholders who

are actively involved in the work of the project, such as the project manager, other

members of the project management team, and the individual contributors. The

roles and responsibilities of the project manager are generally critical on most

projects, but vary significantly by application area. Project roles and responsibilities

should be closely linked to the project scope definition. A Responsibility

Assignment Matrix (RAM) is often used for this purpose. On larger projects, RAMs

may be developed at various levels. For example, a high-level RAM may define

which group or unit is responsible for each component of the work breakdown

structure, while lower-level RAMs are used within the group to assign roles and

responsibilities for specific activities to particular individuals.

􀀔 Organization chart

An organization chart is any graphic display of project reporting relationships. It

may be formal or informal, highly detailed or broadly framed, based on the needs of

the project. For example, the organization chart for a three- to four-person internal

service project is unlikely to have the rigor and detail of the organization chart for a

3,000-person disaster response team. An Organizational Breakdown Structure

(OBS) is a specific type of organization chart that shows; which organizational

units are responsible for which work packages.

􀀔 Project Personnel

The staffing management plan describes when and how human resources will be

brought onto and taken off of the project team. The staffing plan may be formal or

informal, highly detailed or broadly framed, based on the needs of the project. It is a

subsidiary element of the overall project plan.

The staffing management plan often includes resource histograms. Particular

attention should be paid to how project team members (individuals or groups) will

be released when they are no longer needed on the project.

Appropriate reassignment procedures may:

Software Project Management (CS615)

57

© Copyright Virtual University of Pakistan

– Reduce costs by reducing or eliminating the tendency to “make work” to fill

the time between this assignment and the next.

– Improve morale by reducing or eliminating uncertainty about future

employment opportunities.

􀂃 Supporting detail

Supporting detail for organizational planning varies by application area and

project size. Information frequently supplied as supporting detail includes, but is

not limited to:

– Job descriptions (position descriptions) —written outlines by job title of the

competencies; responsibilities, authority; physical environment, and other

characteristics involved in performing a given job.

– Training needs—if the staff to be assigned is not expected to have the

competencies

Needed by the project, those competencies will need to be developed as part of

the project.

􀀔 Key Concepts in Design of Good Organization

Effective Organizational System provides assessment and training in

communication effectiveness through focus groups, retreats, workshops, and

experiential activities. Coaching addresses such skills as active listening,

constructive differing, conflict resolution, negotiation, mediation, persuasiveness,

and clarity in delivering a message. At the core of the training is the fundamental

premise that the role of communication is to create understanding. When

communication is effective, it promotes understanding and plays a fundamental role

in building interpersonal skills, leadership and strong teams.

An efficient organization is characterized by timely and productive systems and

procedures. At its extreme it has no spare capacity to plan ahead or to respond

easily to market changes.

An effective organization is characterized by the ability to pre-empt competitors,

respond swiftly and efficiently to changing situations, and display agility in its

structure and conduct of operations. It has efficient systems and procedures but has

the capacity to anticipate and plan ahead.

Organizational System provides assessment and training in communication

effectiveness through focus groups, retreats, workshops, and experiential activities.

Coaching addresses such skills as active listening, constructive differing, conflict

resolution, negotiation, mediation, persuasiveness, and clarity in delivering a

Software Project Management (CS615)

58

© Copyright Virtual University of Pakistan

message. At the core of the training is the fundamental premise that the role of

communication is to create understanding. When communication is effective, it

promotes understanding and plays a fundamental role in building interpersonal

skills, leadership and strong teams. Organizations that achieve high levels of

maturity in the people management area have a higher likelihood of implementing

effective software engineering practices.

– Span of control - the range of employees who to report to a managerial

position

– Authority - the formally-granted influence of a position to make decisions,

pursue goals and get resources to pursue the goals; authority in a managerial

role may exist only to the extent that subordinates agree to grant this authority

or follow the orders from that position

– Responsibility - the duty to carry out an assignment or conduct a certain

activity

– Delegation - process of assigning a task to a subordinate along with the

commensurate responsibility and authority to carry out the task

– Chain of command - the lines of authority in an organization, who reports to

whom

– Accountability - responsibility for the outcome of the process

– Line authority - the type of authority where managers have formal authority

over their subordinates' activities (the subordinates are depicted under the

manager on a solid line in the organization chart); departments directly

involved in producing services or products are sometimes called line

departments

– Staff departments - the type of authority where managers influence line

managers through staff's specialized advice; departments that support or

advise line departments are called staff departments and include, e.g., human

resources, legal, finance, etc.

Software Project Management (CS615)

59

© Copyright Virtual University of Pakistan

LECTURE # 7

2. Software Development Fundamentals

Management Fundamentals

2.1 Evolution of Software

The understanding about software and software development has come a long

way from the days of punch cards and Ada. In the first stage of computing,

hardware mattered the most. Computers themselves were the domains of the

government, and most software was developed in defense-funded labs, dedicated

to the advancement of science and technology in the national interest.

By the 1950s, large corporations realized the benefits of using computers. They

increasingly started using computers to process and analyze financial and

production data. These computers were huge in size. There was inadequate

software available for them. Even the software that existed was designed

essentially to function on a specific hardware product. The software was

developed and maintained by the company that manufactured the hardware.

Software design and documentation existed only in the developer's head. If the

developer left the company, you would find maintenance to be a nightmare.

In the second phase of software evolution, the corporate and academic sectors

increasingly started using computers, and the perspective about both software and

software development began to change. By the late 1960s and early 1970s,

concepts such as multi-sessions, multi-user systems, multiprogramming gained a

foothold. Soon computers were developed to collect, process, transform, and

analyze data in seconds. The focus of software development shifted from custom

software to product software. Now, multiple users on multiple computers could

use the same software. This phase of software evolution also saw the emergence

of software maintenance activities. These activities comprised fixing bugs, and

modifying the software based on changes in user requirements.

The third phase in software evolution was driven by the widespread use of

silicon-based microprocessors, which further led to the development of highspeed

computers, networked computers, and digital communication. Although, all

the advancement in software and hardware was still largely restricted to enterprise

applications manufacturers had begun to see the application of the microprocessor

in something as mundane as ovens to the robots used in car plants.

The fourth, and current, phase of software evolution began in the early 1990s.

This phase saw the growth of client-server environment, parallel computing,

distributed computing, network computing, and object-oriented programming.

Software Project Management (CS615)

60

© Copyright Virtual University of Pakistan

This phase also witnessed the growing popularity of personal computer (PC).

During this phase, the Internet facilitated easy accessibility of information. In

addition to complex software to support the advanced hardware, the scope of

software development widened to include software products for the common man.

Figure 1.1 sketches the path of software from the 1950s onwards.

• The Software Crisis

The rapid evolution of software design concepts and software development

methodology resulted in an ad hoc approach to software development. In the early

days of computing, stress was laid more on computer hardware than on software.

This happened mainly because hardware consumed the largest portion of the

project budget. Project managers closely followed the process of hardware

funding, budgeting, analysis and design, production, and implementation.

Software development, on the other hand, was left to the developers. There was

no training conducted, documentation maintained, or methodology followed for

software development. You will find that this attitude persisted until the 1970s,

when finally processes and methodologies for software design and development

began to be created. However, the ad hoc approach to software development that

Software Project Management (CS615)

61

© Copyright Virtual University of Pakistan

was prevalent in the early stages of software evolution hampered the application

of systematic processes. This conflict referred to as the software crisis. Some of

the reasons to which you can attribute the software crisis include:

– Software developers used-multiple programming languages.

– Software developers used multiple variations of standard programming

languages.

– Most of the requirements were complex with regard to the existing

capabilities,

– Users, who had little or no experience of developing or even using

software, formulated requirements.

– Software developers poorly mapped requirements to the actual product.

– Software developed had low interoperability.

– Software maintenance was costly.

– Hardware developed at a faster rate than software (better hardware

requires better software to operate it).

During the period of software crisis, you will find that software that was produced

was generally over budgeted, under scheduled, and of poor quality. The

immediate knee-jerk response to these problems was software maintenance,

which began to consume huge resources. During this period, maintaining software

was adopted as a short-term solution due to the costs involved in fixing software

regularly. This often resulted in the original software design approach getting lost

due to the lack of documentation.

In contrast, the situation in the present times has changed to a large extent.

Software costs have risen, although hardware is purchased easily off the shelf.

Now, the primary concerns regarding software projects are project delays, high

costs, and a large number of errors in the finished product.

2.2 Project Execution Fundamentals

Tracking

For the project manager, it is essential to be constantly informed of the true status

of the project. This is achieved by assuring the regular flow of accurate

information from the development teams. Many of the methods of acquiring

information are not objective and rely on the accuracy of the reports provided by

the project developers themselves. They include:

– Periodic written status reports

– Verbal reports

– Status meetings

– Product demonstrations (demos)

Product demonstrations are particularly subjective, because they demonstrate only

what the developer wishes to be seen. The project manager needs objective

Software Project Management (CS615)

62

© Copyright Virtual University of Pakistan

information. Such information can often be acquired from reports produced by

support groups, such as:

– Quality assurance reports

– Independent test reports

Although reports and meetings are indeed useful sources of information, nothing

can replace direct contact between the project manager and the development staff.

Frequent informal talks with the developers are excellent sources of information,

especially when held in an informal atmosphere (and not in the project manager's

office).

The project manager must keep on constant guard against an error commonly

referred to as the '90/50 syndrome’, which states that, 'it takes 50 percent of the

time to complete 90 percent of the work, and an additional 50 percent of the time

to complete the remaining 10 percent of the work'. This means that project

developers will begin to boast quite early that they have 'almost finished' their

tasks. Unfortunately, there is a great difference between 'almost finished' and

‘finished'.

Finishing a task -writing documentation, and polishing off the last few problems,

often takes longer than developers anticipate. This is because these activities

produce very few visible results, and developers tend (wrongly) to associate work

with results. Therefore, managers can obtain more information from developers

by asking them how long they estimate it will take to finish, and not how much of

their work has been completed.

• Status reports

Status reports should be required from every member of the development team,

without exception. The reports should be submitted periodically, usually weekly

or bi-weekly, and should contain at least the following three sections (see Fig.

5.8):

1. Activities during the report period

Each subsection within this section describes a major activity during the report

period. The description of each activity should span two to three lines. Activities

should be linked to the project task list or work breakdown structure (WBS) (see

Chapter 10 for a description of the WBS).

2. Planned activities for the next report period

Each subsection within this section describes a major activity planned for the next

report period. The description of each activity should span one to two lines.

3. Problems

Software Project Management (CS615)

63

© Copyright Virtual University of Pakistan

Each subsection within this section describes a major problem that either occurred

during the report period, or that was reported previously and has not yet been

resolved. This means that problems will be repeatedly reported until they are

resolved. In particular, this section must explain why this report's Section 1 does

not correspond to the previous report's Section 2.

All reports should also contain:

1. Date of report

2. Report period (e.g. 3 July to 10 July 1992)

3. Name of report (e.g. Communications team status report)

4. Name of person submitting the report

The preparation of a periodic status report should take about 20 minutes, but not

longer than 30 minutes. Developers should submit their status reports to their

team leader. The team leader then combines the reports of the team into a single

status report, while maintaining the same report structure. This activity should

take the team leader about 30 minutes, but not longer than 45 minutes (this is

easily done when the reports are prepared and submitted by electronic mail).

Each team leader submits the team status report to the project manager. The

individual status reports need not be submitted; these should be filed and

submitted to the project manager only on request.

Software Project Management (CS615)

64

© Copyright Virtual University of Pakistan

From: John Doe, Team leader

To: Frank Smith, Project Manager

Date: 15 June 1993

User interface team: Weekly status report

for the period 5-12 June 1993

1. Activities during the report period:

1.1 The design of the user help screens (activity 3.12.6) was completed on schedule.

The design specs were submitted to configuration control.

1.2 Coding of the command pass through modules (activity group 5.12) continues, and is

currently behind schedule by about 1 week.

2. Activities planned for next week:

2.1 Coding of the command pass through modules (activity group 5.12) will be

completed, and unit tests will be started.

2.2 Two members of the team (Ed and Joan) will attend a two day course on the

Programmer’s interface to the new user interface package. This is an unscheduled

activity that was approved at the last project meeting. This will not delay the

schedule, due to the early completion of the command pass through modules (see

Section 1.2 above).

3. Problems:

3.1 The user interface package we originally planned to use was found to be inadequate

for the project. Two team members will study the new proposed package (sec Section 2.2

above). If the new package is also found to be unsuitable, then this will severely impact

our development schedule.

3.2 One of our team members (Jack Brown) has been using an old VTI00 terminal

instead of a workstation for the past two weeks, due to the acute shortage of

workstations. This is the reason why Jack's task 5.12 was not completed this week, as

scheduled.

Figure 5.8: Example of a weekly status report

The project manager also receives status reports from other project support

personnel such as the project systems engineer or the deputy project manager. The

project manager then prepares the project status report by combining the

individual reports received into a single three-part report. The project status report

is then submitted to top management.

Software Project Management (CS615)

65

© Copyright Virtual University of Pakistan

Project status reports are not necessarily submitted at the same frequency as

internal project status reports. Project reports may be submitted bi-weekly or

monthly.

• Project status meetings

Project status meetings should be held periodically, usually once a week. A good

time for status meetings is either at the end of the last day of the week, or at the

beginning of the first day of the week. Status meetings also contribute to the

atmosphere of order and control within the project, and should be held regularly,

at a fixed time. Participants who cannot participate in the project status meeting

may, with the project manager's approval, delegate participation to another

member of their team.

The project manager prepares for the status meeting by reviewing the status

reports submitted by the key project members (particularly scrutinizing the

problem section). Therefore the status reports should be submitted at least two to

three hours before the status meeting. Project status meetings are attended by the

key project members. The meeting begins with a report of project activities and

general issues by the project manager. Then each participant should be given

about five to ten minutes to report on the activity of his or her team or area of

responsibility. The discussion of problems should not be restricted to the person

reporting the problem and the project manager. All problems may be addressed by

all participants, with possible assistance offered between team leaders, thus

making their experience available throughout the project. It is not the project

manager's role to provide solutions to the problems, but rather to guide the team

members toward solutions.

Solutions should be worked out whenever possible during the status meeting. Any

problem not resolved within five minutes should be postponed for discussion by

the relevant parties after the status meeting. The proceedings of all project status

meetings must be recorded. Verbatim minutes are not required, though the

following items should appear in the record:

1. Date of meeting

2. Name of meeting

3. Present (list of participants)

4. Absent (list of absent invited participants)

5. Action items (name, action, and date for completion)

6. Major decisions and items discussed

The record of the project status meeting should be typed and distributed as soon

as possible, but no later than by the end of the day. This is particularly important

when there are action items to be completed on the same day. When the project is

sufficiently large to justify a secretary, then the record will be taken and typed by

Software Project Management (CS615)

66

© Copyright Virtual University of Pakistan

the secretary. In smaller projects, the project manager can rotate this task each

week between the participants.

2.3 Software Project Management Framework

You all know that a project is much more than a collection of methodologies,

tasks, resources, and reviews. A project is a synchronized event where there is

perfect harmony and understanding between the participants. The participants are

equipped with the essential skills of planning, cooperating, helping, and

communicating. However, the most important activity here is to orchestrate the

movement of the participants. The onus lies with the project manager to

synchronize the activities of the project to result in a perfect presentation.

Although each project manager has a unique style of functioning, there are some

fundamental approaches that guide a project manager. These approaches are

traditional project management concepts and software engineering concepts. To

understand software projects and their dynamics, you must be aware of the

environment in which a software project is executed. This further requires an

understanding of the larger framework of software project management.

In this chapter, you will learn to, build a connection between traditional project

management concepts and software engineering concepts. Both traditional and

software projects share the same methodologies, techniques, and processes.

However, managing software projects requires a distinct approach. In this,

chapter, you will learn to apply traditional project management principles to

software projects. Further, you will learn about the responsibilities of a software

project manager. You will also learn about the phases in a software project and

the activities within each phase. Finally, the chapter will provide you an overview

of the problems that affect a software project and the myths prevalent about

software project management.

2.4 Software Development Life Cycle (SDLC)

The development of a software project consists of many activities spread across

multiple phases. Dividing a software project into phases helps you in managing

the complexities and uncertainties involved in the software project.

2.5 Phases of a Software project

Each phase represents the development of either a part of the software product or

something associated with the software project, such as user manual or testing.

Each phase is composed of various activities. You can consider a phase complete

when all activities are complete.

Software Project Management (CS615)

67

© Copyright Virtual University of Pakistan

A phase is named according to the primary deliverable set that is achieved at the

end of that phase. For example, if the requirements document is required as the

output, the phase is called the requirements phase. Similarly, most software

projects have phases for analysis, design, construction, implementation, and

testing.

A typical software project includes the following phases:

– Software requirement analysis phase

– Software Design Phase

– Software Planning Phase

– Software construction phase

– Software testing phase

– Software acceptance and maintenance phase

2.6 SDLC Models

Different organizations have different ways of assessing and arranging the phases

in a project. These are called process models. Process models define how a

software life cycle actually works. They provide you with a framework to plan

and execute the various phases in the project. Typically, project life cycles display

the following characteristics:

• The level of cost and effort required in a software project life cycle is small to

begin with but grows larger towards the end of the project. This happens

because the phases such as software construction and implementation, which

come at later stages in a software project, require more resources than the

initial phases of the project.

• At the start of the SDLC, external entities, such as the customer and the

organization, play an important role with regard to their effect on the

requirements. However, towards the end of the software project as the cost

and effort required to implement changes rise, the requests for change in

requirements decreases.

• The uncertainty faced by the software project is highest at the beginning of the

SDLC. Their level decreases as the project progresses.

There are a few standard software process models that you can use, with some

customization. Some standard process models are given below:

• The Waterfall model: This is the traditional life cycle model. It assumes that

all phases in a software project are carried out sequentially and that each

phase is completed before the next is taken up.

• The Prototyping Model: A model that works on an iterative cycle of gathering

customer requirements, producing a prototype based on the requirement

specifications, and getting the prototype validated by the customer. Each

Software Project Management (CS615)

68

© Copyright Virtual University of Pakistan

iteration of the life cycle builds on the prototype produced in the previous

iteration.

• The Incremental Model: The Incremental model is an example of an

evolutionary life cycle model. It combines the linear nature of the Waterfall

model and the iterative nature of the Prototyping model. The Incremental

model divided the development life cycle into multiple linear sequences, each

of which produces an increment of the final software product. In this model,

the software product is developed in builds. A build is defined as a selfcontained

unit of the development activity. The entire development cycle is

planned for a specific number of logical builds, each having a specific set of

features.

• The Spiral model: Another evolutionary life cycle model that combines the

linear nature of the Waterfall model and the iterative nature of the Prototyping

model. The project life cycle is divided into phases, and each phase is

executed in all of the iteration of the Spiral Model.

Software Project Management (CS615)

69

© Copyright Virtual University of Pakistan

LECTURE # 8

2. Software Development Fundamentals

Management Fundamentals

2.7 Organizational Issues and Project Management

Organizational issues have a deep influence on a software project, its progress,

and the role of the project manager. The policies of an organization can affect the

way the organization handles the customer, different types of technologies, and

different software projects. The organizational issues that can influence a software

project include:

• Reaction to external influences

• Interest in adherence to standards

• Definition of core competency area

• Existence of knowledge management system

• Interest in human resources

One organizational issue that can influence a software project is the reaction of

the organization to external influences.- As a project manager, it is important for

you to assess how the organization reacts to changes in the external environment,

For example, in the current technology environment that changes rapidly, an

organization should be proactive in strengthening its capability baseline by

adopting new technology and retraining its employees as per market

requirements.

Interest in adherence to standards is another organizational issue that can

influence a software project. The current technology environment is highly

dynamic. Various nonprofit and independent organizations have developed

protocols and standards for the standardization of software development and

measurement: For example; the Software Engineering Institute at the Carnegie

Mellon University has developed the Capability Maturity Model (SEI-CMM).

The CMM rates the processes of a software development organization and

classifies it into five maturity levels. Software development organizations can also

get the quality-related certifications issued by the International Standards

Organization smoothen your project management tasks by standardizing the

internal processes and optimizing performance.

Definition of core competency area also influences a software project. An

organization that creates software must understand how they are created and

establish processes accordingly For example, if the core competency of the

organization lies in manufacturing chemicals, it should preferably not attempt

Software Project Management (CS615)

70

© Copyright Virtual University of Pakistan

software development for such an organization, it is better to purchase an off-theshelf

software product.

An organizational issue that positively influences the tasks of software project

managers is the presence of a good knowledge management system within the

organization. Knowledge management is the collection of processes that control

the creation and utilization of knowledge within the organization. A good

knowledge management system allows you to access relevant information and

make informed decisions.

Another organizational issue that can influence a software project is the interest of

management in human resources. The human resources of an organization are its

primary resource. You need to ensure that the people in the development team

enjoy a comfortable work environment, which is conducive for smooth and

trouble-free work. This includes providing suitable compensations, a friendly

work environment, and smooth processes. The absence of these factors negatively

affects employee morale, and therefore, productivity.

2.8 Managing Processes

As a software project manager, you become the key player in a software project.

You not only manager the day-to-day activities of the project but also ensure that

the software product is delivered on time. What makes your role challenging is

the performance of project-related activities within a specified budget and time

constraint. At the same time, you need to keep the requirements and specifications

of the customer in mind.

To deliver expected results, you carry out three successive processes: studying the

feasibility of the project, planning to meet the requirement, and executing the

plan. These processes can be further broken down into activities, such as

planning, staffing, and monitoring.

You plan and organize the software development team to complete development

within the stipulated time and budget. To do this, you form a team of people who

have the required technical skills. Then, you ensure that all activities are carried

out as planned by the relevant people.

Your responsibilities include analyzing customer requirements, determining the

scope of the software project, allocating resources top the project, scheduling the

project, and executing the project. These responsibilities can be considered in

terms of the areas where management skills are required. The primary software

project management areas that you need to concentrate on include:

• Managing Resources

• Managing Cost

Software Project Management (CS615)

71

© Copyright Virtual University of Pakistan

• Managing Risk

• Managing Schedule

• Managing the project plan

• Managing quality

⇒ Managing Resources

The primary input required to create software are resources. Resources for a

software project may be of three kinds: human, hardware, "and software. Human

resource management is about effectively identifying the people with the

appropriate skills, assigning roles and responsibilities to these people, and

establishing reporting relationships. On the other hand, hardware and software

resource management relates to identifying and ensuring resources such as

workstations, disk space on servers, software tools, and software licenses. You

need to ensure that human resource identification and allocation is carried out;

simultaneously with hardware and software resource management.

To manage resources effectively, there are two areas that you require your

attention. These include:

• Management of human resource

• Identification of the critical hardware and software resources

Management of human resources calls for a number of actions. First, you define

reporting relationship for the software project. Reporting relationship can exist

within and across organizational units, technical areas, and hierarchical levels.

Next, determine the skills required for the software project, and identify the

appropriate people who possess the required skills. You can review the resource

pool and identify resources on the basis of their experience and availability. In

case the resources are unavailable, you request for their release from another

project or outsource the required resources. Depending upon the organizational

practices arid experiences from past projects, you can assign roles and

responsibilities to the development team. Finally, create a staff management plan

and an organizational chart to show the hierarchical structure of the development

team.

Management of human resources also requires efficient team development. This

is a complex activity because it combines managing people and organizing the

reporting structure within the team. You can build cohesion and commitment

within the team through team building activities. These activities include

conducting team meetings to involve people from areas other than management

into decision-making.

To manage human resources, you also need to implement a reward and

recognition system. This helps in promoting and reinforcing positive

performance. It is important that you make the link between the performance and

Software Project Management (CS615)

72

© Copyright Virtual University of Pakistan

reward explicit and achievable. You should also ensure that the training needs of

the development team are met.

A second resource management area that requires attention is identification of the

hardware and software resources that are critical for the project. As a software

project manager, you must identify all the critical hardware and software

resources and document them in the project plan. After the required resources are

identified, you define control limits for each resource. Control limits for a

resource are the upper and lower limit beyond which the resource is above or

below the required level. For example, if a software project requires disk space on

the central server, the control limits for the disk space are the required maximum

and minimum disk space. Note that not all hardware and software resources are

critical to the success of a software project. In some software projects, you may

not find any critical resource at the beginning. However, as the project progresses,

some resources might become critical. For efficient resource management, you

should periodically assess hardware and software resource requirements for the

software project. Just as a resource may become critical as a project progresses, a

resource might also become less critical over a period of time. Therefore; plan,

assess, and take corrective action for all the resources through the duration of the

software project.

⇒ Managing Cost

The cost factor has a considerable influence on the execution of a software

project. The budget of a software project is affected by factors, such as the current

orientation of the organization toward software development, number of skilled

personnel available, infrastructure, and computer hardware and software. The

budget can also be influenced by timely availability of resources. If a particular

resource is allocated to the project later than required, the costs involved could go

up drastically.

Quite often, when a software project starts to become too expensive, many project

managers also tend to start cutting costs. This can have a direct impact on

employee morale. When employee morale drops, so does the quality of work, and

the productivity. Therefore, as a project manager you must prepare for all

circumstances through proper estimation and allocation. To manage costs for

software projects, you need an accurate estimation of costs. To do that, there is a

sequence of steps that you need to perform.

• Identify the resources required for the project

• Estimate the cost of each activity

• Set cost baselines for each activity

• Implement a control system for cost changes

To estimate costs, you first identify and describe all the resources required in the

software project. You also estimate the duration for which the resources are used.

Software Project Management (CS615)

73

© Copyright Virtual University of Pakistan

Next, estimate the cost of each resource. To estimate the cost, you can use

mathematical tools. However, in the case where limited information is available

about resources, you can also use expert judgment to estimate costs.

After the costs of the required resources are estimated, you set cost baselines for

each activity. Cost baselines measure the performance of an activity with regard

to the cost and duration defined for the completion of the activity.

Finally, as the project manager you implement a control system for cost changes.

The cost control system defines cost baselines, identifies cost changes, and

modifies cost baselines to adjust cost changes.

⇒ Management Risk

Risk management is an integral part of project management. In software projects,

where uncertainties are very high, risk management and mitigation is even more

critical. Taking risks for high payoffs might bring in high profits but not without

the danger of losses. Risk on a small scale is acceptable to most project managers

as the element of loss is minimal. However, large risks pose a danger to the

progress of a software project and you need to manage them. Risk management

activities involve identifying potential risks, assessing them, and planning for

contingent actions if a risk materializes.

As a project manager, you perform two primary activities to manage risks for

software project:

• Risk Analysis

o Risk identification

o Risk quantification

• Risk management

The first activity in risk analysis is risk identification. Risk identification helps

you point out the, potential risks for a software project across all phases of the

project. Risks might evolve through the duration of a software project, and

therefore, risk identification is an ongoing activity. To identify potential risks for

a software project, you can analyze the activities in the software project, the

software product description, and risks faced by the development team in similar

past projects. This exercise allows you to identify the potential sources of risks to

the current software project, Assessing the factor influencing the different inputs

also allows you to identify the phases in the SDLC when risk might materialize.

After potential risks have been identified, you can quantify them. This is done to

ascertain their priority. If multiple risks materialize at the same time, then you

must assign a priority to each risk based on the degree of impact on the project

and handle the highest-risk events first. For example, the risk of change in client

Software Project Management (CS615)

74

© Copyright Virtual University of Pakistan

requirements during the software construction phase is a higher risk than a

deadline for a deliverable being missed. Therefore, you first manage the risk that

has a higher priority. To quantify project risks, you can use various mathematical

and statistical tools. You can also use expert judgment to assess and quantify

risks.

After you have identified and quantified the potential risks for a software project,

you create a risk mitigation plan. The purpose of the risk mitigation plan is to help

you identify procedures to choose the path of least damage and highest returns in

a case a risk materializes. To mitigate risks for a software project, you first need

to be aware of the opportunities and threats that can be pursued or ignored. This

enables you to focus on the risks that might have a negative impact on the

software project and develop contingent plans to deal with these risks. You can

also mitigate risks by evolving alternative strategies to altogether prevent

potential risks from materializing.

In case an unplanned risk materializes, you must be aware of the dependencies of

the project activities so that ad hoc solutions can be evolved. However, as the

project manager you can avoid unplanned risks from materializing by engaging in

an intensive risk identification and mitigation exercise before the software project

commences.

⇒ Managing Schedule

Time is a major constraint for a software project. With most software projects, the

delivery dates for the software product are already committed to the customer at

the time the project commences. As a software project manager you must perform

various tasks to balance time and deadlines. These are:

– Identify the different deliverables that constitutes the software product

– Define the activities that are required to produce the deliverables

– Identify the interdependencies between activities

– Define the duration of each activity

– Assess the project network diagram

– Create a schedule management and control plan

The first task is to identify the different deliverables that constitute the software

product. These deliverables also mark the completion of the different phases

within a software project.

Next, define the activities that are required to produce the deliverables. To do this,

you can break down the SDLC into phases, identify the deliverables at the end of

each phase, and the activities required for creating the deliverables.

Software Project Management (CS615)

75

© Copyright Virtual University of Pakistan

After the activities are defined, you identify the interdependencies between them.

The purpose of this exercise is to organize the activities and sequence them in the

form of a project schedule.

Next, you define the duration of each activity. The inputs that you need for

scheduling are the resources required to complete each activity. Then, assesses the

availability of these resources and the duration of each similar activity in similar

past projects.

After estimating the time required for each activity to complete, you assess the

project network diagram. This includes an assessment of the duration estimates,

resource requirements, resource pool description, and assumptions and constraints

for the software. You can use Mathematical tools to determine a schedule for the

project. The project schedule defines the activities within each phase, the team

members assigned to complete each activity, the duration of each activity, and the

start and end dates for all of the activities.

Finally, create a schedule management and control plan. The purpose of this plan

is to identify when changes occur, Implement the changes to the project schedule,

and ensure that the changes are beneficial to the software project. After the

changes are implemented, you might need to modify the sections of the project

plan to ensure that the project is completed on time.

Software Project Management (CS615)

76

© Copyright Virtual University of Pakistan

LECTURE # 9

2. Software Development Fundamentals

Management Fundamentals

2.8 Managing Processes

⇒ Managing the Project Plan

Preparing it project plan for a software project helps you ensure that the specified

requirements and objectives are met successfully. It is a collation of all planning

activities that have happened for a software project. This includes activities such

as design and analysis, activity definition, risk planning, and cost estimation. To

create the plan, you assess all planning activities, organizational policies

regarding the creation of the project plan and assumption and constraints for the

project. To implement the software project plan, you require management skills,

such as leadership, communication, and problem solving, along with the basic

knowledge about the software. You also need to ensure that the senior

management bf the company has authorized work on the software project.

Knowledge management techniques help you to make informed decision

regarding the project plan.

After the project plan is executed, you manage the changes to it in such a way that

the performance measurement baselines are not impacted, To manage the project

plan effectively you monitor the project plan, periodic performance status reports,

and requests for change. The primary tool that you can use to control the changes

in the project plan is the change control mechanism: This is a set of formal

procedures for changing the project plan.

⇒ Managing Quality

The quality of software development depends largely on the understanding of

‘quality’ and quality management within the software development team. In

software projects where each member has a different understanding of quality and

his or her role in implementing it, the software product is usually not of the

required quality.

Implementing software quality is often associated with the software developer.

However, the role of the project manager is crucial in implementing quality

awareness and a quality-producing work environment. When a software project

starts missing deadlines and is in danger of exceeding the budget, project

managers often lose the focus on quality and lay stress on meeting deadlines.

However, the focus should be the other way round. A focus on delivering a

Software Project Management (CS615)

77

© Copyright Virtual University of Pakistan

quality product, even at the cost of missing a deadline or two ensures that your

customer comes back for repeat orders. On the other hand, the price of nonconformance

(PONC) on quality standards simply translates into the loss of

goodwill and loss of business.

Modern quality management techniques compliment project management and the

role of the project manager. Quality management techniques ensure that a

software product conforms to the customer requirements. Quality management

further ensures that errors are prevented in the first round itself. Checks for errors

and effort for removing the errors consume much more time, effort, and cost than

it takes to prevent the errors in the first place. Therefore, maintaining quality in a

software project is the domain of all team members.

However, as the project manager you have a critical role in maintaining quality.

You provide the resources required to complete the activities of the software

project and ensure that quality levels are constantly monitored.

You first identify the areas that must be monitored for ensuring quality and the

quality measures to implement. Then, consider the quality policy of the

organization, the scope of the project, the applicable standards, and the software

product description. Next, use tools, such as a cost-benefit analysis and a

flowchart, to identify the areas where you need to monitor quality and the

subsequent actions for control. The output of this exercise is the quality plan for

the software project. In addition, this exercise allows you to create checklists to

help monitor quality.

As a software project manager, you also need to use a quality control mechanism

so that the quality of the software product does not suffer. The aim of the quality

control mechanism is to ensure compliance with quality standards.

2.9 Project Execution

You already learned in the beginning of the chapter that a software project is

divided into different phases. This division is done on the basis of the activities

performed in each phase. Similarly, project management activities are also

arranged in phases. As a project manager, you perform the activities that map to

each of these phases. The project management phases can be broadly categorized

as follows;

– Project initiation

– Project closedown

– Project planning, control, and tracking

– Product implementation

• Project Initiation

Software Project Management (CS615)

78

© Copyright Virtual University of Pakistan

The tasks performed for project initiation are mentioned below:

Requirement gathering: The first task is to gather the customer requirements.

Customer requirements may be spoken or unspoken. Therefore, the challenge for

the project manager is to elicit the requirements in such a way that both the

spoken and unspoken customer needs and wants are gathered. After collecting the

required information, you need to translate the customer requirements into

technical specifications for the software project.

Scope determination: The scope of a software project can be defined as the

combination of the software product arid services to be delivered to the customer.

You carry out the scope determination exercise to define the scope of the software

project. The scope determination exercise enables you to refine and understand

the customer requirements. You can refine the scope definition further by

breaking down each deliverable into smaller and more manageable activities. The

scope determination exercise also helps you identify the technology for creating

the software product.

Resource allocation: During project initiation, you identify the resources required

and allocate them to the software project. The resources identified may be people,

reusable software components, and hardware or software tools. You allocate the

resource to the software project on the basis of the activities defined in the scope

determination exercise. While allocating appropriate resources for a software

project, you also need to calculate the cost of each resource. The cost of a

resource is calculated according to the duration of the resource in the software

project. Estimating the cost of resources also helps you prepare a budget for the

software project.

Note:

Scope determination and resource allocation are discussed in more detail in later

chapters.

Initial project plan: Another exercise that you carry out during project initiation

is the creation of a rough project plan. This plan is a draft version and carries only

the primitive project plan features. This project plan carries the initial risk

analysis of the software project, the initial start and end dates, the duration of the

activities in the project, and the sequencing of these activities.

• Project Planning, Controlling, and Tracking

This activity of the project manager involves detailed tasks. These tasks are

mentioned below:

Detailed project plan: After the scope for the software project is determined and

the product design is ready, you prepare a detailed project plan. To create a

detailed project plan, you define a detailed list of all the elements that make up the

Software Project Management (CS615)

79

© Copyright Virtual University of Pakistan

project deliverables. Next, the deliverables are further broken up to help In the

calculation of durations, start dates and end dates for each activity mentioned in

the plan. Roles and responsibilities are assigned to people with the appropriate

skills to complete each activity within specified time.

Control mechanism: These are set up to control the impact of changes on the

software project. The control mechanism includes a detailed risk management and

mitigation plan, a detailed quality plan, and quality assurance activities. You also

implement a review and audit system for periodic assessment and measurement of

the software project activities. The review and audit system enables you to

evaluate the progress of the software project. It ensures that all necessary data is

collected, deviation from the planned baselines is checked, and corrective action

is taken at all checkpoints. In this way, the review and audit system ensures

compliance with the organizational processes for software development.

Software Project Management (CS615)

80

© Copyright Virtual University of Pakistan

LECTURE # 10

2. Software Development Fundamentals

Management Fundamentals

2.9 Project Execution

⇒ Product Implementation

Product implementation activities involve defining processes related to the

implementation of the software product at the customer site. Some of the tasks

that you perform for product implementation are mentioned below:

• Implementation plan creation: An implementation plan defines the duration of

implementation and the hard and software perquisites for implementing the

software product.

• Support plan creation: the project manager also needs to create a support plan for

the customer. The support plan includes consideration such as the postimplementation

support activities provided to the customer. Post-implementation

considerations include the number of support staff available to the customer, their

names, contact numbers, and the duration of their availability.

• Training plan creation: During product implementation, you create a training

plan to train the customer on the software product. The training plan includes

considerations such as the duration of training, the prerequisites for training

people, and the number of people that can be trained simultaneously.

• User acceptance plan: You also need to prepare a user acceptance plan. The user

acceptance plan provides a detailed outline on how and when the user acceptance

tests are performed. The primary focus of user acceptance test is to ensure that the

final software product offers all the functionality and performance that the

customer wanted. Therefore, the customer tests the software product for issues

such as aesthetics, user friendless, and scalability.

⇒ Project Closedown

The final activity for a project manager is project closedown. For most software

projects, the project closedown activities take place in the post-implementation

phase. However, in some software projects, the customer requests support

activities for a longer duration. In such cases, the software project is considered

Software Project Management (CS615)

81

© Copyright Virtual University of Pakistan

closed immediately after implementation. The tasks that you perform in project

closedown are mentioned below:

• Prepare closedown report: The project closedown report contains the results of

the causal analysis that you do for the project. This contains an analysis of what

went wrong, what went right, and what you could have done better in the software

project.

• Identify learning: You also need to assess the entire software project and the

results of the causal analysis to identify the key learning points from the software

project. This helps you identify areas of improvement for future projects. The

learning points can also be used by the organization as considerations while

planning and executing the next software project.

• Identify reusable software components: Reusing software components enables

you to lower the cost, time, and effort required to complete the software project

successfully. After project closedown, you identify the software components that

can be reused in future projects of similar nature. The software components

prepared for a software project may be complete, partially complete, or in the

design stage. These components or their designs can be assessed for usability in

future projects.

• Create reference material: After the project is complete, you can create white

papers and reference documents. This can be a significant contribution to the

organization and the application area of the software by creating an authoritative

knowledge base.

2.10 Project Management Myths

In most cases, you learn the skills required to manage a software project while on

the job. As a result, most software project managers practice a lot of management

techniques that are of doubtful authenticity. Many software project managers

learn about the so-called management skills and concepts that are actually myths.

⇒ Clarifying the Project Management Myths

The following list aims to clarify some of the more prevalent myths in software

project management.

1. Combining the best resources with the worst resources available for a

software project helps to complete the project successfully.

2. A general statement of objectives is sufficient to begin work on the software

project.

Software Project Management (CS615)

82

© Copyright Virtual University of Pakistan

3. Allocating extra resources to a late project allows it to catch up with the

project schedule.

4. As software by itself is flexible, you can change the requirements at any point

in the software project life cycle.

5. The management and the customer always impose an unrealistic deadline for

the software project.

6. A software project that meets all the stated objectives is a success.

7. Software maintenance is an easy task and requires less effort than actual

software development.

8. Identifying and reporting errors during the reviews makes the software

developer unhappy and spoils the work environment.

9. Web-enabling an application or adopting client/server; architecture helps to

run software projects smoothly.

Myth: Combining the best resources with the worst resources available for a project

helps to complete the project successfully.

In software projects, combining the best resources with the worst resources drags

down the efficiency and productivity of good resources. This invariably decreases

the speed of the software project, and the project ends much after the specified

deadline.

Myth: A general statement of objective is sufficient to begin work on the software

project.

Many software project managers and customers believe that a general statement

of objectives gives a reasonable idea of the requirements. However, a formal and

detailed description of the customer requirements is needed before the project

commences. The software project manager must ensure that all information

regarding the software project, such as the functions, performance, interfaces,

constraints, assumptions and validation criteria is gathered.

Myth: Allocating extra resources to a late project allows it to catch up with the

project schedule.

A software project is not a mechanical process such as, say; digging an artificial

lake. In case of creating an artificial lake, adding more people to the job can help

dig a larger area in the same time. However, in a software project, adding, more

people actually increases the time required to finish the project. This happens

because a new person joining the project requires time to understand the

Software Project Management (CS615)

83

© Copyright Virtual University of Pakistan

requirements of the client, software design, and standards. Moreover, the existing

people in the project need to devote time and effort to train the new people on the

software project. Therefore, allocating additional resources to a risky situation

increases the risk to the software project.

Myth: As software by itself is flexible, changes in the requirements can be made at

any point in the software project life cycle.

Requests for changes are common with all projects. However, the timing of the

change for requests is critical. This is because an untimely change adversely,

impacts the cost of the software project. For example, a change request during the

requirements gathering stage has a relatively low impact on costs. On the other

hand, a change request during, the software construction stage can be extremely

expensive to incorporate. The software project manager must decide with the

customer upon a set of objectives that must be achieved at the end of the project.

In addition, the project manager and the customer must decide on a specific

phase, beyond which only critical change requests are accepted.

Myth: The management and customer always impose an unrealistic deadline for the

software project.

The management and customer usually believe that project managers prepare cost

effort, and time estimates inclusive of buffers. The management and customers

rationalize that if they can cut the buffers by imposing a tight deadline or a low

budget on a project, the project manager would still complete the project on time.

Myth: A software project that meets all the stated objectives is a success.

Customer requirements for a software project are always in two forms, spoken

and unspoken. Usually, the objectives formed from the customer requirements are

based on the spoken requirements. The software project manager must to be

aware of the unspoken requirements and ensure that these are met.

Myth: Software maintenance is an easy task and requires less effort than actual

software development.

If change requests are made toward the end of the project, then maintenance

activities can contribute to large costs and effort overruns. Moreover, contrary to

the popular view, implementing changes in the software product in the

maintenance stage is a painstaking task.

Myth: Identifying and reporting errors during the reviews makes the software

developer unhappy and spoil the work environment.

Software Project Management (CS615)

84

© Copyright Virtual University of Pakistan

If a developer makes an error, it is important to point it out so that the error is

fixed in time. A project manager must communicate assertively so that the team

does not lose focus on quality. In addition, letting an error pass may have ripple

effects on the quality of the software product, frustrating the entire team.

Myth: Web-enabling an application or adopting client / server architecture helps to

run software projects smoothly.

No single technology platform, language, or architecture is a one-point solution

for all software projects. All approaches to software development have unique

merits and demerits. For example, if a marketing firm needs to make information

accessible to people at remote locations, then a, Web-based application is a good

option. However, mainframes are still preferred for applications created for the

banking industry.

Software Project Management (CS615)

85

© Copyright Virtual University of Pakistan

LECTURE # 11

2. Software Development Fundamentals

Management Fundamentals

2.11 Problems in Software Projects

Software projects are similar to traditional projects in the sense that the same

types of problems affect them both. However, the difference in managing these

problems lies in the approach that you take to the specific issue. For example, a

technology-related problem for a software project might be the low degree of

reuse of the software components created. However, for a car-manufacturing firm,

there is no chance of reusing a component such as a front axle.

You can classify the problems that affect software projects into the following four

categories:

• People-related problems

• Process-related problems

• Product-related problems

• Technology-related problems

⇒ People-related problems

People-related problems in a software project are:

• Low motivation: As the project manager it is your responsibility to ensure an

optimal level of motivation within the team. Lengthy projects, complex

activities1 and scarce resources often decrease the motivation level in a

software development team. However, you need to lead in such a way that the

team is constantly motivated to do a good job.

• Problem employees: Some members of any team always create a problem. For

example, an employee may carry a 'holier-than thou' attitude. Problem

employees raise the chances of conflicts and differences of opinions within

the development team. They lower the efficiency and productivity of other

team members and make it difficult to meet the objectives of the software

project within the specified time. You need to ensure that employees are not

allowed to create a pr9blem for the rest of the team. Even if the employee is

very competent, you need to assess the indispensability of such emp1oyees for

the project. Moreover, you refrain from playing favorite with certain

employees and treat everyone with the same measure.

Software Project Management (CS615)

86

© Copyright Virtual University of Pakistan

• Unproductive work environment: The work environment is a major factor

that affects the productivity of the development team. For example, a noisy or

cramped workspace decreases the motivation levels of the employees.

Similarly, unfriendly organizational policies also lower the motivation of the

team members. As the project manager, you need to ensure that the team is

protected from harmful external make the workspace friendly to work in.

• Inefficient project management style: the project manager needs to lead by

example. The team members absorb the work culture, work ethic, and attitude

of the project manager and implement it in their work style. If you display a

lack of leadership qualities and weak ideals, the motivation levels decrease

across software team.

• Lack of stakeholder interest: For a software project to be a success, each

stakeholder needs to take an active interest in the progress of the project. Al1

stakeholders, including the customer, the management, and the software

development team, need to commit to the success of the project. For example,

if the software development team is not committed to the project, then their

contribution may not be to the optimum level.

• Ineffective project sponsorship by management: Lack of commitment of the

senior management to a software project lowers the motivation level of the

team members. If the management commits to the progress of a software

project, and takes a keen interest in the progress, the confidence of the

software development team will increase.

⇒ Process- related Problems

The process-related problems in a software project are:

• Unrealistic schedule: Assigning unrealistic deadlines for a software project is

a primary reason why software projects are delayed. Often, the marketing or

the management team commit a delivery date to the customer in the hope of

getting the project contract. However, these dates are not decided in

consultation with the development team. The rationale for assigning the

deadlines is unfounded. You need to ensure that the deadlines match the

ability of the software team to deliver the software product. As it is not always

possible to shift deadlines committed to the customer, you also need to plan

the resource allocation and project execution such that the deadlines are met.

• Insufficient identification: Unidentified, partially identified, and unplanned

risks pose a threat to the success of a software project. You need to intensively

identify risks and evolve a risk management plan such that the project is

completed successfully, on time.

Software Project Management (CS615)

87

© Copyright Virtual University of Pakistan

• Unsuitable life cycle model selection: Different software projects require

different SDLC models. For example, a project to create banking .software is

different from software for a satellite where the concept needs to be

researched. For the former example, the Waterfall model is more applicable.

For the latter example, the Spiral model is more suitable. Selecting the correct

life cycle model is critical to the success of a software project.

• Abandoning quality under pressure of deadlines: Where a software project

faces a shortage of resources, time, and funds, project managers often push

away quality concerns and focus on meeting deadlines and staying within the

budget. Abandoning quality has a ripple effect that actually adds even more

time, effort, and costs to the software projects. The cost of doing things right

the first time is lower than the cost of inspection during product delivery.

Also, the cost of inspection is lower than the cost of debugging software after

the customer spots errors.

• Unstructured and hurried software development: When software project

progresses with more focus on meeting deadlines and staying within a budget,

the approach to the software development is unstructured and hurried. You

should plan the software project such that all the activities are identified,

sequenced properly, and roles and responsibilities assigned to the various

people on the project. You should also maintain the focus of the development

team toward a structured approach to software development.

⇒ Product-related Problems

There are many product-related problems that you can face in a software project.

These are:

• Product scope changed toward the end of the project life cycle: The project

time, effort, and cost estimates for a software project can go up dramatically

when the customer changes the scope 9f the product toward the end of the

project. In such situations, you should verify the criticality of the scope

change. However, if the change request is not critical, you should retain the

original scope with a proper explanation to the customer. If the change request

is critical, you should explain the situation to the customer. Usually, a

customer gives more time and funds to a software project if proper

justification is provided. In some cases, the scope change may also be because

of a change in government policy. It may become mandatory for you to

include such change requests.

• Research-oriented software development: Many software projects digress

from the original scope because of the nature of the software product or

technology used. When a totally new kind of software is developed or a new

Software Project Management (CS615)

88

© Copyright Virtual University of Pakistan

technology is used, the software development team can lose focus of the

objectives by getting into a research-oriented approach. It becomes your

responsibility as the project manager to maintain the focus on the objective.

Software Project Management (CS615)

89

© Copyright Virtual University of Pakistan

LECTURE # 12

2. Software Development Fundamentals

Management Fundamentals

2.10 Problems in Software Projects

⇒ Product-related Problems

• III-defined scope: You need to define the scope of the software product in the

initial stages of a software project. The scope of a software product is defined

in terms of the functionality requirements, the performance requirements, the

assumptions, and the constraints on the product. If the product scope is ill

defined, the software project does not have a proper focus on the features

required in the product.

• Fuzzy users: You also need to clarify the background characteristics of the

users of the final software product at the beginning of the software project. If

the description of the users is fuzzy, then the software analysis, design, and

development stages may reflect the ambiguity with regard to the functions and

performance of the final software product.

⇒ Technology-related problems

You may also encounter technology-related problems in a software project. These

include:

• Overestimated savings from reusable components and new tools and

methods: You can reuse software components in a software project to save

time, effort, and cost of creating the component again. It is important that you

assess the savings that the use of such a software component provides to a

software project. This expectation of both the customer and the management

might not be met, if you overestimate the savings from reusing software

components.

• Switching tools in mid way: The current technology environment offers new

tools and technologies for software development at a fast rate. All these tools

and technologies offer the benefits of a shorter development cycle, lower

costs, and under better functionality than earlier tools. You should identify

and commit to the tool and technology for the software project before the

project commences. Switching the tool or technology used during the software

development stage causes the developers to relearn a new tool. In addition,

Software Project Management (CS615)

90

© Copyright Virtual University of Pakistan

there is a chance that it might not be possible to integrate the software already

developed with the new tool.

• Integrating different software products in cross-platform implementation:

The modem software environment requires that all software should integrate

with each other. However, many software projects do not plan for integration

with existing software in the same or different domain. This limits the

applicationofsu9h software and reduces the shelf life drastically. They key to

the success of a software product is interoperability. The software project

manager needs to determine the scope for the software product such that is

can be integrated easily with existing software.

⇒ Summary

The phases in a software project can be organized into a project life cycle. Some

standard life cycle models are the Waterfall model, the Prototyping model, the

Incremental model, and the Spiral model.

Organizational policies and attitudes influence the progress of a software project

and the tasks of a software project manager. For smooth progress of software,

project, the organization should be proactive in adopting changes in technology

and market environments, focused on developing software, and accept software

projects that match the organizational capability baseline. In addition, the

organization should implement employee-friendly human resource policies and

good knowledge management system.

The role of a software project manager includes managing resources, cost, risk,

schedules, project plan, and quality. Software project management activities can

be divided into phases. The main phases and the associated activities are initiating

the project, planning, controlling, and tracking, implementing the product, and

project closedown.

Initiating the project includes gathering requirements, determining the scope,

allocating resources, and creating an initial project plan. Planning, controlling,

and tracking involve creating a detailed project plan, constructing software, and

implementing a control mechanism. Implementing the product comprises

implementation plan, support plan, training plan, and user acceptance plan.

Project closedown includes preparing closedown report, identifying learning for

future projects, and identifying reusable software components for future software

projects.

Problems- affecting software projects can be classified into people-related,

project-related, product-related, and technology-related.

Various myths regarding software project management are adding more people to

a late project can help to finish the project on time, combining the best resources

Software Project Management (CS615)

91

© Copyright Virtual University of Pakistan

with the worst resources results in optimal resource allocation, and changes to the

scope of the software project and the software product can be made at any-time in

the SDLC.

Software Project Management (CS615)

92

© Copyright Virtual University of Pakistan

LECTURE # 13

2. Software Development Fundamentals

Technical Fundamentals

2.11 Requirements Management

⇒ Preview

Software requirements engineering is a process of discovery, refinement,

modeling and specification. The system requirements and role allocated to

software-initially established by the system engineer-are refined in detail.

Models of the required data information and control flow and operational

behavior are created. Alternative solutions are analyzed and a complete

analysis model is created.

Requirements engineering is the systematic use of proven principles,

techniques, languages, and tools for the cost effective analysis,

documentation, and on-going evolution of user needs and the specification

of the external behavior of a system to satisfy those user needs. Notice that

like all engineering disciplines, requirements engineering is not conducted

in a sporadic random or otherwise haphazard fashion, but instead is the

systematic use of proven approaches.

Both the software engineer and customer take an active role in software

requirements engineering-a set of activities that is often referred to as

analysis. The customer attempts to reformulate a sometimes nebulous

system-level description of data, function and behavior into concrete

detail. The developer acts as interrogator, consultant, problem solver and

negotiator.

The overall role of Software in a larger system is identified during system

engineering. However, it's necessary to take a harder look at software's

role-to understand the specific requirements that must be achieved to build

high-quality software. That's the job of software requirements analysis. To

perform the job properly, you should follow a set of underlying concepts

and principles. Generally, a software engineer performs requirements

analysis However, for complex business applications a 'system analyst’

trained in the business aspects of the application domain may perform the

task. If you don't analyze, it's highly likely that you'll build a very elegant

software solution that solves the wrong problem. The result is wasted time

and money, personal frustration and unhappy customers.

Software Project Management (CS615)

93

© Copyright Virtual University of Pakistan

Data, functional, and behavioral requirements are identified by eliciting

information from the customer. Requirements are refined and analyzed to

assess their clarity, completeness, and consistency.

⇒ Requirements analysis

Requirements analysis is a software engineering task that bridges the gap

between system level requirements engineering and software design

(Figure 1). Requirements engineering activities result in the specification

of software's operational characteristics (function, data; and behavior),

indicate software's interface with other system elements, and establish

constraints that software must meet. Requirements analysis allows the

software engineer (sometimes called analyst in this. role) to refine the

software allocation and build models of the data, functional, and

behavioral domains that will be treated by software. Requirements

analysis provides the software designer with a representation of

information, function, and behavior that can be translated to data,

architectural, interface, and component-level designs. Finally, the

requirements specification provides the developer and the customer with

the means to assess quality once software is built.

Figure 1: a bridge between system engineering and software design

Software requirements analysis may be divided into five areas of effort:

(1) Problem recognition,

(2) Evaluation and synthesis,

(3) Modeling

(4) Specification, and

(5) Review

System

Engineerin

g

Software

Design

Software

Requirement

s

Analysis

Software Project Management (CS615)

94

© Copyright Virtual University of Pakistan

Initially, the analyst studies the System Specification (if one exists) and

the Software Project Plan. It is important to understand software in a

system context and to review the software scope that was used to generate

planning estimates. Next, communication for analysis must be established

so that problem recognition is ensured. The goal is recognition of the basic

problem elements as perceived by the customer/users.

􀂃 Problem evaluation

Problem evaluation and solution synthesis is the next major area of

effort for analysis. The analyst must define all externally observable

data objects, evaluate the flow and content of information, define and

elaborate all software functions, understand software behavior in the

context of events that affect the system, establish system interface

characteristics, and uncover additional design constraints. Each of

these tasks serves to describe the problem so that an overall approach

or solution may be synthesized. For example, an inventory control

system is required for a major supplier of auto parts. The analyst finds

that problems with the current manual system include:

(1) Inability to obtain the status of a component rapidly

(2) Two or three-day turnaround to update a card file

(3) Multiple reorders to the same vendor because there is no way to

associate vendors with components, and so forth.

Once problems have been identified, the analyst determines what

information is to be produced by the new system and what data will be

provided to the system. For instance, is the customer desires a daily

report that indicates what parts have been taken from inventory and

how many similar parts remain. The customer indicates that inventory

clerks will log the identification number of each part as it leaves the

inventory area.

􀂃 Solution synthesis

Upon evaluating current problems and desired information (input and

output), the analyst begins to synthesize one or more solutions. To

begin, the data objects processing functions and behavior of the system

are defined in detail. Once this information has been established, basic

architectures for implementation are considered.

A client/server approach would seem to be appropriate, but does the

software to support this architecture fall within the scope outlined in

the Software Plan? A database management system would seem to be

required, but is user/customer's need for associativity justified? The

process of evaluation and synthesis continues until both analyst and

Software Project Management (CS615)

95

© Copyright Virtual University of Pakistan

customer feel confident that software can be adequately specified for

subsequent development steps.

Throughout evaluation and solution synthesis, the analyst's primary

focus is on "what, not "how." What data does the system produce and

consume what functions the system must perform. What behaviors do

the system exhibit, what interfaces, are defined and what constraints

apply?

During the evaluation and solution synthesis activity, the analyst

creates models of the system in an effort to better understand data and

control flow, functional processing, operational behavior, and

information content. The model serves as a foundation for software

design and as the basis for the creation of specifications for the

Software. The customer may be unsure of precisely what is required.

The developer may be unsure that a specific approach will properly

accomplish function and performance. For these, and many other

reasons, an alternative approach to requirements analysis, called

Prototyping, may be conducted.

Software Project Management (CS615)

96

© Copyright Virtual University of Pakistan

LECTURE # 14

2. Software Development Fundamentals

Technical Fundamentals

2.11 Requirements Management

⇒ Requirements Analysis

• Evaluation and Synthesis

Upon evaluating current problems and desired information (input

and output), the analyst begins to synthesize one or more solutions.

To begin, the data objects processing functions and behavior of the

system are defined in detail. Once this information has been

established, basic architectures for implementation are considered.

A client/server approach would seem to be appropriate, but does

the software to support this architecture fall within the scope

outlined in the Software Plan? A database management system

would seem to be required, but is user/customer's need for

associativity justified? The process of evaluation and synthesis

continues until both analyst and customer feel confident that

software can be adequately specified for subsequent development

steps.

Throughout evaluation and solution synthesis, the analyst's

primary focus is on "what, not "how." What data does the system

produce and consume what functions the system must perform.

What behaviors do the system exhibit, what interfaces, are defined

and what constraints apply?

• Models

During the evaluation and solution synthesis activity, the analyst

creates models of the system in an effort to better understand data

and control flow, functional processing, operational behavior, and

information content. The model serves as a foundation for software

design and as the basis for the creation of specifications for the

Software.

• Specification

Software Project Management (CS615)

97

© Copyright Virtual University of Pakistan

During the evaluation and solution synthesis activity, the analyst

creates models of the system in an effort to better understand data

and control flow, functional processing, operational behavior, and

information content. The model serves as a foundation for software

design and as the basis for the creation of specifications for the

Software. The customer may be unsure of precisely what is

required. The developer may be unsure that a specific approach

will properly accomplish function and performance. For these, and

many other reasons, an alternative approach to requirements

analysis, called Prototyping, may be conducted.

• Concerns for Review

The customer may be unsure of precisely what is required. The

developer may be unsure that a specific approach will properly

accomplish function and performance. For these, and many other

reasons, an alternative approach to requirements analysis, called

Prototyping, may be conducted.

For example, an inventory control system is required for a major

supplier of auto parts. The analyst finds that problems with the

current manual system include:

(1) Inability to obtain the status of a component rapidly,

(2) Two- or three-day turn- around to update a card file,

(3) Multiple reorders to the same vendor because there is no way to

associate vendors with components, and so forth.

Once problems have been identified, the analyst determines what

information is to be produced by the new system and what data

will be provided to the system. For instance, customer desires a

daily report that indicates what parts have been taken from

inventory and how many similar parts remain. The customer

indicates that inventory clerks will log the identification number of

each part as it leaves the inventory area.

Upon evaluating current problems and desired information (input

and output), the analyst begins to synthesize one or more solutions.

To begin, the data objects, processing functions, and behavior of

the system are defined in detail. Once this information has been

established, basic architectures for implementation are considered.

A client/server approach would seem to be appropriate, but does

the software to support this architecture fall within the scope

outlined in the Software Plan? A database management system

would seem to be required, but is the user/customer's need for

Software Project Management (CS615)

98

© Copyright Virtual University of Pakistan

associativity justified? The process of evaluation and synthesis

continues until both analyst and customer feel confident that

software can be adequately specified for subsequent development

steps.

⇒ Requirements Elicitation for Software

Before requirements can be analyzed, modeled, or specified they must be

gathered through an elicitation process. A customer has a problem that

may be amenable to a computer-based solution. A developer responds to

the customer's request for help.

Communication has begun. But, as we have already noted, the road from

communication to understanding is often full of potholes.

1. Initiating the Process

The most commonly used requirements elicitation technique is to

conduct a meeting or interview. The first meeting between a

software engineer (the analyst) and the customer can be likened to

the awkwardness of a first date between two adolescents. Neither

person knows what to say or ask; both are worried that what they

do say will be misinterpreted; both are thinking about where it

might lead (both likely have radically different expectations here);

both want to get the thing over with, but at the same time, both

want it to be a success. Yet, communication must be initiated.

Gause and Weinberg [GAU89] suggest that the analyst start by

asking context-free questions. That is, a set of questions that will

lead to a basic understanding of the problem, the people who want

a solution, the nature of the solution that is desired, and the

effectiveness of the first encounter itself. The first set of contextfree,

questions focuses on the customer, the overall goals, and the

benefits. For example; the analyst might ask:

– Who is behind the request for this work?

– Who will use the solution?

– What will be the economic benefit of a successful solution?

– Is there another source for the solution that you need?

These questions help to identify all stakeholders who will have

interest in the software to be built. In addition, the questions

identify the measurable benefit of a successful implementation and

possible alternatives to custom software development.

Software Project Management (CS615)

99

© Copyright Virtual University of Pakistan

The next set of questions enables the analyst to gain a better

understanding of the problem and the customer to voice his or her

perceptions about a solution:

– How would you characterize "good" output that would be

generated by a successful solution?

– What problem(s) will this solution address?

– Can you show me (or describe) the environment in which the

solution will be used?

– Will special performance issues or constraints affect the way

the solution is approached?

The final set of questions focuses on the effectiveness of the

meeting. Gause and Weinberg call these meta-questions and

propose the following (abbreviated) list:

– Are you the right person to answer these questions? Are your

answers "official"?

– Are my questions relevant to the problem that you have?

– Am I asking too many questions?

– Can anyone else provide additional information?

– Should I be asking you anything else?

These questions (and others) will help to "break the ice" and

initiate the communication that is essential to successful analysis.

But a question and answer meeting format is not an approach that

has been overwhelmingly successful. In fact, the Q&A session

should be used for the first encounter only and then replaced by a

meeting format that combines elements of problem solving,

negotiation, and specification.

2. Facilitated Application Specification Techniques

Too often, customers and software engineers have an unconscious

"us and them" mind-set. Rather than working as a team to identify

and refine requirements, each constituency defines its own

"territory" and communicates through a series of memos, formal

position papers, documents, and question and answer sessions.

History has shown that this approach doesn't work very well.

Misunderstandings abound, important information is omitted, and

a successful working relationship is never established.

It is with these problems in mind that a number of independent

investigators have developed a team-oriented approach to

requirements gathering that is applied during early stages of

Software Project Management (CS615)

100

© Copyright Virtual University of Pakistan

analysis and specification. Called facilitated application

specification techniques "(FAST).

This approach encourages the creation of a joint team of customers

and developers who work together to:

Identify the problem

Propose elements of the solution

Negotiate different approaches and specify a preliminary set of

solution requirements.

FAST has been used predominantly by the information systems

community, but the technique offers potential for improved

communication in applications of all kinds.

Many different approaches to FAST have been proposed. Each

makes use of a slightly different scenario, but all apply some

variation on the following basic guidelines:

– A meeting is conducted at a neutral site and attended by both

software engineers and customers.

– Rules for preparation and participation are established.

– An agenda is suggested that is formal enough to cover all

important points but informal enough to encourage the free

flow of ideas.

– A ‘facilitator’ (can be a; customer, a developer, or an outsider)

controls the meeting.

– A "definition mechanism" (can be work sheets, flip charts, or

wall stickers or an electronic bulletin board, chat room or

virtual forum) is used.

The goal is to identify the problem, propose elements of the

solution, negotiate different approaches, and specify a preliminary

set of solution requirements in an atmosphere that is conducive to

the accomplishment of the goal.

To better understand the flow of events as they occur in a typical

FAST meeting, we present a brief scenario that outlines the

sequence of events that lead up to the meeting, occur during the

meeting, and follow the meeting.

Initial meetings between the developer and customer occur and

basic questions and answers help to establish the scope of the

problem and the overall perception of a solution. Out of these

initial meetings, the developer and customer write a one- or twopage

"product request." A meeting place, time, and date for FAST

are selected and a facilitator is chosen. Attendees from both the

Software Project Management (CS615)

101

© Copyright Virtual University of Pakistan

development and customer/user organizations are invited to attend.

The product request is distributed to all attendees before the

meeting date.

3. Quality Function Deployment

A quality management technique that translates needs of customers

into technical requirements of software.

i. Normal Requirement: meeting objectives & goals stated for a

product or system during meeting

i. Expected Requirement: Implicit to products / system and may

be so fundamental that customer does not explicitly state them

i. Exciting Requirement: Features beyond customer’s expectation

and prove to be very satisfying when present

4. Use Cases

As requirements are gathered as part of:

• Informal meeting

• FAST or QFD

SW Engineer can create a set of scenario that identify a thread of

usage for system to be constructed; providing a description of how

system will be used.

5. Analysis Principles

A variety of modeling notations are developed by investigators.

Each analysis method has a unique point of view. However all

analysis methods are related by a set of operational principles like:

– The information domain of a problem must be represented and

understood.

– The functions that the software is to perform must be defined.

– The behavior of the software (as a sequence of external events)

must be represented.

– The models that depict information function and behavior must

be partitioned in a manner that uncovers details in a layered (or

hierarchical) fashion.

Software Project Management (CS615)

102

© Copyright Virtual University of Pakistan

– The analysis process should move from essential information

toward implementation detail.

6. Software Prototyping

Analysis should be conducted regardless of the SW engineering

paradigm. (Various approaches apply)

In some cases it is possible to apply operational analysis principles

and derive a model of SW from which a design can be developed.

In other situation Requirement Elicitation (FAST, QFD etc) is

conducted and a model is built, called Prototype.

Software Project Management (CS615)

103

© Copyright Virtual University of Pakistan

LECTURE # 15

2. Software Development Fundamentals

Technical Fundamentals

2.11 Requirements Management

⇒ The Software Requirements Specification

The Software Requirements Specification is produced at the culmination of the

analysis task, The function and performance allocated to software as part of

system engineering are refined by establishing a complete information

description, a detailed functional description, a representation of system behavior,

an indication of performance requirements and design constraints, appropriate

validation criteria, and other: information pertinent to requirements. The National

Bureau of Standards; IEEE (Standard No. 830-1984), and the U.S. Department of

Defense have all proposed candidate formats for software requirements

specifications (as well as other software engineering documentation).

Mode of specification has a great impact on quality of solution. Forcing SWE to

work with incomplete, inconsistence, or misleading specifications result in

frustration and confusion affecting:

– Quality

– Timeliness and

– Completeness of SW product

• Principles

i. Separate functionality from implementation.

ii. Develop a model of desired behavior of a system that encompasses data and

the functional response of a system to various stimuli from the environment.

iii. Establish the context in which SW operates by specifying the manner in which

other system components interact with software.

iv. Define the environment in which system operates and indicate how a highly

inter-wined collection of agents react to stimuli in the environment (changes

to objects) produced by those agents.

v. Create a cognitive model rather than a design or implementation model.

Cognitive model describes a system as perceived by its user community.

Software Project Management (CS615)

104

© Copyright Virtual University of Pakistan

vi. Recognize that; “the specifications must be tolerant of incompleteness and

augmentable.”

vii. A specification is always a model –an abstraction-of some real (or envisioned)

situation that is normally quite complex. Hence it will be incomplete and will exit

at many levels of detail.

i. Establish the content and structure of a specification in a way that will enable it to

be amenable to change.

• Representation

i. Representation format and content should be relevant to the problem. (A

general outline of SRS can be developed).

ii. Information contained within the specification should be nested.

iii. It should reveal layers of information so that reader can move to the level

of detail required. Paragraph & diagram number scheme to indicate level.

iv. Diagrams and other notational forms should be restricted in number and

consistent in use. (Confusing or inconsistent notations, whether graphical

or symbolic degrades understating and foster errors.)

v. Representation should be revisable.

vi. The content of specification will change. Ideally, CASE tools should be

available to update all representations that are affected by each change.

The function and performance allocated to software as part of system engineering

are refined by establishing:

1. A complete information description,

2. A detailed functional description,

3. A representation of system behavior,

4. An indication of performance requirements and design constraints,

5. Appropriate validation criteria, and other: information pertinent to

requirements.

The Introduction of the software requirements specification states the goals and

objectives of the software, describing it in the context of the computer-based

system; actually, the Introduction may be nothing more than the software scope of

the planning document.

Software Project Management (CS615)

105

© Copyright Virtual University of Pakistan

The Software Requirements Specification is produced at the culmination of the

analysis task. The function and performance allocated to software as part of

system engineering are refined by establishing:

– A complete information description

– A detailed functional description

– A representation of system behavior

– An indication of performance requirements and design constraints

– Appropriate validation criteria and other information pertinent to

requirements.

The Information Description provides a detailed description of the problem that

the software must solve. Information content, flow, and structure are documented.

Hardware, software, and human interfaces are described (or external system

elements: and internal software functions.

A description of each function required to solve the problem is presented in the

Functional Description.

A processing narrative is provided for each function:

– Design constraints are stated and justified

– Performance characteristics are stated, and

– One or more diagrams are included to graphically represent the overall

structure of the software and interplay among software functions and other

system elements

The Behavioral Description section of the specification examines the operation of

the software as a consequence of external events and internally generated control

characteristics.

Validation Criteria is probably the most important and, ironically, the most often,

neglected section of the Software Requirements specification.

– How do we recognize a successful implementation?

– What classes of tests must be conducted to validate function, performance,

and constraints?

We neglect this section because completing it demands a thorough understanding

of software requirements-something that we often do not have at this stage.

Yet, specification of validation criteria acts as an implicit review of all other

requirements. It is essential that time and attention be given to this section.

Finally, the specification includes a Bibliography and Appendix.

Software Project Management (CS615)

106

© Copyright Virtual University of Pakistan

– The bibliography contains references to all documents that relate to the

software. These include other software engineering documentation,

technical references, vendor literature, and; standards.

– The appendix contains information that supplements the specifications.

Tabular data, detailed description of algorithms, charts, graphs and other

material, are presented as appendixes.

In many cases the Software Requirements Specification may be accompanied by

an executable prototype (which in some cases may replace the specification), a

paper prototype or a Preliminary User's Manual. The Preliminary Users Manual

presents the software as a black box: That is, heavy emphasis is placed on user

input and the resultant output. The manual can serve as a valuable tool for

uncovering problems at the human/machine interface.

⇒ Review

A review of the Software Requirements Specification (and/or prototype) is

conducted by both the software developer and the customer.

Extreme care should be taken in conducting the review because the specification

forms the foundation of the development phase.

The review is first conducted at a macroscopic level; that is, reviewers attempt to

ensure that the specification is complete, consistent, and accurate when the overall

information, functional, and behavioral domains; are considered. However, to

fully explore each of these domains, the review becomes more detailed,

examining not only broad descriptions but the way in which requirements are

worded. For example, when specifications contain "vague terms" (e.g., some,

sometimes, often, usual ordinarily, most, or mostly), the reviewer should flag the

statements for further clarification.

Once the review is complete, the Software Requirements Specification is "signedoff

by both the customer and the developer. The specification becomes a

"contract" for software development. Requests for changes in requirements after

the specification is finalized will not be eliminated. But the customer should note

that each after- the-fact change is an extension of software scope and therefore

can increase cost, and/or protract the schedule.

Even with the best review procedures in place, a number of common specification

problems persist. The specification is difficult to "test" in any meaningful way,

and therefore inconsistency or omissions may pass unnoticed. During the review,

changes to the specification may be recommended. It can be extremely difficult to

assess the global impact of a change; that is, how a change in one function affects

requirements for other functions. Modem software engineering environments

incorporate CASE tools that have been developed to help solve these problems.

Software Project Management (CS615)

107

© Copyright Virtual University of Pakistan

LECTURE # 16

2. Software Development Fundamentals

Technical Fundamentals

2.12 Design

⇒ Management Aspect

– Major design styles

• Object, structured, data-structured design

– Foundational design concepts

• Information hiding, abstraction, encapsulation, Inheritance, basic

algorithms & data structures, ...

⇒ Attributes of SW Design

Software design is actually a multi step process that focuses on four

distinct attributes of a program:

– Data structure,

– Software architecture,

– Interface representations, and procedural (algorithmic) detail.

The design process translates requirements into a representation of the

software that can be assessed for quality before coding begins.

Like requirements, the design is documented and becomes part of the

software configuration.

Design is the technical kernel of software engineering. During design,

progressive refinements of data structure, architecture, interfaces, and

procedural detail of software components are developed, reviewed, and

documented.

Design results in representations of software that can be assessed for

quality. A number of fundamental software design principles and concepts

have been proposed over the past four decades.

Design principles guide the software engineer as the design process

proceeds. Design concepts provide basic criteria for design quality.

Software Project Management (CS615)

108

© Copyright Virtual University of Pakistan

a. Code generation

The design must be translated into a machine-readable form. The

code generation step performs this task. If design is performed in a

detailed manner, code generation can be accomplished

mechanistically.

b. Testing

Once code has been generated, program testing begins. The testing

process focuses on the logical internals of the software, ensuring

that all statements have been tested and on the functional externals;

that is, conducting tests to uncover errors and ensure that defined

input will produce actual results that agree with required results.

⇒ Key Features of Design

A number of fundamental software design principles and concepts have

been proposed over the past four decades. Design principles guide the

software engineer as the design process proceeds. Design concepts provide

basic criteria for design quality.

Support

Support

Software will undoubtedly undergo change after it is delivered to the

customer (a possible exception is embedded software). Change will occur

because errors have been encountered, because the software must be

adapted to accommodate changes in its external environment (e.g. a

change required because of a new operating system or peripheral device),

or because the customer requires functional or performance enhancements.

Software support/maintenance reapplies each of the preceding phases to

an existing program rather than a new one.

Modularity

Modularity (in both program and data) and the concept of abstraction

enable the designer to simplify and reuse software components.

Refinement provides a mechanism for representing successive layers of

functional detail. Program and data structure contribute to an overall view

of software architecture, while procedure provides the detail necessary for

algorithm implementation.

Software Project Management (CS615)

109

© Copyright Virtual University of Pakistan

Information hiding and functional independence provide heuristics for

achieving effective modularity.

We try to solve the problem by rushing through the design process so that

enough time will be left at the end of the project to uncover errors that

were made because we rushed through the design process.

The moral is this: Don't rush through it! Design is worth the effort.

⇒ Standard design approaches

• Exception handling,

• Localization

• Portability

• Reuse

• Input/output

• Memory management,

• Performance

2.13 Construction

– Coding practices

Naming, layout, documentation

– Data-related concepts

Scope, persistence, binding time

– Data usage guidelines

Bytes, arrays

– Use of construction tools

Programming environment, group work support (documents, code),

code libraries & generators

2.14 Software Configuration management

Software configuration management (SCM) takes care of changes in a

software process. SCM identifies controls, audits, and reports

modifications that occur during software development. SCM helps

maintain the integrity of configurable items produced during software

development. SCM is an integral part of Software Quality Assurance

(SQA). SCM involves assessing the impact of the changes made during

SQA activities and making decisions based on cost and benefit analysis.

SCM is used to establish and maintain integrity of software items and

ensure that they can be traced easily. SCM helps define a library structure

for storage and retrieval of software items.

Software Project Management (CS615)

110

© Copyright Virtual University of Pakistan

• To ensure that project stays consistent over time: You need to:

a) Evaluate proposed changes

b) Track the changes

c) Control the Version

d) Check integrity of Source code, documents, plans, design

e) Ensure quality

⇒ Software Configuration Management Activities

SCM is used to establish and maintain integrity of software items and

ensure that they can be traced easily. Using SCM, you can define a library

structure for storage and retrieval of software items. SCM needs to be

performed at all phases in the SDLC of a software project. The various

SCM activities are:

1. Identifying Objects

2. Controlling Versions

3. Controlling Changes

4. Auditing

5. Communicating Changes

1. Identifying Objects

The first activity in SCM involves identifying software configurable

items (SCIs). SCI is an aggregation of software that is designated for

configuration management. It is treated as a single entity in the

configuration management process. For example, design documents,

program code, test case, and custom requirement document are

configurable items.

You can use the Item Traceability Matrix to identify SCIs at the end of

each phase. A sample of Item Traceability Matrix is displayed in Table

1. In the table, you can see the different SCIs in different phases of the

development process.

Software Project Management (CS615)

111

© Copyright Virtual University of Pakistan

Table 1: Item Traceability Matrix

Phase Deliverable

Name Requirement

Analysis Design Construction Testing

Requirement

Analysis

Document

Requirement

Analysis Document

Design

Document

Functional

Specification

Document and

Program

Specification

Document

Code

Code A

Code B

Code C

Test Document

Unit Test

Cases

System Test

Cases

Database

Design

Document

Database Design

Specification

To identify SCls, you need to first breakdown the project deliverable

to the SCI level. Each phase in the project has its own deliverables. To

trace the deliverables, you need to map the SCls to the phases in which

they are delivered.

2. Controlling Versions

Version control combines procedures and tools to manage different

versions of configuration objects that are created during software

product development. To control versions, you can use Version

Control Register. In Version Control Register, you enter the details of

components, such as component identification numbers, their versions,

and dates of validity. It is advisable to release a baseline after a version

is released. Baseline is a specification or a product that is formally

reviewed and agreed upon. This serves as the basis for further

development. Baseline can be changed only through formal change

control procedures. A baseline consists of a set of SCIs that are

logically related to each other. Baselines are established when

subsequent changes to the SCIs need to be controlled. Version control

is essential so that everybody uses only the latest version. Any kind of

version mismatch might result in rework.

Software Project Management (CS615)

112

© Copyright Virtual University of Pakistan

LECTURE # 17

2. Software Development Fundamentals

Technical Fundamentals

2.14 Software Configuration management

b. Controlling Versions

Version control combines procedures and tools to manage different versions

of configuration objects that are created during software product development.

To control versions, you can use Version Control Register. In Version Control

Register, you enter the details of components, such as component

identification numbers, their versions, and dates of validity. It is advisable to

release a baseline after a version is released. Baseline is a specification or a

product that is formally reviewed and agreed upon. This serves as the basis for

further development. Baseline can be changed only through formal change

control procedures. A baseline consists of a set of SCIs that are logically

related to each other. Baselines are established when subsequent changes to

the SCIs need to be controlled. Version control is essential so that everybody

uses only the latest version. Any kind of version mismatch might result in

rework.

c. Controlling Changes

Uncontrolled change can lead to chaos. Change control combines human

procedures and automated tools to provide a mechanism for controlling

change. The purpose of change control is to monitor and control changes in

order to baseline SCIs. There are various reasons that trigger changes. A

problem report might call for a change. Similarly, suggestions or ideas from

brainstorming sessions and feedback from clients can result in change.

Modifications or addition to functionality and changes in environment can

also cause changes. The Figure 1 explains the formal change control process

using a flow chart.

Software Project Management (CS615)

113

© Copyright Virtual University of Pakistan

Figure 1: Formal Change Control Process

A request for change triggers that change control procedure. Then request is

logged in the change request register. Next, the change request number is

recorded in the change request evaluation plan. The request is evaluated and

analyzed to check if the change is valid. Change request is also evaluated in

Start

Change request is made

Change request is logged

Change request is evaluated

Outcome is notified

Is the

Request

Rejected?

Change request is implemented

Stop

Yes

Yes

No

No

Is the

Request

Deferred?

Software Project Management (CS615)

114

© Copyright Virtual University of Pakistan

terms of the number of items affected and the effort involved in effecting the

change. Finally, the possible outcome of the change request is communicated.

The request for change is rejected, deferred, or approved. If the request for

change is rejected, the requestor needs to log a fresh request. A deferred

change request is evaluated at a later date while the change request that is

approved is implemented.

There are tools that provide facilities to check in and check out so that the

same version of the object is not updated more than once. The check-in and

checkout facilities provide synchronization control. Synchronization control

helps to ensure that parallel changes performed by two different people do not

overwrite one another.

d. Auditing

Configuration audit is conducted formally by the SQA group in projects

where SCM is a formal activity. The identification, version control, and

change control tasks help the developer maintain order and decorum in an

environment of change. However, the control mechanisms track a change only

until an item is generated. FTRs and software configuration audits (SCA) are

conducted to ensure that change is properly implemented. FTR verifies the

technical correctness of the SCI that is subjected to change. SCA assesses

those characteristics of an SCI that are not considered during FTRs. Audit

verifies whether the changes specified in the request for change are made and

additional modifications, if any, are also noted. Audits ensure that FTRs are

conducted to check for technical correctness. Audits verify that changes made

are highlighted in the SCI. The change date and change author are specified

and the attributes of SCI reflect the change. The SCM procedures for noting,

recording, and reporting change are also followed. Audits also ensure that

related SCIs are updated.

e. Communicating Changes

Another task of SCM is communicating changes. This task ensures

communication between different members in the project. It notes the

activities performed, the time when they are performed, those involved in the

activities, and those affected by the activities. In short, the task is all about

status reporting. In a large project, there is a possibility of miscommunication

among various people involved in the project. This is usually done using

configuration status report shown in Table 11.7. The table contains the name

of the SCI, the latest released version, the date of release, brief description of

changes performed, and associated change request. Further details of the

changes can be obtained from the associated change request. There can be

instances where two developers may be trying to modify the same software

configurable item with different and conflicting intentions. Absence of status

reporting could result in incorrect decisions being taken or important decisions

Software Project Management (CS615)

115

© Copyright Virtual University of Pakistan

not being communicated. At times, those who should be pointing out the

serious side effects caused by a change are not aware of the implementation of

the change. There are also instances of version mismatch when teams are

unaware of the latest version to be followed. To avoid such hazards due to

lack of communication among the project team, changes are communicated

among team members. Therefore, status reporting provides information about

each change to those who need to know. Software configuration management

takes care of changes in a software process. SCM identifies controls, audits,

and reports modifications that occur during software development. SCM helps

maintain the integrity of configurable items produced during software

development.

⇒ Software Configuration Management Vs Software Maintenance

SCM is an integral part of SQA. SCM involves assessing the impact of the

changes made during SQA activities and making decisions based on cost and

benefit analysis. SCM can be defined as the art of identifying, organizing, and

controlling changes in a software project with the objective of minimizing

mistakes. SCM is different from software maintenance. Software maintenance is

required after the software is delivered to the client and is put into operation. As

opposed to this, SCM is a set of tracking and controlling activities that begins

when a software project begins and ends only when the software is taken out of

operation.

⇒ Baselines vs. Interim Versions

SCM differentiates between baselines and interim versions. A baseline is a tested

and certified version of a system. Baselines can be assigned version numbers such

as 1.0, 2.0, 3.0, and so on. A baseline usually undergoes intensive testing. Interim

versions, on the other hand, have version numbers, such as 1.1 or 1.2. The interim

version is a temporary version. Interim versions have a short life and survive only

during bug fixing, testing, or debugging. However, interim versions also have a

unique version number or name. Baselines are more visible with the marketing

team and the vendors than the interim versions. However, as part of SCM, all

versions of changes are saved, clearly labeled, and archived. Archiving is the

process of maintaining controlled copies of prior versions. Archiving helps in recreating

earlier versions in the event of data loss or data corruption.

⇒ Effective Configuration Control

Effective configuration control requires effective and well-defined organization.

Any configuration control method must be based on the following four concepts:

A clearly defined configuration management authority must be established.

Configuration control standards, procedures and guidelines must be produced and

distributed to the developers.

Software Project Management (CS615)

116

© Copyright Virtual University of Pakistan

Configuration control cannot be effective without the necessary tools and

facilities.

A configuration management plan must be developed at the beginning of the

project.

The configuration management environment consists of the resources necessary

for the implementation of the configuration control plan.

Configuration control tools, including:

􀂃 Automatic version control and

􀂃 Change control tools

􀂃 Monitoring, auditing and registration support utilities

􀂃 Storage facilities; a safe repository for all approved configuration items,

including:

– On-site storage for the day to day development process

– Off-site storage for catastrophe recovery

⇒ Guidelines for effective configuration management

The following are some additional guidelines for effective configuration

management. Some of these guidelines are equally applicable to other

management support functions.

• Configuration management requires authority in order to be effective. This

authority must be clearly delegated by the project manager to the responsible

engineers. Any configuration management plan will become meaningless if

the plan cannot be enforced.

• Blunt enforcement of any plan policy or standard is best avoided, whenever

possible. One of the qualities of a good manager is the ability to apply policy

with minimal enforcement. Whenever policies and standards are readily

accepted by the developers, they are more willingly followed and there are

fewer rejections of submitted material. This leads to a more efficient

development process.

• Configuration management should be implemented from the start of a

software project. Many of the formal documents issued during the initial

concept phase are crucial for the requirements and design phases, and must be

placed under configuration control.

• The early application of configuration management is especially important in

rapid prototyping, spiral models, or other iterative development

methodologies. These development approaches initially produce several

Software Project Management (CS615)

117

© Copyright Virtual University of Pakistan

versions of each product. Many different versions can become an engineering

nightmare without orderly configuration control.

• Occasionally some software configuration control activities may overlap with

software quality assurance activities. In small projects, these two functions

may be assigned to a single support engineer. Even in large projects, these two

functions are sometimes performed by a single support group.

⇒ Misapplication of Guidelines

It should be noted that configuration management can be greatly exaggerated.

The various configuration control activities are not an objective in themselves,

they are a means.

• A typical example of the misapplication of configuration management (and

misguided quality control), is a requirement to modify reused software to

comply with current standards and procedures.

• Reused software is software developed previously in another project, and

found suitable to be incorporated into the current project. In such cases it

rarely makes sense to modify a complete and working product in order to

make it comply with administrative standards intended to make it a complete

and working product.

Software Project Management (CS615)

118

© Copyright Virtual University of Pakistan

LECTURE # 18

2. Software Development Fundamentals

Technical Fundamentals

2.15 Quality Assurance Management

⇒ Definition

According to American Heritage Dictionary, quality is defined as "an inherent or

distinguishing characteristic or a property".

The distinguishing characteristics of a software product are the cyclomatic

complexity, cohesion, function points, and lines of code. These characteristics of

a software product define the quality of the product.

• The US DOD (1988) defines software quality rather simply as:

– The ability of a software product to satisfy its specified requirements.

• The British Standards Institution (1986) has stated that:

– “Quality is in the eye of the beholder, a matter, of the client's judgment.”

⇒ Quality Standards and Procedures

The quality of software is said to be high if it meets the standards and procedures,

defined for the product. Standards are criteria to which the products are compared.

For example, there may be standards that govern the quality review process.

Documentation standard design standard and code standard are the three types of

standards that software projects usually follow.

Documentation standard specifies the form and content for planning, control, and

product documentation. Design standards provide rules and methods for

translating the software requirements into software design. The design standards

are specified in the form and content of the product design.

Unlike documentation standard, code standard defines the language in which code

should be written. The standard clearly mentions the structures, style conventions,

and rules for data structures and interfaces that will be implemented in the project.

Software Project Management (CS615)

119

© Copyright Virtual University of Pakistan

Procedures are criteria to which the development and control processes are

compared. Procedures are explicit steps followed in a process. Procedures need to

be properly documented because they are needed for configuration management,

nonconformance reporting, corrective action, testing, and formal inspections.

Proper documentation of procedures is necessary because SQA activities rely on

them for project compliance. Organizations normally enforce quality standards

with the help of checklists, common error lists, and standards and guidelines.

⇒ Concepts

Product quality depends on its conformance to software requirements,

development standards, and implicit requirements.

During software development, the quality of a product depends on the quality of

the design.

The quality of product design, in turn, depends on how effectively the product

designer captures the client requirements and specifications. At times, the client

has some implicit requirements that are not captured in the requirements

document. There are three things that guide requirements: want, desire, and wish.

Usually, wants are captured explicitly in the requirements documents. However, if

you manage to capture desires and wishes, the product becomes a great success.

The product designer needs to state these implicit requirements clearly during

analysis. The adherence to these implicit requirements is the key attribute that sets

one product apart from another.

The product quality also depends on how strictly, and to what degree the

developer adheres to design specifications. This is what the concept quality is

meeting or exceeding our client's needs and requirements' means.

The product quality is said to be high if the product is manufactured according to

design specifications.

⇒ Quality Control

Quality control is a series of review activities, such as:

• Inspections

• Reviews and

• Tests, used throughout the SDLC of the software product

The objective of quality control is to find problems as early as possible and fix

them.

Quality control ensures that the software product meets the requirements defined

at every stage in its development.

Software Project Management (CS615)

120

© Copyright Virtual University of Pakistan

There is provision for feedback mechanism during quality control. Any slippage

in meeting the requirements during the development process is communicated to

the development team immediately.

Feedback ensures that errors or misses found during quality control are rectified

as soon as they are detected.

During software development, quality control plays a valuable role by evaluating

products against standards and specifications.

Quality control activities can be fully automated manual, or a combination of

these. Quality control involves monitoring specific project results to determine if:

– They comply with relevant quality standards

– Identifying ways to eliminate causes of unsatisfactory results.

Project results include both:

– Product results, such as deliverables, and

– Project management results, such as cost and schedule performance.

⇒ Quality Factors

There are a number of factors that determine the quality of a software product.

These factors can be measured either directly or indirectly. McCall (MCC77) and

his colleagues proposed some software quality factors based on three most

important aspects of a software product:

1. Product operation

2. Product revision and

3. Product transition

1. Product Operation Factors

The product operation factors determine the quality of software when a

program is executed. Good quality software is not only correct and reliable

but also delivers correct performance in all circumstances. Some of the factors

of product operation are correctness, reliability, efficiency, integrity, and

usability. You can look at the factor description in Table 1.

Table 1: Product Operation Factors

Correctness Accuracy of the program and the extent to which it fulfills design specifications

Reliability Extent to which the program is secure and its ability to recover quickly from failure.

Software Project Management (CS615)

121

© Copyright Virtual University of Pakistan

Efficiency Performance of the program and its ability to perform tasks within a time frame

Integrity Ability of the program to take care of security and the extent to which it can prevent

unauthorized.

Usability Ease with which a user can learn, operates, and uses the program.

2. Product Revision Factors

Product revision factors focus on the ease of maintenance of the software

product. Maintenance tasks could be either correcting faults in the original

design or making improvements to adapt the functionality to changing

environments. Product revision covers the following factors: maintainability,

flexibility, and testability. These factors are described in Table 2.

Table 2: Product Revision Factors

Maintainability Ease with which a program is debugged.

Flexibility Ease with which a program is modified.

Testability Ease with which a program is tested.

3. Product Transition Factors

The product transition factors determine the quality of programs that are

designed for open systems. Here the focus is more on the portability and

reusability of a software product. To help a system run on different platforms,

certain parts of a system may be reused. The product transition factors are

portability, reusability, interoperability, configurability, and expandability.

These factors are described in Table 3.

Table 3: Product Transition Factors

Portability Efficiency with which a program runs on different platforms or operating systems

Reusability Extent to which the program can be used in more than one program or system

Interoperability Effort needed to transfer a program to another system

Configurability Ability of the program to be installed at more than one location with different

features at each location

Expandability Ability of the program to support an increase in data and users

Software Project Management (CS615)

122

© Copyright Virtual University of Pakistan

LECTURE # 19

2. Software Development Fundamentals

Technical Fundamentals

2.15 Quality Assurance Management

⇒ Software Quality Assurance Activities

SQA is the process of evaluating the quality of a product and enforcing adherence

to software product standards and procedures. It is an umbrella activity that

ensures conformance to standards and procedures throughout the SDLC of a

software product. There are a large number of tasks involved in SQA activities.

These include:

i. Formulating a quality management plan

ii. Applying software engineering techniques

iii. Conducting formal technical reviews

iv. Applying a multi-tiered testing strategy

v. Enforcing process adherence

vi. Controlling change

vii. Measuring impact of change

viii. Performing SQA audits

ix. Keeping records and reporting

i. Formulating a Quality Management Plan

One of the tasks of SQA is the formulation of a quality management plan. The

quality management plan identifies the quality aspects of the software product to

be developed. It helps in planning checkpoints for work products and the

development process. It also tracks changes made to the development process

based on the results of the checks. The quality management plan is tracked as a

live plan throughout the SDLC.

ii. Applying Software Engineering

Application of software engineering techniques helps the software designer to

achieve high quality specification. The designer gathers information using

techniques such as interviews and FAST. Using the information gathered, the

designer prepares project estimation with the help of techniques such as WBS,

SLOC estimation, or FP estimation.

iii. Conducting Formal Technical Reviews

Formal technical review (FTR) in conducted to assess the quality and design of

the prototype. It is a meeting with the technical staff to discuss the quality

Software Project Management (CS615)

123

© Copyright Virtual University of Pakistan

requirements of a software product and its design quality. FTRs help in detecting

errors at an early phase of development. This prevents errors from percolating

down to the latter phases and resulting in rework.

iv. Applying a Multi-tiered Testing Strategy

Software testing is a critical task of SQA activity, which aims at error detection.

Unit testing is the first level of testing. The subsequence levels of testing are

integration testing and system level testing. There are various testing strategies

followed by organization. At times, developers perform unit testing and

integration testing with independence testing support. There are also occasions

where testers perform functional testing and system level testing with developer

support. Sometimes beta testing with selected clients is also conducted to test the

product before it is finally released.

v. Enforcing Process Adherence

This task of SQA emphasizes the need for process adherence during product

development. In addition, the development process should also adhere to

procedures defined for product development. Therefore, this is a combination of

two tasks, product evaluation and process monitoring.

vi. Product Evaluation

Product evaluation ensures that the standards laid down for a project are followed.

During product evaluation, the compliance of the software product to the existing

standards is verified. Initially, SQA activities are conducted to monitor the

standards and procedures of the project. Product evaluation ensures that the

software product reflects the requirements identified in the project management

plan.

vii. Process Monitoring

Process monitoring ensures that appropriate steps to follow the product

development procedures are carried out. SQA monitors processes by comparing

the actual steps carried out with the steps in the documented procedures.

Product evaluation and process monitoring ensure that the development and

control processes described in the project management plan are correctly carried

out. These tasks ensure that the project-re1ated procedures and standards are

followed. They also ensure that products and processes conform to standards and

procedures. Audits ensure that product evaluation and process monitoring are

performed.

viii. Controlling Change

This task combines human procedures and automated tools to provide a

mechanism for change control. The change control mechanism ensures software

quality by formalizing requests for change, evaluating the nature of change, and

controlling the impact of change. Change control mechanism is implemented

during the development and maintenance stages.

Software Project Management (CS615)

124

© Copyright Virtual University of Pakistan

ix. Measuring Impact of Change

Change is inevitable in the SDLC. However, the change needs to be measured and

monitored. Changes in the product or process are measured using software quality

metrics. Software qua1ity metrics helps in estimating the cost and resource

requirements of a project. To control software quality; it is essential to measure

quality and then compare it with established standards. Software qua1ity metrics

are used to evaluate the effectiveness of techniques and tools, the productivity of

development activities and the qua1ity of products. Metrics enables mangers and

developers to monitor the activities and proposed changes throughout the SDLC

and initiate corrective actions.

x. Performing SQA Audits

SQA audits scrutinize the software development process by comparing it to

established processes. This ensures that proper control is maintained over the

documents required during SDLC. Audits also ensure that the status of an activity

performed by the developer is reflected in the status report of the developer.

xi. Keeping Records and Reporting

Keeping records and reporting ensure the collection and circulation of information

relevant to SQA. The results of reviews, audits, change control, testing, and other

SQA activities are reported and compiled for future reference.

⇒ Software Review

Software review is an effective way of filtering errors in a software product.

Typically, an error found after the product release costs 50 times as much to

correct as one detected during the design phase.

This means the cost of fixing a defect rises dramatically if it is found late in the

development life cycle of the product. Therefore, you need to filter errors as early

as possible.

Software review is used as a filter at various points of software development.

Reviews conducted at each of these phases, analysis, design, coding, and testing

reveal areas of improvement in the product.

Reviews also indicate those areas that do not need any improvement. You can use

software reviews to achieve consistency and uniformity across products. Reviews

also make the task of product creation more manageable. Some of the most

common software review techniques, practiced across software organizations

include:

a) Inspection

b) Walkthrough

c) Formal technical reviews

a) Inspections

Software Project Management (CS615)

125

© Copyright Virtual University of Pakistan

Inspections improve the reliability, availability, and maintainability of a

software product. Anything readable that is produced during software

development can be inspected. The readable material can be requirements

specifications, design documents and models, test plans, system

documentation, and user aids. Group inspections enable team members to

exchange knowledge and ideas during an inspection session.

Inspections can be combined with structured, systematic testing to provide a

powerful tool for creating defect-free programs. The inspection activity

follows a specified process and the participants play well-defined roles. An

inspection team consists of three to eight members who play the roles of

moderator, author, reader, recorder, and inspector.

Moderator leads the inspection, schedules meetings, controls meetings, reports

inspection results, and follows up on rework issues. Author creates or

maintains the work product being inspected. Reader describes the sections of

the work product to the team as they proceed through inspection. Recorder

classifies and records defects and issues raised during the inspection. The

moderator might perform this role in a small inspection team. Inspector finds

errors in the product. All participants play the role of inspectors. However,

good inspectors are those who have created the specification for the work

product being inspected. For example, the designer can act as an inspector

during code inspection while a quality assurance representative can act as

standard enforcer. It also helps to have a client representative participate in

requirements specification inspections.

b) Walkthroughs

The term walkthrough refers to a group activity in which the developer of the

product guides the progress of the review. Walkthroughs are less rigorous than

either formal inspections or peer reviews in which the developer plays a more

passive role. Normally walkthroughs turn into a presentation by the author.

The focus of finding errors is diluted. Such misadventures make walkthroughs

usually less successful at detecting bugs than the more formal review

methods.

Two useful walkthrough approaches adopted worldwide are group reviews

with individual preparation and individual peer desk-checks. Group reviews

are not very rigorous like inspections. The group reviews involve many of the

same activities and roles, such as individual preparation and the use of a

moderator and a recorder. Usually the overview meeting and the follow-up

steps are skipped and checklists are used sparingly. At the end, the readers

paraphrase their interpretation of what a program is doing.

Software Project Management (CS615)

126

© Copyright Virtual University of Pakistan

Individual peer desk-checks are quite cost-effective. Only one person besides

the author examines the material. This approach can be more effective if there

are individuals who are extremely good at finding defects on their own.

Tip:

If someone consistently finds most of the group-identified defects during the

individual preparation step, such a person is fit to perform individual peer

desk-checks.

c) Formal Technical Reviews

One of the most common, yet important, software quality assurance activity

performed is FTR. This activity is performed to check errors in logic,

function, or implementation for any representation of the software.

Using FTR, you can verify whether or not the software product adheres to the

defined standards. FTR is also conducted to check for consistency in the

software product and audit the manageability of the software product. It

includes activities such as walkthrough and inspection.

FTR focuses on specific parts of the software product, such as the

requirements components, detailed design module, and the source code listing

for a module.

FTR also concentrates on the entire product. The participants in FTR are the

developer, the project leader, and all the reviewers.

At the end of the review meeting, the issues recorded are formalized into

review issues list. The minutes of the meeting are summarized into a review

summary report as displayed in table 4.

Technical Review Report

Review Identification

Project Name Current Phase Review Number

Product Identification

Item Reviewed Version No. Developer

Brief Description

Documents Referred (along with versions, if any)

Start Name End Time

Review Material Attached: Yes / No

Participants Role Preparation Time

Software Project Management (CS615)

127

© Copyright Virtual University of Pakistan

Total Review Time (No. of Participants * Actual duration of meeting)

Total Review Person Hours

Product Appraisal

Accepted as is ( ) With Minor Modification ( )

Not Accepted Major Revision ( ) Minor Revision ( )

Review Not Completed (Explanation as follows)

Supplementary Material Attached

Issue Lists: Others

Revise and Reschedule (if required) Target Date for Next Review

Verification of Defect Closure

Responsibility of: Planned Date of Verification

Recommended for Release Signature: Date:

Table 4: Technical Review Report

Tip:

To prepare realistic schedule, you can collect data from past projects. Speak to related

project managers regarding time estimation for reviews, the review capacity of the

reviewer, and estimates the review effort accordingly.

Percentage of

Defects Removed

Development

Time

Fastest schedule

(BEST schedule)

Most Organizations Are somewhere around this

point

95% 100%

Development

Time

Software Project Management (CS615)

128

© Copyright Virtual University of Pakistan

Figure 1: Quality Assurance

LECTURE # 20

3. Processes

3.1 Software Process

When you build a product or system, it's important to go through a series of

predictable steps – a road map that helps you create a timely, high-quality result,

The road map that you follow is called a 'software process' .

Software engineers and their managers adapt the process to their needs and then

follow it. In addition, the people who have ties defined by the process requested

the software play a role in the software process.

It provides stability, control, and organization to an activity that can, if left

uncontrolled, become quite chaotic.

At a detailed level, the process that you adopt depends on the software you're

building. One process might be appropriate for creating software for an aircraft

avionics system, while an entirely different process would be indicated for the

creation of a web site.

From the point of view of a software engineer, the work products are the

programs, documents and data produces as a consequence of the software

engineering activities defined by the process.

A number of software process assessment mechanisms enable organizations to

determine the “maturity” of a software process. However, the quality, timeliness

and long-term viability of the product you build are the best indicators of the

efficacy of the process that you use.

A common process framework is established by defining a small number of

framework activities that are applicable to all software projects, regardless of their

size or complexity. A number of task sets-each a collection of software

engineering work tasks, project milestones, work products, and quality assurance

points enable the framework activities to be adapted to the characteristics of the

software project and the requirements of the project team. Finally, umbrella

activities-such as software quality assurance, software configuration management,

and measurement - overlay the process model. Umbrella activities are

independent of anyone framework activity and occur through- out the process.

Software Project Management (CS615)

129

© Copyright Virtual University of Pakistan

⇒ Software Process Vs Software Engineering

But what exactly is a software process from a technical point of view? A software

process is a framework for the tasks that are required to build high-quality

software. Is process synonymous with software engineering? The answer is "yes"

and "no." A software process defines the approach that is taken as software is

engineered. But software engineering also encompasses technologies that

populate the process-technical methods and automated tools.

More important, software engineering is performed by creative, knowledgeable

people who should work within a defined and mature software process that is

appropriate for the products they build, and the demands of their marketplace.

⇒ Software Engineering

Software engineering is a layered technology. Referring to Figure 2, any

engineering approach (including software engineering) must rest on an

organizational commitment to quality. Total quality management and similar

philosophies foster a continuous process improvement culture, and this culture

ultimately leads to the development of increasingly more mature approaches to

Figure 1: The software Process

Tasks

Milestones,

SQA points

Tasks

Framework activities

Common process

Software Project Management (CS615)

130

© Copyright Virtual University of Pakistan

software engineering. The bedrock that supports software engineering is a quality

focus.

Figure 2: Software engineering layers

The foundation for software engineering is the process layer. Software

engineering process is the glue that holds the technology layers together and

enables rational and timely development of computer software. Process defines a

framework for a set of key process areas that must be established for effective

delivery of software engineering technology.

The key process areas form the basis for management control of software projects

and establish the context in which technical methods are applied, work products

(models, documents, data, reports, forms, etc.) are produced, milestones are

established, quality is ensured, and change is properly managed.

Software engineering methods provide the technical how-to’s for building

software. Methods encompass a broad array of tasks that include requirements

analysis, design, program construction testing and support. Software engineering

methods rely on a set of basic principles that govern each area of the technology

and include modeling and other descriptive techniques.

Software engineering tools provide automated or semi-automated support for the

process and the methods. When tools are integrated so that information created by

one tool can be used by another, a stem for the support of software development

called computer-aided software engineering, is established. CASE combines

software, hardware, and a software engineering database (a repository containing

important information about analysis, design, program construction and testing) to

create software engineering environment analogous to CAD/CAE (computeraided

design engineering) for hardware.

Metho

Tools

Process

A quality focus

Software Project Management (CS615)

131

© Copyright Virtual University of Pakistan

3.2 PM Process Groups

Project management processes can be organized into five groups of one or more

processes each:

1. Initiating processes—authorizing the project or phase

2. Planning processes—defining and refining objectives and selecting the best

of the alternative courses of action to attain the objectives that the project

was undertaken to address

3. Executing processes—coordinating people and other resources to carry out

the plan

4. Controlling processes—ensuring that project objectives are met by

monitoring and measuring progress regularly to identify variances from plan

so that corrective action can be taken when necessary

5. Closing processes—formalizing acceptance of the project or phase and

bringing it to an orderly end

Each process is described by:

– Inputs

– Tools & Techniques

– Outputs

3.3 PM Process Links

The process groups are linked by the results they produce—the result or outcome

of one often becomes an input to another.

Among the central process groups, the links are iterated—planning provides

executing with a documented project plan early on, and then provides documented

updates to the plan as the project progresses. These connections are illustrated in

Figure 3.

The project management process groups are not discrete, one-time events; they

are overlapping activities that occur at varying levels of intensity throughout each

phase of the project. These process groups overlap and vary within a phase.

Figure 4 illustrates how the process groups overlap and vary within a phase.

3.4 PM Phase interactions

Software Project Management (CS615)

132

© Copyright Virtual University of Pakistan

Finally, the process group interactions also cross phases such that closing one

phase provides an input to initiating the next. For example, closing a design phase

requires customer acceptance of the design document. Simultaneously, the design

document defines the product description for the ensuing implementation phase.

This interaction is illustrated in Figure 5. Repeating the initiation processes at the

start of each phase helps to keep the project focused on the business need that it

was undertaken to address. It should also help ensure that the project is halted if

the business need no longer exists, or if the project is unlikely to satisfy that need.

It is important to note that the actual inputs and outputs of the processes depend

upon the phase in which they are carried out. Although Figure 5 is drawn with

discrete phases and discrete processes, in an actual project there will be many

overlaps. The planning process, for example, must not only provide details of the

work to be done to bring the current phase of the project to successful completion,

but must also provide some preliminary description of work to be done in later

phases. This progressive detailing of the project plan is often called rolling wave

planning; indicating that planning is an iterative and ongoing process.

Involving stakeholders in the project phases generally improves the probability of

satisfying customer requirements and realizes the buy-in or shared ownership of

the project by the stakeholders, which is often critical to project

success.

Figure 3: Links among Process Groups in a phase

Planning

Processes

Initiating

Processes

Controlling

Processes Executing

Processes

Closing

Processes

Software Project Management (CS615)

133

© Copyright Virtual University of Pakistan

Figure 4: Overlap of Process Groups in a Phase

Figure 5: Interaction between phases

Phase

Start

Phase

Finish

Initiating

Processes

Planning

Processes

Executing

Processes

Closing Processes

Controlling

Processes

Initiating Planning

Executing Controlling

Closing

Design Phase

Initiating Planning

Executing

Controlling

Closing

Implementation Phase

Software Project Management (CS615)

134

© Copyright Virtual University of Pakistan

LECTURE # 21

3. Processes

3.5 Initiating Process

⇒ Inputs

• Product Description

• Strategic Plan

• Selection Criteria

• Historical Information

⇒ Outputs

• Project Charter

• Project Manager assignments

• Constraints

• Assumptions

⇒ Tools and Techniques

• Project selection methods

• Expert judgment

The tasks performed for project initiation are mentioned below:

• Requirement gathering: The first task is to gather the customer requirements.

Customer requirements may be spoken or unspoken. Therefore, the challenge for

the project manager is to elicit the requirements in such a way that both the

spoken and unspoken customer needs and wants are gathered. After collecting the

required information, you need to translate the customer requirements into

technical specifications for the software project.

• Scope determination: The scope of a software project can be defined as the

combination of the software product arid services to be delivered to the customer.

You carry out the scope determination exercise to define the scope of the software

project. The scope determination exercise enables you to refine and understand

the customer requirements. You can refine the scope definition further by

breaking down each deliverable into smaller and more manageable activities. The

scope determination exercise also helps you identify the technology for creating

the software product.

• Resource allocation: During project initiation, you identify the resources required

and allocate them to the software project. The resources identified may be people,

reusable software components, and hardware or software tools. You allocate the

resource to the software project on the basis of the activities defined in the scope

Software Project Management (CS615)

135

© Copyright Virtual University of Pakistan

determination exercise. While allocating appropriate resources for a software

project, you also need to calculate the cost of each resource. The cost of a

resource is calculated according to the duration of the resource in the software

project. Estimating the cost of resources also helps you prepare a budget for the

software project.

• Initial project plan: Another exercise that you carry out during project initiation

is the creation of a rough project plan. This plan is a draft version and carries only

the primitive project plan features. This project plan carries the initial risk

analysis of the software project, the initial start and end dates, the duration of the

activities in the project, and the sequencing of these activities.

3.6 Planning Process

Devising and maintaining a workable scheme to accomplish the business need

that the project was undertaken to address

Planning is setting the direction for something -- some system -- and then guiding

the system to follow the direction.

The basic planning process typically includes similar nature of activities carried

out in similar sequence.

The phases are carried out carefully or -- in some cases -- intuitively, for example,

when planning a very small, straightforward effort the complexity of the various

phases (and their duplication throughout the system) depend on the scope of the

system.

For example, in a large corporation, the following phases would be carried out in

the corporate offices:

• In each division

• In each department

• In each group, etc.

Planning typically includes use of the following basic terms

• Goals: Goals are specific accomplishments that must be accomplished in total, or

in some combination, in order to achieve some larger, overall result preferred

from the system, for example, the mission of an organization. (goals are outputs

from the system.)

• Strategies or Activities: These are the methods or processes required in total, or

in some combination, to achieve the goals. (strategies are processes in the

system.)

Software Project Management (CS615)

136

© Copyright Virtual University of Pakistan

• Objectives: Objectives are specific accomplishments that must be accomplished

in total, or in some combination, to achieve the goals in the plan. Objectives are

usually "milestones" along the way when implementing the strategies

• Tasks: Particularly in small organizations, people are assigned various tasks

required to implement the plan. If the scope of the plan is very small, tasks and

activities are often essentially the same.

• Resources (and Budgets): Resources include the people, materials, technologies,

money, etc., required to implement the strategies or processes. The costs of these

resources are often depicted in the form of a budget. (Going back to our reference

to systems, resources are input to the system.)

Goals and Objectives Should Be SMARTER

SMARTER is an acronym, that is, a word composed by joining letters from

different words in a phrase or set of words. In this case, a SMARTER goal or

objective is:

Specific:

For example, it's difficult to know what someone should be doing if they are to

pursue the goal to "work harder". It's easier to recognize "Write a paper".

Measurable:

It's difficult to know what the scope of "Writing a paper" really is. It's easier to

appreciate that effort if the goal is "Write a 30-page paper".

Acceptable:

If I'm to take responsibility for pursuit of a goal, the goal should be acceptable to

me. For example, I'm not likely to follow the directions of someone telling me to

write a 30-page paper when I also have to five other papers to write.

However, if you involve me in setting the goal so I can change my other

commitments or modify the goal, I'm much more likely to accept pursuit of the

goal as well.

Realistic: Even if I do accept responsibility to pursue a goal that is specific and

measurable, the goal won't be useful to me or others if, for example, the goal is to

"Write a 30-page paper in the next 10 seconds".

Time frame: It may mean more to others if I commit to a realistic goal to "Write

a 30-page paper in one week". However, it'll mean more to others (particularly if

they are planning to help me or guide me to reach the goal) if I specify that I will

write one page a day for 30 days, rather than including the possibility that I will

write all 30 pages in last day of the 30-day period.

Software Project Management (CS615)

137

© Copyright Virtual University of Pakistan

Extending: The goal should stretch the performer's capabilities. For example, I

might be more interested in writing a 30-page paper if the topic of the paper or the

way that I write it will extend my capabilities.

Rewarding: I'm more inclined to write the paper if the paper will contribute to an

effort in such a way that I might be rewarded for my effort.

Software Project Management (CS615)

138

© Copyright Virtual University of Pakistan

LECTURE # 22

3. Processes

⇒ Planning Process Tasks

1. Scope Planning

2. Scope Definition

3. Activity Definition

4. Activity Sequencing

5. Activity Duration Estimating

6. Resource Planning

7. Cost Estimating

8. Cost Budgeting Risk Planning

9. Schedule Development

10. Quality Planning

11. Communications Planning

12. Organization Planning

13. Staff Acquisition

14. Procurement Planning

15. Project Plan Development

1) Scope Planning — developing a written scope statement as the basis for

future project decisions

2) Scope Definition—subdividing the major project deliverables into smaller,

more manageable components

3) Activity Definition—identifying the specific activities that must be

performed to produce the various project deliverables

4) Activity Sequencing—identifying and documenting interactivity

dependencies

5) Activity Duration Estimating—estimating the number of work periods that

will be needed to complete individual activities.

6) Resource Planning—determining what resources (people, equipment,

materials, etc.) and what quantities of each should be used to perform project

activities.

7) Cost Estimating—developing an approximation (estimate) of the costs of the

resources required to complete project activities.

Software Project Management (CS615)

139

© Copyright Virtual University of Pakistan

8) Cost Budgeting—allocating the overall cost estimates to individual work

packages.

9) Schedule Development —analyzing activity sequences, activity durations,

and resource requirements to create the project schedule.

10) Quality Planning—identifying which quality standards are relevant to the

project and determining how to satisfy them.

11) Communications Planning—determining the information and

communications needs of the stakeholders: who needs what information,

when will they need it, and how will it be given to them.

12) Organizational Planning—identifying, documenting, and assigning project

roles, responsibilities, and reporting relationships.

13) Staff Acquisition—getting the human resources needed assigned to and

working on the project.

14) Procurement Planning—determining what to procure, how much to procure,

and when.

15) Project Plan Development —taking the results of other planning processes

and putting them into a consistent, coherent document.

3.7 Executing Process

⇒ Executing Process Tasks

1. Project Plan Execution—carrying out the project plan by performing the

activities included therein.

2. Quality Assurance—evaluating overall project performance on a regular basis to

provide confidence that the project will satisfy the relevant quality standards

3. Team Development —developing individual and group skills/competencies to

enhance project performance

4. Information Distribution—making needed information available to project

stakeholders in a timely manner.

5. Solicitation —obtaining quotations, bids, offers, or proposals as appropriate.

6. Source Selection —choosing from among potential sellers.

Software Project Management (CS615)

140

© Copyright Virtual University of Pakistan

7. Contract Administration —managing the relationship with the seller.

3.8 Controlling Process

Ensuring that project objectives are met by monitoring and measuring progress

and taking corrective measures when necessary

Project performance must be monitored and measured regularly to identify

variances from the plan. Variances are fed into the control processes in the

various knowledge areas. To the extent that significant variances are observed

(i.e., those that jeopardize the project objectives), adjustments to the plan are

made by repeating the appropriate project planning processes. For example, a

missed activity finish date may require adjustments to the current staffing plan,

reliance on overtime, or tradeoffs between budget and schedule objectives.

Controlling also includes taking preventive action in anticipation of possible

problems.

⇒ Controlling Process Tasks

1. Integrated Change Control

2. Scope Verification

3. Scope Change Control

4. Schedule Control

5. Cost Control

6. Quality Control

7. Performance Reporting

8. Risk Response Control

The controlling process group contains core processes and facilitating processes.

1. Integrated Change Control —coordinating changes across the entire project.

2. Scope Verification—formalizing acceptance of the project scope.

3. Scope Change Control—controlling changes to project scope.

4. Schedule Control—controlling changes to the project schedule.

5. Cost Control—controlling changes to the project budget.

6. Quality Control—monitoring specific project results to determine if they comply

with relevant quality standards and identifying ways to eliminate causes of

unsatisfactory performance.

7. Performance Reporting—collecting and disseminating performance

information. This includes status reporting, progress measurement, and

Software Project Management (CS615)

141

© Copyright Virtual University of Pakistan

forecasting.

8. Risk Response Control—keeping track of identified risks, monitoring residual

risks and identifying new risks, ensuring the execution of risk plans, and

evaluating their effectiveness in reducing risk.

3.9 Closing Process

Formalizing acceptance of the project or phase and bringing it to an orderly end.

⇒ Closing Process Tasks

• Contract Closeout —completion and settlement of the contract, including

resolution of any open items.

• Administrative Closure—generating, gathering, and disseminating information

to formalize phase or project completion, including evaluating the project and

compiling lessons learned for use in planning future projects or phases.

Software Project Management (CS615)

142

© Copyright Virtual University of Pakistan

LECTURE # 23

4. PLANNING

Planning is one of the most important management activities and is an ongoing effort

throughout the life of the project. Software project management begins with a set of

activities that are collectively called Project Planning.

• Preliminary planning starts on day one even in the pre-project phase

• It should not be conducted “in secret”

• It needs buy-in and approval

4.1 Project Planning Objectives

The objective of software project planning is to provide a framework that enables the

manager to make reasonable estimates of:

• Resources

• Cost, and

• Schedule

These estimates are made within a limited time frame at the beginning of a software

project and should be updated regularly as the project progresses.

In addition, estimates should attempt to define best case and worst-case scenarios so

that project outcomes can be bounded.

Planning is one of the most important management activities and is an ongoing effort

throughout the life of the project.

Software project management begins with a set of activities that are collectively

called Project Planning.

The software project planner must estimate following things before a project begins:

1. How much will it cost?

2. How long will it take?

3. How many people will it take?

4. What might go wrong?

4.2 Project Planning - Definition

Software Project Management (CS615)

143

© Copyright Virtual University of Pakistan

• What is it? Software project planning involves estimation - your attempt to

determine how much money, how much effort, how many resources, and how

much time it will take to build a specific software-based system or product.

• Who does it? Software Project Managers- Using information solicited from

customers and software engineers and software metrics data collected from past

projects. It is advisable to generate your estimates using at least two different

methods (as a cross check). Problem complexity and risk are considered before a

final estimate is made.

• What is the work product? A Simple table delineating the tasks to be

performed, the functions to be implemented and the cost, effort and time involved

for each is generated. A list of required project resources is also produced.

• How do I ensure that I've done it right? That’s hard, because you won't really

know until the project has been completed. However, if you have experience and

follow a systematic approach, generate estimates using solid historical data, create

estimation, data points using at least two different methods, and factors in

complexity and risk. You can feel confident that you've done a right job to

achieve the targets.

4.3 Project Planning: Key Tasks

1. Set goal and scope

2. Select lifecycle

3. Set organization team form

4. Start team selection

5. Determine risks

6. Create WBS

7. Identify tasks

8. Estimate size

9. Estimate effort

10. Identify task dependencies

11. Assign resources

12. Schedule work

4.4 Project Management Process

The software development management section, which describes the organization and

resources that will be used to develop the product, should always be included. The

management section discusses how the facilities will be organized to support the

development effort. This is one of the sections that provide much of the detail needed

to prepare the heart of the development plan, namely the development schedule. The

schedule provides answers to two basic planning questions: what and when, while

much of the remaining sections discuss how.

Software Project Management (CS615)

144

© Copyright Virtual University of Pakistan

The discussion in the how sections provides information on how the project will be

organized, how risks will be handled, how reviews will be conducted, how standards

will be applied, what development methodologies will be used, and how the product

will be tested.

It is usually best to leave the completion of the schedule section for last. The

schedule, being dependent on most of the other sections, is the most sensitive part of

the development plan. After a first draft of the development plan is ready, an initial

development schedule can then be prepared. As we shall see, the schedule will then

be further refined as the development plan goes through progressive iteration.

Why is the system being developed? The answer to this question enables all parties

to assess the validity of business reasons for the software work. Stated in another

way, does the business purpose justify the expenditure of people, time and money?

What will be done, by when? The answers to these questions help the team to

establish a project schedule by identifying key project tasks and the milestones that

are required by the customer.

Who is responsible for a function? Earlier in this chapter, we noted that the role and

responsibility of each member of the software team must be defined. The answer to

this question helps accomplish this.

Where they are organizationally located? Not all roles and responsibilities reside

within the software team itself. The customer, users, and other stake" holders also

have responsibilities.

How will the job be done technically and managerially? Once product scope is

established, a management and technical strategy for the project-must be defined.

How much of each resource is needed? The answer to this question is derived by

developing estimates based on answers to earlier questions.

The definition phase focuses on what. That is, during definition, the software

engineer attempts to identify what information is to be processed, what function and

performance are desired, what system behavior can be expected, what interfaces are

to be established, what design constraints exist, and what validation criteria are

required to define a successful system. The key requirements of the system and the

software are identified. Although the methods applied during the definition phase will

vary depending on the software engineering paradigm (or combination of paradigms)

that is applied, three major tasks will occur in some form: system or information

engineering, software project planning and requirements analysis.

The development phase focuses on how. That is, during development a software

engineer attempts to define how data are to be structured, how function is to be

implemented within a software architecture, how procedural details are to be

Software Project Management (CS615)

145

© Copyright Virtual University of Pakistan

implemented, how interfaces are to be characterized, how the design will be

translated into a programming language (or nonprocedural language), and how testing

will be performed. The methods applied during the development phase will vary, but

three specific technical tasks should always occur: software design, code generation,

and software testing.

The support Phase focuses on Change associated with error correction, adaptations

required as the software's environment evolves, and changes due to enhancements

brought about by changing customer requirements. The support phase reapplies the

steps of the definition and development phases but does so in the context of existing

software. Four types of change are encountered during the support phase:

1. Correction

Even with the best quality assurance activities, it is likely that the customer will

uncover defects in the software. Corrective maintenance changes the software to

correct defects.

2. Adaptation

Over time, the original environment (e.g., CPU, operating system, business rules,

external product characteristics) for which the software was developed is likely to

change. Adaptive maintenance results in modification I the software to

accommodate changes to its external environment.

3. Enhancement

As software is used, the customer/user will recognize additional functions that

will provide benefit. Perfective maintenance extends the software beyond its

original functional requirements.

4. Prevention

Computer software deteriorates due to change, and because ( this, preventive

maintenance, often called software reengineering, must be conducted to enable

the software to serve the needs of its end users, in essence, preventive

maintenance makes changes to computer programs so that they ca be more easily

corrected, adapted, and enhanced.

In addition to these support activities, the users of software require continuing

support. In-house technical assistants, telephone-help desks, and applicationspecific

Web sites are often implemented as part of the support phase.

4.5 Planning Puzzle

Planning is one of the most important management activities and includes the

preparation of good estimates, the maintenance of the development schedules and the

efficient assignment of personnel.

i. Scope Planning

Software Project Management (CS615)

146

© Copyright Virtual University of Pakistan

Scope planning is the process of progressively elaborating and documenting the

project work (project scope) that produces the product of the project.

ii. Risk Planning

Risk management planning is the process of deciding how to approach and plan

the risk management activities for a project. It is important to plan for the risk

management processes that follow to ensure that the level, type, and visibility of

risk management are commensurate with both the risk and importance of the

project to the Organization.

iii. Schedule Development

Analyzing activity sequences, activity durations, and resource requirements to

create the project schedule.

iv. Cost Estimating

Developing an approximation (estimate) of the costs of the resources required to

complete project activities

v. Project Control

Project Control may be considered to be one of the continuous objectives for the

project manager. As such he is responsible for taking remedial actions, within

the defined terms of reference, to correct potential problems or taking risk

avoidance measures. The prime objective is to protect the integrity of the project

at all times.

4.6 Primary Planning Steps

Once the scope of the project has been defined in the Terms of Reference, the project

enters the detailed planning phase. This involves the creation of a:

1. Project Plan (outlining the activities, tasks, dependencies and timeframes)

2. Resource Plan (listing the labor, equipment and materials required)

3. Financial Plan (identifying the labor, equipment and materials costs)

4. Quality Plan (providing quality targets, assurance and control measures)

5. Risk Plan (highlighting potential risks and actions taken to mitigate them)

6. Acceptance Plan (listing the criteria to be met to gain customer acceptance)

7. Communications Plan (listing the information needed to inform stakeholders)

8. Procurement Plan (identifying products to be sourced from external suppliers).

At this point the project has been planned in detail and is ready to be executed

By this stage, the benefits and costs of the project have been clearly documented, the

objectives and scope have been defined, the project team has been appointed and a

formal project office environment established. It is now time to undertake detailed

planning to ensure that the activities performed in the execution phase of the project

are properly sequenced, resourced, executed and controlled.

Software Project Management (CS615)

147

© Copyright Virtual University of Pakistan

1. Develop Project Plan

The first step is to document the Project Plan. A 'Work Breakdown Structure'

(WBS) is identified, which includes a hierarchical set of phases, activities and

tasks to be undertaken on the project. After the WBS has been agreed, an

assessment of the effort required to undertake the activities and tasks is made. The

activities and tasks are sequenced, resources are allocated and a detailed project

schedule is formed. This project schedule will become the primary tool for the

Project Manager to assess the progress of the project.

2. Develop Resource Plan

Immediately after the Project Plan is formed, it is necessary to allocate the

resources required to undertake each of the activities and tasks within the Project

Plan. Although general groups of resources may have already been allocated to

the Project Plan, a detailed resource assessment is required to identify the:

􀂃 Types of resources (labor, equipment and materials)

􀂃 Total quantities of each resource type

􀂃 Roles, responsibilities and skill-sets of all human resources

􀂃 Items, purposes and specifications of all equipment resource

􀂃 Items and quantities of material resource

A schedule is assembled for each type of resource so that the Project Manager can

assess the resource allocation at each stage in the project.

3. Develop Financial Plan

Similar to the Resource Plan, a Financial Plan is prepared to identify the quantity

of money required for each stage in the project. The total cost of labor, equipment

and materials is quantified and an expense schedule is defined which provides the

Project Manager with an understanding of the forecast spending vs. the actual

spending throughout the project. Preparing a detailed Financial Plan is extremely

important as the project's success will depend on whether or not it is delivered

within the 'time, cost and quality' estimates for this project.

4. Develop Quality Plan

Meeting the quality expectations of the customer is critical to the success of the

project. To ensure that the quality expectations are clearly defined and can

reasonably be achieved, a Quality Plan is documented. The Quality Plan:

􀂃 Defines what quality means in terms of this project

Software Project Management (CS615)

148

© Copyright Virtual University of Pakistan

􀂃 Lists clear and unambiguous quality targets for each deliverable. Each quality

target provides a set of criteria and standards which must be achieved to meet

the expectations of the customer

􀂃 Outlines a plan of activities which will assure the customer that the quality

targets will be met (i.e. a Quality Assurance Plan)

􀂃 Identifies the techniques used to control the actual level of quality of each

deliverable as it is built (i.e. a Quality Control Plan).

Finally, it is important to review the quality not only of the deliverables produced

by the project but also of the management processes which produce them. A

summary of each of the management processes undertaken during the execution

phase is identified, including Time, Cost, Quality, Change, Risk, Issue,

Procurement, Acceptance and Communications Management.

5. Develop Risk Plan

The foreseeable project risks are then documented within a Risk Plan and a set of

actions to be taken formulated to both prevent each risk from occurring and

reduce the impact of the risk should it eventuate. Developing a clear Risk Plan is

an important activity within the planning phase as it is necessary to mitigate all

critical project risks prior to entering the Execution phase of the project.

6. Develop Acceptance Plan

The key to a successful project is gaining acceptance from the customer that each

deliverable produced meets (or exceeds) his/her requirements. To clarify the

criteria used to judge each deliverable for customer acceptance, an Acceptance

Plan is produced. The Acceptance Plan provides the criteria for obtaining

customer acceptance, a schedule of acceptance reviews within which customer

acceptance will be sought and a summary of the process used to gain acceptance

of each deliverable from the customer.

7. Develop Communications Plan

Prior to the Execution phase, it is also necessary to identify how each of the

stakeholders will be kept informed of the progress of the project. The

Communications Plan identifies the types of information to be distributed, the

methods of distributing information to stakeholders, the frequency of distribution

and responsibilities of each person in the project team for distributing information

regularly to stakeholders.

8. Develop Procurement Plan

The last planning activity within the Planning phase is to identify the elements of

the Project which will be acquired from external suppliers to the project. The

Procurement Plan provides a detailed description of the Products (i.e. goods and

services) to be procured from suppliers, the justification for procuring each

Software Project Management (CS615)

149

© Copyright Virtual University of Pakistan

product externally, as opposed to from within the business, and the schedule for

procurement. It also references the process for the selection of a preferred supplier

("Tender Process") and the process for the actual order and delivery of the

procured products ("Procurement Process").

4.7 The Software Development Plan (SDP)

The project development plan is one of the first formal documents produced by the

project. Within this document, the project manager describes in detail:

􀂃 How the project will be developed?

􀂃 What resources will be required?

􀂃 How these resources will be used?

The project development plan assures that the development of the project is well

charted before the main development activities begin. In -addition to the basic

development schedule, the plan addresses such issues as:

􀂃 The timely provision of equipment and tools so that they are available to

developers when needed.

􀂃 The availability of staff to perform the development tasks in accordance with

the schedule.

􀂃 Provision of contingency plans in the event that project risks materialize

􀂃 The designation .of duties within the development team, and the assignment

of these duties to the team members.

Preparing the project plan for a software project helps you ensure that the specified

requirements and objectives are met successfully. It is a collation of all planning

activities that have happened for a software project. This includes activities such as

design and analysis, activity definition, risk planning, and cost estimation. To create

the plan, you assess all planning activities, organizational policies regarding the

creation of the project plan and assumption and constraints for the project. To

implement the software project plan, you require management skills, such as

leadership, communication, and problem solving, along with the basic knowledge

about the software. You also need to ensure that the senior management bf the

company has authorized work on the software project. Knowledge management

techniques help you to make informed decision regarding the project plan.

After the project plan is executed, you manage the changes to it in such a way that the

performance measurement baselines are not impacted, To manage the project plan

effectively you monitor the project plan, periodic performance status reports, and

requests for change. The primary tool that you can use to control the changes in the

project plan is the change control mechanism: This is a set of formal procedures for

changing the project plan.

4.7.1 Software Development Plan (SDP) Information needs

Software Project Management (CS615)

150

© Copyright Virtual University of Pakistan

The Project Plan is a vital part of the project initiation stage. The plan

should normally contain the following information:

1. Introduction and status of the plan

2. The authorisation procedures

3. Statement of project objectives

4. Statement of requirement

5. Deliverables in the project

6. A Work Breakdown Structure

7. The project milestones

8. The resource requirements

9. Interdependencies of work

10. The timetable of events

11. Staffing, organisation and responsibilities

12. Development methods and toolsets to be used

13. Source documentation

14. Resource and financial summary

This information creates the generation of a Project Book (log). The log

should be in a loose-leaf binder with clearly identified sections and version

control exercised over the documentation sets. These logs are now often

retained as computer file, which enables a greater level of security to be

maintained over them and version control to be established as an automatic

feature.

4.7.2 Software Development Plan (SDP) Steps/items required

The contents of the project development plan may be adapted to the size of

the project; it may be a large document or just a few pages. Table 1 presents

an outline of some of the subjects covered in the project development plan.

Not all subjects in Table 1 are applicable to all projects. For example, many

projects do not administer their own budget. Some organizations have a

financial officer responsible for the administration of project budgets. The

interface with external sources is another area riot applicable to all projects.

The term, external sources covers such activities as interfacing with

subcontractors, vendors and representatives of the customer.

Many standards have been produced for the project development plan. The

formal structure or the project development plan document differs,

depending on the actual documentation standard used. For example, the US

DOD standard 2167 provides the option of describing the testing,

configuration management and quality assurance plans in three separate

documents. For large projects, this option can become a requirement.

Software Project Management (CS615)

151

© Copyright Virtual University of Pakistan

The IEEE standard 1058.1 describes what is referred to as the software

project management plan, which is essentially the same as the project

development plan. This standard is largely compatible with the 2167 project

development plan, although it is significantly less detailed.

This standard, too, provides the option of including configuration

management and quality assurance plans, or of describing them in separate

documents. The project development plan should be prepared as a

standalone document, in the sense that it should be read and understood

without the need to refer to other documents.

A general overview of the project is therefore usually included in the first

section of the document. References for additional detail, of course, should

always be provided, including pointers to such documents as the project

contract, the concept document or the market research analysis.

Software Project Management (CS615)

152

© Copyright Virtual University of Pakistan

Table 1: Software project development plan items

1. System overview

2. Software development management

Project organization and resources

Development facilities

Project organizational structure

Personnel

3. Schedule and milestones

Scheduled activities

Milestones and baselines

Activity network diagrams

System component source

Budget administration

Milestone payments

Major budgetary expenditures

Expenditure authorization procedure

4. Risk analysis

5. Security

6. Interface with external sources

7. Procedure for formal reviews

8. Corrective action process

9. Problem change report

10. Software engineering

Standards and procedures

Development methodology

Development resources

Personnel - qualifications and function

11. Testing procedure

12. Software configuration management

13 Software quality assurance

4.7.3 Inputs to SDP

Project plan development uses the outputs of the other planning processes,

including strategic planning, to create a consistent, coherent document that

can be used to guide both project execution and project control. This process

is almost always iterated several times. For example, the initial draft may

include generic resource requirements and an undated sequence of activities

while the subsequent versions of the plan will include specific resources and

explicit dates.

1. Other planning outputs. All of the outputs of the planning processes in

the other knowledge areas are inputs to developing the project plan. Other

planning outputs include both base documents, such as the WBS, and the

Software Project Management (CS615)

153

© Copyright Virtual University of Pakistan

supporting detail. Many projects will also require application area-specific

inputs (e.g., most major projects will require a cash-flow forecast).

2. Historical information. The available historical information (e.g.,

estimating data-bases, records of past project performance) should have

been consulted during the other project planning processes. This

information should also be available during project plan development to

assist with verifying assumptions and assessing alternatives that are

identified as part of this process.

3. Organizational policies. Any and all of the organizations involved in the

project may have formal and informal policies whose effects must be

considered. Organizational policies that typically must be considered

include, but are not limited to:

􀂃 Quality management—process audits, continuous improvement

targets

􀂃 Personnel administration—hiring and firing guidelines, employee

performance reviews

􀂃 Financial controls—time reporting, required expenditure and

disbursement reviews, accounting codes, and standard contract

provisions.

4. Constraints. A constraint is an applicable restriction that will affect the

performance of the project. For example, a predefined budget is a

constraint that is highly likely to limit the team’s options regarding scope,

staffing, and schedule. When a project is performed under contract,

contractual provisions will generally be constraints.

5. Assumptions. Assumptions are factors that, for planning purposes, are

considered to be true, real, or certain. Assumptions affect all aspects of

project planning, and are part of the progressive elaboration of the project.

Project teams frequently identify, document, and validate assumptions as

part of their planning process. For example, if the date that a key person

will become available is uncertain, the team may assume a specific start

date. Assumptions generally involve a degree of risk.

Software Project Management (CS615)

154

© Copyright Virtual University of Pakistan

LECTURE # 24

4. PLANNING

4.7.4 Tools and Techniques for SDP

6. Project planning methodology. A project planning methodology is any

structured approach used to guide the project team during development of the

project plan. It may be as simple as standard forms and templates (whether

paper or electronic, formal or informal) or as complex as a series of required

simulations (e.g., Monte Carlo analysis of schedule risk). Most project

planning methodologies make use of a combination of “hard” tools, such as

project management software, and “soft” tools, such as facilitated startup

meetings.

7. Stakeholder skills and knowledge. Every stakeholder has skills and

knowledge that may be useful in developing the project plan. The project

management team must create an environment in which the stakeholders can

contribute appropriately. Who contributes, what they con-tribute, and when

they contribute will vary. For example:

􀂃 On a construction project being done under a lump-sum contract, the

professional cost engineer will make a major contribution to the

profitability objective during proposal preparation when the contract

amount is being determined.

􀂃 On a project where staffing is defined in advance, the individual

contributors may contribute significantly to meeting cost and schedule

objectives by reviewing duration and effort estimates for

reasonableness.

8. Project management information system (PMIS). A PMIS consists of the

tools and techniques used to gather, integrate, and disseminate the outputs of

project management processes. It is used to support all aspects of the project

from initiating through closing, and can include both manual and automated

systems.

9. Earned value management (EVM). A technique used to integrate the

project’s scope, schedule, and resources and to measure and report project

performance from initiation to closeout.

4.7.5 Outputs from SDP

1. Project plan: The project plan is a formal, approved document used to

manage project execution. The project schedule lists planned dates for

Software Project Management (CS615)

155

© Copyright Virtual University of Pakistan

performing activities and meeting milestones identified in the project plan.

The project plan and schedule should be distributed as defined in the

communications management plan (e.g., management of the performing

organization may require broad coverage with little detail, while a contractor

may require complete details on a single subject). In some application areas,

the term integrated project plan is used to refer to this document. A clear

distinction should be made between the project plan and the project

performance measurement baselines. The project plan is a document or

collection of documents that should be expected to change over time as more

information becomes available about the project. The performance

measurement baselines will usually change only intermittently and then

generally only in response to an approved scope of work or deliverable

change.

4.7.6 SDP Execution

Project plan execution is the primary process for carrying out the project plan the

vast majority of the project’s budget will be expended in performing this process.

In this process, the project manager and the project management team must

coordinate and direct the various technical and organizational interfaces that exist

in the project. It is the project process that is most directly affected by the project

application area in that the product of the project is actually created here.

Performance against the project baseline must be continuously monitored so that

corrective actions can be taken based on actual performance against the project

plan. Periodic forecasts of the final cost and schedule results will be made to

support the analysis.

4.7.7 Inputs to SDP Execution

1. Project plan: The subsidiary management plans (scope management plan,

risk management plan, procurement management plan, configuration

management plan, etc.) and the performance measurement baselines are key

inputs to project plan execution.

2. Supporting detail

3. Organizational policies: Any and all of the organizations involved in the

project may have formal and informal policies that may affect project plan

execution.

4. Preventive action: Preventive action is anything that reduces the probability

of potential consequences of project risk events.

5. Corrective action: Corrective action is anything done to bring expected

future project performance in line with the project plan. Corrective action is

an output of the various control processes—as an input here it completes the

feedback loop needed to ensure effective project management.

4.7.8 Tools and Techniques for SDP Execution

Software Project Management (CS615)

156

© Copyright Virtual University of Pakistan

1. General management skills: General management skills such as leadership,

communicating, and negotiating are essential to effective project plan

execution.

2. Product skills and knowledge: The project team must have access to an

appropriate set of skills and knowledge about the project’s product.

3. Work authorization system. A work authorization system is a formal

procedure for sanctioning project work to ensure that work is done at the right

time and in the proper sequence. The primary mechanism is typically a written

authorization to begin work on a specific activity or work package. The design

of a work authorization system should balance the value of the control

provided with the cost of that control. For example, on many smaller projects,

verbal authorizations will be adequate.

4. Status review meetings. Status review meetings are regularly scheduled

meetings held to exchange information about the project. On most projects,

status review meetings will be held at various frequencies and on different

levels (e.g., the project management team may meet weekly by itself and

monthly with the customer).

5. Project management information system.

6. Organizational procedures. Any and all of the organizations involved in the

project may have formal and informal procedures that are useful during

project execution.

4.7.9 Outputs from SDP Execution

1. Work results. Work results are the outcomes of the activities performed to

accomplish the project. Information on work results—which deliverables have

been completed and which have not, to what extent quality standards are

being met, what costs have been incurred or committed, etc.—is collected as

part of project plan execution and fed into the performance reporting process.

It should be noted that although outcomes are frequently tangible deliverables

such as buildings, roads, etc., they are also often intangibles such as people

trained who can effectively apply that training.

2. Change requests. Change requests (e.g., to expand or contract project scope,

to modify cost [budgets], or schedule estimates [dates, etc.]) are often

identified while the work of the project is being done.

Software Project Management (CS615)

157

© Copyright Virtual University of Pakistan

LECTURE # 25

4. PLANNING

4.7.4 Elements of SDP

Project Plan is iteratively defined through Concept & Requirements Phase. Initial

estimates are refined as scope and requirements become clearer. There are two

phases of project plan:

1. Preliminary

2. Final

Following are some elements of Software Project Plan:

a) Scope Planning

• Scope planning is the process of progressively elaborating and documenting

the project work (project scope) that produces the product of the project.

• Project Scope Planning starts with the initial inputs of product description, the

project charter, and the initial definition of constraints and assumptions.

• Note that the product description incorporates product requirements that

reflect agreed-upon customer needs and the product design that meets the

product requirements.

• The outputs of scope planning are the scope statement and scope management

plan, with the supporting detail.

• The scope statement forms the basis for an agreement between the project and

the project customer by identifying both the project objectives and the project

deliverables.

• Project teams develop multiple scope statements that are appropriate for the

level of project work decomposition.

b) Objectives – Business Requirements

– Could be “Mission Statement”

– Defines Business objectives for project

– Includes Business Case (NPV Model) & Detailed Description of assumptions.

c) Technical Approach

Software Project Management (CS615)

158

© Copyright Virtual University of Pakistan

• Description of how new system is to be developed

– Technologies

– In House vs. Consultants

– Derivatives of existing (i.e. use existing object model)

– Architectural Layout – Layers

d) Contractual Aspects

• Specifies general needs from outside sources

– Consultants

– Software Suppliers

– Hardware Suppliers

– Network/Infrastructure Suppliers

• There are two types of contracts

1. Cost -Plus

2. Fixed Price

Most other relationships are some kind of combination of these two

1. Cost-plus (also called Time and material)

Cost-plus is a contractual relationship where the developer is paid for the cost of

the service provided and in addition is allowed an agreed profit margin.

This is rather like renting a car the customer pays for the time that the car is used

(by the hour, day, week etc.), and for any other expenses such as insurance and

gasoline.

2. Fixed price

A fixed price contract is a commitment by the developer to provide an agreed

product or service for an agreed fee, within an agreed schedule.

This is similar to purchasing a bus ticket, when the bus company agrees to take

the customer to a specific destination within a published timetable, and for an

agreed fee.

e) Schedules

• Defines specific dates for milestones components

• Work Breakdown Structure

• Use Scheduling Engines like MS project etc.

f) Resource Allocation

Software Project Management (CS615)

159

© Copyright Virtual University of Pakistan

• Resources such as licenses, servers, or other software/hardware related items

• Personnel – how many people of what type and for how long

(Remember these are initial estimates in preliminary project plan)

g) Evaluation Methods

• What methods to be used to validate performance

– Testing for adherence to spec

– Monitoring usage

• Web trends

• Database Logs

– Transaction logs

– Setup schedule for reviews

h) Overview of Project Management

• Define where possible problems can occur

– New technologies

– Business risks

– Resources

• Define Contingency Plans

– Development methods

– If the worst happens, what to do

Software Project Management (CS615)

160

© Copyright Virtual University of Pakistan

LECTURE # 26

5. ORGANIZATION

4.8.1 Life cycle Models

To ensure the successful execution of a project, it is necessary to break down the

project into: multiple manageable tasks.

Each task is performed in a series using processes. To understand what a process

is, consider an example of a non software-related project. You are planning the

market launch of an office management product. To create an effective plan, you

need to perform certain tasks.

• First, you schedule a meeting of all managers and the Finance, Marketing,

Production, and Systems personnel. You can follow a process to complete

this 'task. You may send email messages or call them up personally.

• Next, you decide some feasible marketing and advertising strategies.

Again there are processes that help you select the strategies.

• Fina1ly, you determine the territory where the product should be launched.

This is done in consultation with the Production and Marketing

departments.

Just like a non software-related project plan consists of multiple processes, a

software development activity also consists of multiple tasks. A process or a

combination of multiple processes is required to complete each task. A typical

SDLC follows a consistent sequence of processes or a process model.

A process is defined as a collection of related tasks with specific milestones. To

ensure smooth progress of a software project, relevant processes are arranged and

executed in a sequence. Every software project is discrete with respect to its

complexity, size, and goals. Therefore, different process models are designed for

different software projects. These process models provide approaches that decide

the path of software development from the conceptualization of a project to its

formal termination.

1. The Waterfall model: This is the traditional life cycle model. It assumes that

all phases in a software project are carried out sequentially and that each

phase is completed before the next is taken up.

2. The Prototyping Model: A model that works on an iterative cycle of

gathering customer requirements, producing a prototype based on the

requirement specifications, and getting the prototype validated by the

Software Project Management (CS615)

161

© Copyright Virtual University of Pakistan

customer. Each iteration of the life cycle builds on the prototype produced in

the previous iteration.

3. The Incremental Model: The Incremental model is an example of an

evolutionary life cycle model. It combines the linear nature of the Waterfall

model and the iterative nature of the Prototyping model. The Incremental

model divided the development life cycle into multiple linear sequences, each

of which produces an increment of the final software product. In this model,

the software product is developed in builds. A build is defined as a selfcontained

unit of the development activity. The entire development cycle is

planned for a specific number of logical builds, each having a specific set of

features.

4. The Spiral model: Another evolutionary life cycle model that combines the

linear nature of the Waterfall model and the iterative nature of the Prototyping

model. The project life cycle is divided into phases, and each phase is

executed in all of the iteration of the Spiral Model.

5. The RAD Model:

A Process defines the overall processes that an organization needs to follow to

manage a project efficiently. It defines a structured approach to sequence the

phases and identify the requirements of each phase in the SDLC. The definition of

the phases in a process model helps organize, monitor, and execute a project

efficiently.

A process model is flexible and does not follow any rigid rules of implementation.

An organization can deploy a totally new process model for its overall software

development effort. It can also customize an existing process model to merge with

its implemented process model. For example, figure 1, shows two process models,

A and B. Process model A was used by an organization that manufactures

confidential defense applications. The management used the model to plan

extensively for unexpected project risks. However, after discussing with the

project managers and system analysts, the organization wants to merge its current

process model with a model lat has simple and consistent SDLC phases. This

leads to the evolution of the process model B.

Software Project Management (CS615)

162

© Copyright Virtual University of Pakistan

Figure: Customizing Process Models

4.8.2 Choosing the lifecycle model

In choosing a lifecycle model for your project, you should examine:

1. How well requirements are understood at the beginning? Is it going to

change when moving through the project?

2. Is system architecture understood? Any changes on the way?

3. Level of reliability?

4. Level of re-design for future versions?

5. Risk Level?

6. Stuck With Predefined Schedule?

7. Need For Midcourse Correction?

8. Customer Informed through the Project?

9. Visible Management through the Project?

10. If a Model is chosen, how much it needs Modification?

Selecting an appropriate process model is crucial because it can provide a basic

framework to initiate and carry out a project to its conclusion. It also defines the path for

various project- related activities.

For example, if you select a process model, you know for sure that you need to carry out

certain activities, such as planning, scheduling, resource allocation, risk management, and

cost and effort estimation. These activities ensure smooth progress of a project within the

Process Model A Process Model B

Software Project Management (CS615)

163

© Copyright Virtual University of Pakistan

allocated time and ensure maintenance of quality and measurability throughout the

project.

With so many process models available, a project manager is likely to face the dilemma

of selecting the right process model for managing a software project efficiently.

To select a process model that is suitable to a project, the following criteria can be

considered:

• Business goals of the organization

• Expected size of the project

• Client and project requirements

• Availability of funds and development staff

• Risks perceived in the project

Business Goals of the Organization

This criterion indicates the overall approach and mindset of an organization. If the

organization has a past history of developiI;1g projects in accordance with well-defined

plans and other job aids in every phase, the suitable process model can be the Waterfall

model. However, if the organization is well equipped with the resources to deal with

financial, technological, and personnel risks, it can choose the Spiral model. The

organization can choose the Prototyping model if it is used to working in an experimental

and a constant feedback mode.

Expected Size of the Project

If the size of a project is extensive and the client prefers all the features of the proposed

project at the first delivery, you can select the Waterfall model. When you want the entire

product to be developed and delivered in piecemeal so that the clieI;1t can immediately

begin the unit testing of each module, you would select the Incremental model. In

contrast, if the size of the project is doubtful, you can go for the Prototyping or Spiral

model. These models help to develop projects that have a vague and uncertain estimate of

the project size.

Client and Project Requirements

The Waterfall model or the Incremental model is chosen if the client needs and the

project requirements are defined and approved. In addition, no changes or negligible

changes are 1 expected in the future regarding design requirements. In contrast, you

would choose the Spiral j and Prototyping models when the client needs and system

requirements are uncertain and is likely to change in the future.

Availability of Funds and Development Staff

The Waterfall and Prototyping models require predetermined and adequate resources at

the start of a project. However, if you expect additional funds and human resources as

you progress through the different phases, you should go in for the Incremental or Spiral

models. This is because the Incremental model operates on the assumption of developing

a project into several builds due to lack of human resources. Similarly, the funds and

Software Project Management (CS615)

164

© Copyright Virtual University of Pakistan

staffing requirements in the Spiral model may increase or decrease depending on the

changes in requirements arid feasibility of the proposed project in the future.

Risks Perceived in a Project

This is yet another important criterion for the selection of a process model. You choose

the Waterfall or Incremental model if the occurrence of risks and their impact perceived

is minimum. However, you should go in for the Spiral model if the risks and their

perceived impact are very high.

You should use the waterfall model if:

• The project is large yet it is clearly divided into discrete phases and each phase

has defined number of days, personnel, and resources allocated. The Waterfall

model requires the presence of defined phases and processes in each phase.

• The development also perceives that it can have defined set of input and certified

output. This is because each phase would lead to another and the next phase

would not begin until the previous phase is certified as closed. This way baselines

and milestones for each phase can be identified. The Waterfall model assumes the

closure of a previous phase before the successive phase begins. This ensures

linear progression of a project where developers do not need to revert to an earlier

phase or a process.

• The development team is not likely to face any bumps in the development process

because of clear cut project requirements as well documentation provided to them

by the client. Clarity of project vision and project requirements are the essential

features of the Waterfall model, which are fulfilled in the preceding scenario.

Therefore, if the requirements are defined and a project is large enough to be divided into

defined phases, you can go for the Waterfall model.

However Waterfall model has the following drawbacks:

• There cannot be a sudden crossover from one phase to the next. Real-time projects

require sudden crossover between phases because such projects are subjected to

change in every phase of the development cycle. For example, real-time projects such

as embedded software development where the phases and the requirements for every

phase cannot be determined at the analysis phase cannot deploy the Waterfall model.

• Another reason for the unpopularity of the Waterfall model is that it requires too

much effort for stringent documentation-in every phase. Every phase is closed with

formal documentation. Projects with predictable final product, such as banking

software or an airline reservation project, usually have formal documentation. This is

because the phases of these projects are defined. However, it is difficult for research

and development (R&D) related projects to complete all project documentation.

• The Waterfall model does not support the development of a working model of a

Software Project Management (CS615)

165

© Copyright Virtual University of Pakistan

project first and then further development based on client feedback. Absence of a

working model prevents you from detecting an issue in an early phase. As a result,

you incur higher expenditure in rectifying the issue in a later phase. This in turn has

an adverse effect on the effort, cost, and time spent on rework.

• Finally, the Waterfall model causes, as a "blocking state". When a blocking state

occurs, some team members wait for other team members to finish a dependent task.

For example, in the following figure, the team member assigned to do the design task

cannot begin work until the analysis is complete. This delays the turnaround of the

software project. Many times, the blocking state wastes a lot of developers' time that

could have been spent on productive project -related work.

Figure: Idle Team Members in the Phases of the Waterfall Model

You should use Prototyping model when:

• The client is not clear about the requirements of the proposed system or

Analysis

Design

Coding

Testing

Implementation &

Design

Software Project Management (CS615)

166

© Copyright Virtual University of Pakistan

• When there is a conflict in client requirements.

To resolve the conflict, the development team develops a working model so that the

requirements of the client become defined. Defined client requirements enable the

physical development of the actual product.

The Prototyping model enables an analysis team to first construct a working model with

their prior software experience combined with the vague needs of the client.

The Prototyping model can be as simple as a drawing on a paper or as complex as the real

working software. The closer your prototype is to the actual product, the more precise is

your evaluation.

There are different types of prototyping methods that an organization can implement:

• Rapid prototyping

• Reusable prototyping

• Modular prototyping

Rapid prototyping

This model is suitable when:

• The cost and time required to create a prototype is minimal.

• The project has a substantially long cycle

• Development team wants the design to be strong.

Reusable prototyping

This model is used when:

• The old design needs major changes but the supplementary components of the old

design do not need major changes.

Modular prototyping

This model is used when:

• Considerable cost, time and effort are deployed to create a prototype.

• Client feedback for enhancements is not major

• Minor improvisations are needed to obtain client approval.

Using the Prototyping model saves cost and time involved in the build-it-twice approach.

The experience of developing the prototype is useful for developers while developing the

final product. It reduces the risks of an unfeasible project design because the developers

gain a fair idea of the resources and the probable time taken to create the [mal product.

They also get a feel of the implementation tool to be used in the project.

Incremental Model

Software Project Management (CS615)

167

© Copyright Virtual University of Pakistan

You can use the Incremental model approach in software projects:

• Where human resource is scarce.

In such cases, the management can decide to divide and develop a product in individual

builds. When the resources are available, the subsequent builds are planned and executed.

This process model is useful in real life because normally all the resources required to

complete the project are not available at the same time.

Example:

Consider a situation in which you might need to use the Incremental model of SDLC.

Supersoft2000 requires a software product that automates the employee and their salary

details. It has assigned this project to Blue Valley Consulting (BVC) that specializes in

developing Human Resources (HR)-related applications. The project requirements are

defined to start the project. However, the client wants to roll out the new system for the

benefit of its employees as early as possible. The analysis team in BVC has been able to

divide the entire project into seven independent modules. On the basis of their prior

experience, it feels each module can be executed and deployed independently by the

client. After all the modules are completed, the maintenance team in BVC can assemble

and implement the system at the client site. Currently, the development personnel in BVC

are hired on contract and BVC faces shortage of skilled personnel.

In such a case, you use the Incremental model because of the following reasons:

• Time and lack of skilled personnel are the main hindrances in this project.

Therefore, by using the Incremental model, you can design, develop, and deliver

independent modules. This way by using a few skilled personnel you are able to develop

a system with basic features and provide it to the client immediately. The most important

and the least dependent module are developed first. While the client is using the module,

BVC can arrange for additional skilled personnel to complete the rest of the modules and

deliver them to the client.

The Incremental model enables you to revert to an earlier phase and refine the product

based on client feedback. After all the modules have been developed, the development

personnel can be released. BVC can then hire or retain a few experienced personnel to

create a maintenance team. This team would assemble and implement the entire

employee salary details product at the client site. This flexibility of personnel can be

exercised because you use the Incremental model. Using the Incremental model enables:

• Division of skilled labor

• Division of a complex project into modules

• Development of those modules within a short time frame

Software Project Management (CS615)

168

© Copyright Virtual University of Pakistan

Therefore, if time and skilled personnel are constraints of a Project, you can effectively

use the Incremental model.

Spiral Model

The basic goal of using the Spiral model is to define ways of eliminating risks in the

design phase. Consequently, minimum and manageable risks percolate into the

development phase.

Example:

LMN Inc. has acquired a project to develop a telecommunications project using the

Voice-over Internet telephony (VOIP) technology. The company does not have any prior

experience or the required level of expertise to develop such a project. There is a team of

three analysts and the company does not propose to dedicate a team to complete this

project. This is because it anticipates many risks and a large amount of rework that may

add to the cost of project execution. The company has determined multiple models and

designs to execute the project. After presenting the models to the client, the client is itself

confused. However, it assures LMN Inc. of continued feedback and support. The client

fully understands the ambitiousness of the project and does not consider time and budget

as constraints for the project. Consequently, LMN Inc. decides to use the client feedback

and risk analysis effectively until the end of the project.

In this situation, you would use the Spiral model because of the following reasons:

• LMN Inc. has no prior experience or expertise in executing such a project.

Therefore, it expects a lot of rework in reverting to an earlier phase and

incorporating client feedback therein. Using the Spiral model, you can to revert to

an earlier phase to incorporate client feedback and compete that phase.

• It needs to perform risk analysis effectively to eliminate losses arising due to

uncertain development models, resource requirements, project constraints, and

time.

• It is also preferable to create a prototype for every deliverable that LMN Inc.

might deem necessary to receive client feedback.

• Spiraling cumulative project costs can be covered up by the liberal budget

provided by the client.

4.9 Planning Documents

You (the PM) need to choose which documents are appropriate. Documents do not have

to be lengthy.

The requirements phase produces one main product document:

• The software requirements specification document

And two Project Planning Documents:

Software Project Management (CS615)

169

© Copyright Virtual University of Pakistan

1. The Project Development Plan

• The Software Test Plan

The requirements phase formally concludes with the project's first major review: the

software requirements review (SRR). It is this review that signs off the requirements

specification and formally declares the requirements document as the first approved

project baseline.

2. The Statement of Requirement (SOR)

The project manager (or the advising consultant adopting this role) must ensure

that the project sponsor has produced a written statement of requirements (SOR).

This must be a thorough document which is:

o Unambiguous

o Fully defined or complete

o Verifiable deliverables

o No conflicts

o Consistent

o Auditable

The SOR will be the document against which change control will be exercised.

The SOR should be closely matched to the contract and there should be no

conflict of interests between the two. Where consultants are involved, the client or

sponsor SOR will normally form the basis of the proposal. All of these documents

must carefully align and there should be no scope for misinterpretation, confusion

or lack of understanding. This will be the cornerstone of the project.

3. System Specification

If a System Specification has been properly developed, nearly all information

required for a description of software scope is available and documented before

software project planning begins. In cases where a specification has not been

developed, the planner must take on the role of system analyst to determine

attributes and bounds that will influence estimation tasks.

4. Design Specification

The first stage of risk analysis requires a review of all, project technical and

administrative plans in order to identity potential problems. It includes:

• The project development plan

• The requirements specification

• The design specification

Software Project Management (CS615)

170

© Copyright Virtual University of Pakistan

All major dependencies in the project development plan are examined and

evaluated.

Examples may be the dependence on external sources such as subcontractors,

vendors and suppliers, and service providers. Problems will arise if external

components or services are not provided on time, or if they do not function as

expected.

The project design specification is a detailed plan of how the requirements are to

be implemented.

The implementation decisions involved may contain potential problems, For

example, problems will arise if the selected hardware turns out to be inadequate,

such as if the CPU is too slow, the LAN is not sufficiently reliable, or the

maximum available memory is insufficient.

A list of all anticipated problems is then compiled, identifying each problem and

describing the potential effect on the project. Following table presents an example

of an anticipated problem list.

Table 1: Example of an anticipated problem list

Problem Description

1. Late delivery of the If the computer is not delivered by June 1, as

Development computer planned the integration phase will be delayed.

2. Insufficient memory The size of the memory resident part of the

System may exceed 8 megabytes (the maximum

memory size supported by the computer).

3. No operating system The system requires changes to the standard expert

operating system. John Adams is the only OS

Expert in the company, and he may not be available

for this project.

4. System response time The required system response time to the

input

too slow. may exceed the 5 seconds specified in the

requirements.

5. High staff turnover The schedule is tight with only minimal slack

time. If there is more than average staff

Replacement during development, we will slip the

schedule.

Software Project Management (CS615)

171

© Copyright Virtual University of Pakistan

6. Communication The standard communications package is too

too slow slow. The design is based on the new binary

Communication package. This package has never

Been used with this system and may not be suitable.

7. Late delivery of the The data based subsystem is subcontracted to

Data base subsystem Software Developer Inc. (SDI), who have

Committed to delivery by April 15, SDI may not

Deliver on time, thus delaying the final integration

and test phase.

The anticipated problem list should be compiled with the participation of the

principle members of the project development team. Other people may also be

invited to contribute to the list, based on their experience and technical or

administrative knowledge. This might include people from other project teams,

support groups, the company's legal department or the purchasing department.

While the objective is not to list every conceivable problem that any project may

experience, it is necessary to identify those problems that should reasonably be

considered in relation to the project. In any event, the following analysis stage is

designed to isolate only those problems that could have significant impact on the

project, and that can reasonably be expected to appear.

5. The Data Item Descriptions (DID s)

Standard 2168 (DOD 1988b) contains the requirements for the development,

documentation and implementation of a software quality program. The software

quality program includes planning for and conducting:

􀂃 Evaluations of the quality of software

􀂃 Associated documentation and related activities

􀂃 Follow-up activities necessary to assure timely and effective resolution of

problems

The DID s are a comprehensive set of documentation standards that cover all

phases of software development, maintenance and the production of user

reference manuals. The DID s include a section called preparation instructions

that provide a large degree of freedom by permitting tailoring of the document

format and the use of alternate presentation styles. The full set of DID s is

described in Table 2.

Standard 2167 states that it is not intended to specify or discourage the use of any

particular software development method (DOD 1988a). However, as mentioned

previously, the standard is heavily inclined toward phased development

methodologies, such as the Waterfall paradigm. The phased approach is inherent

Software Project Management (CS615)

172

© Copyright Virtual University of Pakistan

in the required development stages and reviews, requiring system design to be

followed by software requirements, software design, implementation and testing.

The Data Item Descriptions define the formal documentation standards for all

required documents generated during the development of software according to

standard 2167. DID s apply to the development of one or more computer system

configuration items (CSCI s), a term used throughout the 2167 standard to

identify high level decomposition components of a computer system.

Table 2: DOD Data Item Descriptions (DID s)

Development documentation

• Software development plan

System documentation

• System/segment specification

• System/segment design document

Software design and requirements

• Software requirements specification

• Software design document

Interface design and requirements

• Interface requirements, specification

• Interface design document

Version description

• Version description document

Test documentation

• Software test plan

• Software test description

• Test report

Release manuals

• Computer system operator's manual

• Software user's manual

• Software programmer's manual

• Firmware support manual

Maintenance documentation and source code

• Computer resources integrated support document

• Software product specification

Software Project Management (CS615)

173

© Copyright Virtual University of Pakistan

A CSCI, as applied to software; is a component of the system that can be

individually controlled, configured, tested and documented. CSCI s are often

reviewed and approved as separate development items, and though a single

review or audit can consider more than one CSCI, each is usually addressed

separately during the review process. There are no clear-cut guidelines for the

division of a software system into CSCI s as the division is essentially one of

convenience.

Table 3: DOD Data Item Description standards

Data requirements title Acronym

1. System segment design document SSDD

2.Software development plan SDP

3.Software requirements specification SRS

4. Interface requirements specification IRS

5. Interface design document IDD

6. Software design document SDD

7. Software product specification SPS

8. Version description document VDD

9. Software test plan STP

10. Software test description STD

II. Software test report STR

12. Computer system operator's manual CSOM

13. Software user's manual SUM

14. Software programmer's manual SPM

15. Software support manual FSM

16. Computer resources integrated support document CRISD

17. Engineering change proposal ECP

18. Specification change notice SCN

Table 3 contains a list of the DID s referenced by standard 2167A. The software

quality DID is referenced separately in the DOD software quality program

standard 2168. All DID document formats follow a similar pattern. Several of the

sections are common to most, if not all of the documents, such as:

• Title page format

• Table of contents

• Scope (including identification, overview, references etc.)

• Other applicable documents

• Notes and appendices

Software Project Management (CS615)

174

© Copyright Virtual University of Pakistan

phasis is on the required content and not on the required format. This is

specifically addressed in the preparation instructions accompanying each DIn

addition, the page format, page numbering scheme, section numbering scheme

and various other preparation instructions are common. This clearly suggests the

use of an automatic tool to assist in the preparation of the documents, a practice

greatly encouraged by the 2167 standard. Many such tools have been developed

to support 2167, and Polack, in a paper analyzing the use of CASE tools for DOD

projects (Polack 1990), concludes that these tools do indeed save time, and result

in a higher quality software system.

Each DID describe the requirements for the preparation of a specific document,

but the main emID, which state that other presentation styles, including charts,

tables or matrices, are acceptable (e.g. Hatley and Pirbhai (1988) or Ward and

Mellor (1986). There is also substantial flexibility in the requirements regarding

the content of the documents. The standard provides for considerable tailoring to

adapt the standard to the type of project being developed.

Tailoring the standard

Tailoring of standard 2167 is not only encouraged, it is required. The foreword to

2167 states that the standard must be appropriately tailored by the Program

Manager to ensure that only cost-effective requirements are cited in defense

solicitations and contracts.

The DOD has issued a guide for tailoring that can be used as a reference source

for adapting the standards to the type of project being developed. Two basic

principles apply to tailoring:

• The tailoring process is the deletion of non-applicable requirements.

• Tailoring of the standard should be carried out by the contracting agency.

The first principle means that these modifications can only include the deletion of

requirements from the standard (and not changes to the requirements in the

standard). The second principle means that the contractor (i.e. the developer)

cannot tailor the standard without receiving permission from the contracting

agency (i.e. the DOD).

Tailoring of the 2167 standard must be completed as early as possible. This is best

performed either during contract negotiations or as one of the initial activities as

soon as the project begins. The following is a description of the basic procedure

for tailoring standard 2167:

1. Review all standard 2167 requirements, including;

• reviews and audits

• documentation

Software Project Management (CS615)

175

© Copyright Virtual University of Pakistan

• testing activities

• quality assurance activities

• configuration control activities

• other required development activities

2. Identify the requirements that are not applicable, justifiable or reasonable for

the project being developed. For example, the Firmware Support Manual will

not be required if no firmware is being developed: or two design reviews

(POR and COR) may not be necessary for a small project.

3. Prepare a list of requests for deletions from the standard. This may include:

• exclusion of documents

• exclusion of sections in documents

• exclusion of activities.

• exclusion of parts of activities

4. Prepare a written description of the justifications for each item that is

requested to be tailored out.

5. Submit the tailoring request, together with the justification, as early as

possible (preferably before the project begins).

In order to be able to differentiate between forgotten items and tailored items, all

tailored items must be clearly referenced. When submitting a list of documents for

a formal review or milestone, all documents tailored out should be listed together

with a statement to that effect. Within a document, when a paragraph is tailored

out a statement to that effect will appear directly after the paragraph number. If a

paragraph and all of its subparagraphs are tailored out, only the highest level

paragraph number need be included.

The list of the DID s together with the list of tailoring approvals are an integral

part of the project deliverables. Until tailoring approval has been granted, the

developer is obligated to provide the full list of Dills, with all their inclusions.

This is the reason why tailoring should be concluded as early as possible.

6. The software configuration management plan (SCMP)

The software configuration management plan (SCMP) is part of the project's

software development plan. The SCMP may appear as a separate document or as

a section within the project development plan.

The SCMP documents the resources that are needed, how they are to be used, and

which standards and procedures will be applied during the project.

Software Project Management (CS615)

176

© Copyright Virtual University of Pakistan

The SCMP then becomes the mandate for the configuration control group during

project development. The issuance of this plan is the responsibility of the project

manager, though in large projects it may be delegated to the configuration Control

manager.

Table 4 contains a list of the main subjects covered in the SCMP. When any of

these subjects is covered elsewhere (e.g. in the software quality assurance plan), it

can be omitted from the SCMP and replaced by a pointer to the document in

which it is covered. Though most of the subjects in Table 1 are self-descriptive,

the following are some guidelines:

Configuration status accounting describes the way in which status information

flows:

􀂃 From the developers to the configuration management organization (audits

and reviews)

􀂃 From the configuration management organization to project management

(status reporting procedures)

Configuration identification describes the method for designating development

items as SCCI s. This is part of the high level decomposition of the system into

major development components.

The section on identification methods describes the way in which each component

generated by the project is marked for unique identification. Security, restricted

access and classification refer to the secure development of sensitive products

(such as documents, software, patents, military classified information etc.). It is

often convenient to assign many of these tasks to configuration control because of

the need to be involved in the review and classification of documents and other

related activities that are associated with security.

Subcontractors, vendors and suppliers mayor may not implement their own

configuration management plan. It is the project manager's responsibility to assure

that either subcontractors or external developers submit a CMP for review, or that

the project's configuration manager assumes responsibility for their work.

The SCMP may also include diagrams and flow charts to describe procedures for

submitting change requests, or for reporting problems.

7. Statistical software process improvement (SSPI)

As an organization becomes more comfortable with the collection and use or

process metrics, the derivation of simple indicators gives way to a more rigorous

approach called statistical software process improvement (SSPI).

Software Project Management (CS615)

177

© Copyright Virtual University of Pakistan

In essence, SSPI uses software failure analysis to collect information about all

errors and defects encountered as an application, system, or product is developed

and used. Failure analysis works in the following manner:

1. All errors and defects are categorized by origin (e.g., flaw in specification, flaw in

logic, non conformance to standards).

2. The cost to correct each error and defect is recorded.

3. The number of errors and defects in each category is counted and ranked in

descending order.

4. The overall cost of errors and defects in each category is computed.

5. Resultant data are analyzed to uncover the categories that result in highest cost to

the organization.

6. Plans are developed to modify the process with the intent of eliminating or

reducing the frequency of the class of errors and defects that is most costly.

Table 4: Example of the contents of a software configuration management plan

1. Software configuration management organization and resources

􀂃 Organization structure

􀂃 Personnel skill level and qualifications

􀂃 Resources

2. Standards, procedures, policies and guidelines

3. Configuration identification

􀂃 Method for defining SCCI s Description of the SCCI s for this project

4. Identification methods (naming and marking of documents, software components,

revisions. releases, etc.)

5. Submission of configuration items

􀂃 Approval/rejection procedure

6. Change control

􀂃 Change control procedures (method of submission, review. approval and

rejection)

􀂃 Reporting documentation (change requests, problem reports)

􀂃 Change review procedures and review board

7. Version control

􀂃 Preparation of software and documentation versions

􀂃 Release approval procedure

8. Storage, handling and delivery of project media

􀂃 Storage requirements

􀂃 Backups

Software Project Management (CS615)

178

© Copyright Virtual University of Pakistan

9. Configuration control of subcontractors, vendors and suppliers

10. Additional control

􀂃 Miscellaneous control procedures

􀂃 Project specific control (security etc)

11. Configuration status accounting

􀂃 Configuration audits and reviews

􀂃 Configuration structure reporting procedures

12. Configuration management major milestones

13. Tools, techniques and methodologies

8. Communications management plan

A communications management plan is a document that provides:

• A collection and filing structure that details what methods will be used to gather

and store various types of information. Procedures should also cover collecting

and disseminating updates and corrections to previously distributed material.

• A distribution structure that, details to whom information (status reports, data,

schedule, technical documentation, etc.) will flow, and what methods (written

reports, meetings, etc.) will be used to distribute various types of information.

This structure must be compatible with the responsibilities and reporting

relationships described by the project organization chart.

• A description of the information to be distributed, including format, content, level

of detail, and conventions/definitions to be used.

• Production schedules showing when each type of communication will be

produced.

• Methods for accessing information between scheduled communications.

• A method for updating and refining the communications management plan as the

project progresses and develops. The communications management plan may be

formal or informal, highly detailed or broadly framed, based on the needs of the

project. It is a subsidiary component of the overall project plan.

9. The software quality assurance plan

Every project must have a quality plan. The quality plan will be presented as a

section in the project plan.

Software Project Management (CS615)

179

© Copyright Virtual University of Pakistan

It is drawn up by the project manager at the start of the project and should be

agreed with the project sponsor.

You would expect the quality plan to contain the following elements:

􀂃 Statement of the quality control organisation

􀂃 Identification of specific standards and methods that will be used

􀂃 Definition of the quality control procedures; this is aligned to the Work

Breakdown Structure

􀂃 Specification of quality milestones

􀂃 Detail of unusual features

􀂃 Change control and configuration management

􀂃 Detail of acceptance procedures

􀂃 Specification of quality assurance procedures

The software quality assurance plan (SQAP), like the software configuration plan,

is also part of the overall software project development plan.

The SQAP documents which resources are needed, how they should be used and

which standards and procedures will be applied during the project.

The SQAP then becomes the mandate for the quality assurance group during

project development. The issuance of this plan is the responsibility of the project

manager, though in large projects it will usually be delegated to the quality

assurance manager.

The SQAP may appear as a separate document or as a section within the project

development plan, and may include the configuration management plan (if this

has not been documented separately).

Table 5 contains a list of the main subjects covered in the SQAP. When any of

these subjects is covered elsewhere, such as in the software configuration

management plan (SCMP), it can be omitted from the SQAP and replaced by a

pointer to the document in which it is covered.

However, the SCMP and the SQAP are concerned with different aspects of the

controlled items. The SCMP is primarily concerned with the format of controlled

items while the SQAP is more involved with the contents of controlled items.

The SQAP must cover subcontractors, vendors and suppliers, irrespective of

whether or not these external entities have their own quality assurance

organization.

In any project, the quality of external components is ultimately the concern of the

project manager and the SQA organization. When a system fails, it usually makes

Software Project Management (CS615)

180

© Copyright Virtual University of Pakistan

little difference whether the failure is due to an externally developed component

or an in-house developed component.

The plans for supervising these external groups must be adapted to the type of

external components being provided (off the shelf or new development) and the

type of organization (do they have their own quality assurance organization?).

Software Project Management (CS615)

181

© Copyright Virtual University of Pakistan

Table 5: Example of the contents of a software quality assurance plan

1. Software quality assurance organization and resources

Organizational structure

Personnel skill level and qualifications

Resources

2. SQA standards. Procedures, policies and guidelines

3. SQA documentation requirements

List of all documentation subject to quality control

Description of method of evaluation and approval

4. SQA software requirements

Evaluation and approval of software

Description of method of evaluation

Evaluation of the software development process

Evaluation of reused software

Evaluation of non-deliverable software

5. Evaluation of storage handling and delivery

Project documents

Software

Data files

6. Reviews and audits

7. Software configuration management (when not addressed in a separate document)

8. Problem reporting and corrective action

9. Evaluation of test procedures

10. Tools techniques and methodologies

11. Quality control of subcontractors, vendors and suppliers

12. Additional control

Miscellaneous control procedures

Project specific control

13. SQA reporting, records and documentation.

Status reporting procedures

Maintenance

Storage and security

Retention period

The SQAP, as part of the project development plan, should be reviewed and

updated periodically and whenever any requirements, project development

procedures, methodologies or other relevant activities are changed.

Software Project Management (CS615)

182

© Copyright Virtual University of Pakistan

The IEEE SQAP guide recommends periodic evaluation of two aspects of the

plan:

(1) The plan's content and

(2) The plan's implementation

The plan's content should be evaluated with regard to the specific SQAP standard

used, to assure the plan's continuing compliance with the standard even when the

characteristics of the software project change.

The plan's implementation should be evaluated in terms of the changing scope of

the project, including the tasks and responsibilities referenced in the plan, and

other new or changed characteristics of the project.

When updating the SQAP the following project activities and events should be

considered:

􀂃 New or changed contractual requirements

􀂃 Additional standards and policies

􀂃 Additional project documents

􀂃 Changes in the project's organizational structure

􀂃 New tools and utilities

􀂃 Additional subcontractors and vendors

10. The RMMM Plan

A collection of risk information sheets developed for all risks that lie above the

cut off. A risk management strategy can be included in the software project plan

or the risk management steps can be organized into a separate Risk Mitigation,

Monitoring and Management Plan. The RMMM plan documents all work

performed as part of risk analysis and are used by the project manager as part of

the overall project plan.

Some software teams do not develop a formal RMMM document. Rather, each

risk is documented individually using a risk information sheet (RIS) [WIL97]. In

most cases, the RIS is maintained using a database system, so that creation and

information entry, priority ordering, searches, and other analysis may be

accomplished easily.

Once RMMM has been documented and the project has begun, risk mitigation

and monitoring steps commence.

Software Project Management (CS615)

183

© Copyright Virtual University of Pakistan

As we have already discussed, risk mitigation is a problem avoidance activity.

Risk monitoring is a project tracking activity with three primary objectives:

1. To assess whether predicted risks do, in fact, occur;

2. To ensure that risk aversion steps defined for the risk are being properly

applied; and

3. To collect information that can be used for future risk analysis. In many cases,

the problems that occur during a project can be traced to more than one risk.

Another job of risk monitoring is to attempt to allocate origin (what risk(s)

caused which problems throughout. the project).

11. Project Development Budget

Good estimates are important, as they form the foundations of a good project

development plan. This plan, prepared by the project manager, is produced during

the initial stages of the project and includes estimates related to:

• The project development budget

• The project development schedule

• The required development resources (development staff, development

equipment etc.)

In parallel with integration and testing, the following managerial and activities

take place:

• Final budgeting of the project; the cost of changes is determined, risk

contingency activities are evaluated, and the budget is updated.

• Training is conducted for users, operators, customers, installers, maintenance

engineers, and marketing engineers.

• Installation sites are prepared, and the infrastructure for hardware and special

equipment is planned and installed.

• The development team size is reduced.

12. Maintenance Documents

The phased approach to software development divides the development life cycle

into:

• The development of the software code

• Preparation for integration and test of the system (the next phase)

• The development of the maintenance plan

Apart from the actual code being written (and hopefully being well commented),

some of the other documents that are developed during this phase include:

Software Project Management (CS615)

184

© Copyright Virtual University of Pakistan

• The programmer's notebook, documenting coding decisions, unit tests, and

resolution of implementation problems.

• Maintenance plan and documentation, including all necessary documentation

needed for system maintenance.

• Initial versions of the user documentation, including reference manuals and

operator guides.

At the conclusion of the integration and test phase all documentation must be

complete and ready for delivery, including:

• Maintenance documentation

• Final user documentation

• All updated development documentation

• Test documentation and test reports

Maintenance requires a much smaller team, and a different type of management. In

fact, a single maintenance group can be established to maintain several products, with

common management, configuration control, installation and field engineers, and

maintenance of documentation.

The documents that need to be updated during this phase include:

• Version release documentation

• Problem reports

• All development documentation

• All user documentation

• Maintenance logs and customer service reports

13. The statement of work (SOW)

The statement of work is the basis of the contract between the pro-poser and the

customer, and is often incorporated into the contract. The SOW contains a

detailed list of all work to be performed by the pro-poser for the benefit of the

customer.

It is a narrative description of products or services to be supplied by the project.

For internal projects, the project initiator or sponsor provides the statement of

work based on business needs, or product or service requirements. For external

projects, the statement of work can be received from the customer as part of a bid

document, for example, request for proposal, request for information, request for

bid, or as part of a contract. The SOW indicates a:

• Business need - an organization’s business need, can be based on needed

training, market demand, technological advance, legal requirement, or

governmental standard.

Software Project Management (CS615)

185

© Copyright Virtual University of Pakistan

• Product scope description - documents the product requirements and

characteristics of the product or service that the project will be undertaken to

create. The product requirements will generally have less detail during the

initiation process and more detail during later processes, as the product

characteristics are progressively elaborated. These requirements should also

document the relationship among the products or services being created and

the business need or other stimulus that causes the need. While the form and

substance of the product requirements document will vary, it should always be

detailed enough to support later project planning.

• Strategic plan - all projects support the organization’s strategic goals—the

strategic plan of the performing organization should be considered as a factor

in project selection decisions.

The SOW starts as a general list of required deliverables in the RFP. A more

detailed version t of the SOW is submitted as part of the proposal, and is still

considered only an initial description of the work to be performed. The blinding

version of the SOW is finalized during contract negotiations, or after the detailed

project requirements have been completed.

Table 6 presents an example of an SOW outline for a software project. The list of

items varies considerably, depending on the type of project being developed; for

example not all projects include the delivery of hardware components, and not all

projects require training or installation.

The basic guideline for the preparation of the SOW is that any activity, service or

product required by the customer, and agreed to by the developer, must be

included. This means that there can be no binding work items that were

informally understood or agreed to verbally, which do not appear in the SOW.

The formal SOW must include all and only the work to be performed. This

condition prevents misunderstandings and disagreements later, after the project

begins.

The statement of work (SOW) describes the procurement item in sufficient detail

to allow prospective sellers to determine if they are capable of providing the item.

“Sufficient detail” may vary, based on the nature of the item, the needs of the

buyer, or the expected contract form.

Some application areas recognize different types of SOW. For example, in some

government jurisdictions, the term SOW is reserved for a procurement item that is

a clearly specified product or service, and the term Statement of Objectives (SOO)

is used for a procurement item that is presented as a problem to be solved.

The statement of work may be revised and refined as it moves through the

procurement process. For example, a prospective seller may suggest a more

Software Project Management (CS615)

186

© Copyright Virtual University of Pakistan

efficient approach or a less costly product than that originally specified. Each

individual procurement item requires a separate statement of work. However,

multiple products or services may be grouped as one procurement item with a

single SOW.

Table 6: A sample SOW outline for a software project

1. Referenced documents

• requirements specification

• existing system description

• customer's RFP

• developer's proposal

• vendor's and developer's technical literature

2. Software deliverables

• functionality (as documented in the requirements specification)

• list of major software components

3. Equipment and hardware deliverables

• functionality (as documented in the requirements specification)

• list of major hardware components

4. Training

• user courses

• operator training

• installation training

5. Market research

6. Procurement

7. Supervision of subcontractors

8. Documentation

• development documentation

• user documentation

• maintenance documentation

• other technical documentation

9. Testing

• alpha testing

• beta testing

• acceptance tests (ATP)

10. Installation

11. Maintenance services

12. Other services and deliverable items

13. Method of delivery

Software Project Management (CS615)

187

© Copyright Virtual University of Pakistan

• software

• documentation

• hardware

The statement of work should be as clear, as complete, and as concise as possible.

It should include a description of any collateral services required, such as

performance reporting or post-project operational support for the procured item.

In some application areas, there are specific content and format requirements for a

SOW.

14. Responsibility Assignment Matrix (RAM)

Project roles (who do what) and responsibilities (who decide what) must be

assigned to the appropriate project stakeholders.

Roles and responsibilities may vary over time. Most roles and responsibilities will

be assigned to stakeholders who are actively involved in the work of the project,

such as the project manager, other members of the project management team, and

the individual contributors.

The roles and responsibilities of the project manager are generally critical on most

projects, but vary significantly by application area. Project roles and

responsibilities should be closely linked to the project scope definition.

A Responsibility Assignment Matrix (RAM) is often used for this purpose. On

larger projects, RAM s may be developed at various levels.

For example, a high-level RAM may define which group or unit is responsible for

each component of the work breakdown structure, while lower-level RAM s are

used within the group to assign roles and responsibilities for specific activities to

particular individuals.

A structure that relates the project organization structure to the work breakdown

structure, to help ensure, that each element of the project’s scope of work is

assigned to a responsible individual.

– Shows who does what (x=person, y=phase). The most important feature of the

RAM is the participatory development process involving all stakeholders.

Show who is participant, who is accountable, who handles reviews, who

provides input and who must sign off on specific work packages or project

phases.

15. Project Charter

Software Project Management (CS615)

188

© Copyright Virtual University of Pakistan

A document issued by senior management that formally authorizes the existence

of a project. And it provides the project manager with the authority to apply

organizational resources to project activities.

16. Risk management plan

The risk management plan describes how risk identification, qualitative and

quantitative analysis, response planning, monitoring, and control will be

structured and performed during the project life cycle. The risk management plan

may include the following.

– Methodology. Defines the approaches, tools, and data sources that may be

used to perform risk management on this project. Different types of

assessments may be appropriate, depending upon the project stage, amount of

information available, and flexibility remaining in risk management.

– Roles and responsibilities. Defines the lead, support, and risk management

team membership for each type of action in the risk management plan. Risk

management teams organized outside of the project office may be able to

perform more independent, unbiased risk analyses of project than those from

the sponsoring project team.

– Budgeting. Establishes a budget for risk management for the project.

– Timing. Defines how often the risk management process will be performed

throughout the project life cycle. Results should be developed early enough to

affect decisions. The decisions should be revisited periodically during project

execution.

– Scoring and interpretation. The scoring and interpretation methods

appropriate for the type and timing of the qualitative and quantitative risk

analysis being performed. Methods and scoring must be determined in

advance to ensure consistency.

– Thresholds. The threshold criteria for risks that will be acted upon, by whom,

and in what manner. The project owner, customer, or sponsor may have a

different risk threshold. The acceptable threshold forms the target against

which the project team will measure the effectiveness of the risk response plan

execution.

– Reporting formats. Describes the content and format of the risk response

plan. Defines how the results of the risk management processes will be

documented, analyzed, and communicated to the project team, internal and

external stakeholders, sponsors, and others.

Software Project Management (CS615)

189

© Copyright Virtual University of Pakistan

– Tracking. Documents how all facets of risk activities will be recorded for the

benefit of the current project, future needs, and lessons learned. Documents if

and how risk processes will be audited.

4.10 Scheduling

Any project can be completed, given an infinite amount of time and resources.

Realistically, the amount of time available for project development is always

finite.

In fact, in most cases it is less than the project manager considers sufficient.

Few projects are completed ahead of time; many projects overrun their schedule.

The project schedule is one of the most important parts of the project

development plan.

The plan includes:

– Scheduling of development activities and

– Scheduling of project resources, particularly people

The project development plan describes in detail:

– how the project manager plans to develop the project

– what resources will be required and

– how these resources will be applied

No matter how well the project schedule is prepared, that schedule is useless

unless it is adhered to. It is the project manager's responsibility to withstand

pressure and to assure that the project is developed in an orderly fashion,

according to the schedule. Whenever circumstances change, the project schedule

should then be updated to reflect the new situation.

A schedule is a list of:

– Activities and

– Anticipated time of implementation of these activities

There are many ways of representing a schedule:

– Lists of activities,

– Diagrams,

– Graphs etc.

Software Project Management (CS615)

190

© Copyright Virtual University of Pakistan

The most common methods of schedule representation are :

– precedence network diagrams (such as PERT),

– Gantt charts and

– lists of milestones

4.11 Guidelines for successful Planning

A common failure in many kinds of planning is that the plan is never really

implemented. Instead, all focus is on writing a plan document.

Most of the following guidelines help to ensure that the planning process is

carried out completely and is implemented completely or, deviations from the

intended plan are recognized and managed accordingly.

i. Involve the Right People in the Planning Process

It's critical that all parts of the system continue to exchange feedback in order to

function effectively. This is true no matter what type of system.

When planning, get input from everyone who will be responsible to carry out

parts of the plan, along with representative from groups who will be affected by

the plan.

Of course, people involved should be responsible to review and authorize the

plan.

ii. Write Down the Planning Information and Communicate it Widely

New managers, in particular, often forget that others don't know what these

managers know.

Even if managers do communicate their intentions and plans verbally, chances are

that others won't completely hear or understand what the manager wants done.

Also, as plans change, it's extremely difficult to remember who is supposed to be

doing what and according to which version of the plan.

Key stakeholders (employees, management, board members, sponsors, customers,

clients, etc.) may request copies of various types of plans.

Therefore, it's critical to write plans down and communicate them widely.

iii. Goals and Objectives Should Be SMARTER

• Specific

• Measurable

Software Project Management (CS615)

191

© Copyright Virtual University of Pakistan

• Acceptable

• Realistic

• Time frame

• Extending

• Rewarding

iv. Build in Accountability (Regularly Review Who's Doing What and By

When?)

Plans should specify who is responsible for achieving each result, including goals

and objectives.

Dates should be set for completion of each result, as well.

Responsible parties should regularly review status of the plan.

Be sure to have someone of authority "sign off" on the plan, including putting

their signature on the plan to indicate they agree with and support its contents.

Include responsibilities in policies, procedures, job descriptions, performance

review processes, etc.

v. Note Deviations from the Plan and Re-plan Accordingly

It's OK to deviate from the plan. The plan is not a set of rules. It's an overall

guideline. It is equally important to notice deviations and adjust the plan

accordingly.

vi. Evaluate Planning Process and the Plan

During the planning process, regularly collect feedback from participants. Do they

agree with the planning process? If not, what don't they like and how could it be

done better?

In large, ongoing planning processes (such as strategic planning, business

planning, project planning, etc.), it's critical to collect this kind of feedback

regularly.

During regular reviews of implementation of the plan, assess if goals are being

achieved or not. If not, were goals realistic? Do responsible parties have the

resources necessary to achieve the goals and objectives?

Should goals be changed? Should more priority be placed on achieving the goals?

What needs to be done?

Write down how the planning process could have been done better. File it away

and read it the next time you conduct the planning process.

Software Project Management (CS615)

192

© Copyright Virtual University of Pakistan

vii. Recurring Planning Process is at Least as Important as Plan Document

Far too often, primary emphasis is placed on the plan document.

This is extremely unfortunate because the real treasure of planning is the planning

process itself.

During planning, planners learn a great deal from ongoing analysis, reflection,

discussion, debates and dialogue around issues and goals in the system.

The ongoing communications are what sensitize people to understanding and

following the values and behaviors described

viii. Nature of the Process Should Be Compatible to Nature of Planners

A prominent example of this type of potential problem is when planners don't

prefer the "top down" or "bottom up", "linear" type of planning

For example, going from general to specific along the process of an

environmental scan, SWOT analysis, mission/vision/values, issues and goals,

strategies, objectives, timelines, etc.

Software Project Management (CS615)

193

© Copyright Virtual University of Pakistan

LECTURE # 27

5. ORGANIZATION

5.1 Basic Definition

Basically, an organization is a group of people intentionally organized to

accomplish an overall, common goal or set of goals. Business organizations can

range in size from two people to tens of thousands.

How you interpret each of the above major parts of an organization depends very

much on your values and your nature. People can view organizations as machines,

organisms, families, groups, etc.

People are managed through an organizational structure. This hierarchical

structure is based on the four cornerstones of management:

– Delegation

– Authority

– Responsibility

– Supervision.

Delegation bestows authority, and authority produces (and requires)

responsibility. Both authority and responsibility require supervision, and effective

supervision requires a suitable organizational structure:

Most projects are organized as teams, with each team assigned specific functions

within the project.

Different types of project require different types of team structure, as for example

a team of junior programmers requires a technical team leader while a team of

experts may require only an administrative team leader.

It is the project manager's responsibility to select the structure best suited for the

project.

Basically an organization is a group of people intentionally organized to

accomplish an overall, common goal or set of goals. Business organizations can

range in size from two people to tens of thousands.

How you interpret each of the above major parts of an organization depends very

much on your values and your nature. People can view organizations as machines,

organisms, families, groups, etc.

Software Project Management (CS615)

194

© Copyright Virtual University of Pakistan

5.2 Organization as a System

It helps to think of organizations are systems.

Simply put, a system is an organized collection of parts that are highly integrated

in order to accomplish an overall goal.

The system has various inputs which are processed to produce certain outputs,

which together, accomplish the overall goal desired by the organization.

There is ongoing feedback among these various parts to ensure they remain

aligned to accomplish the overall goal of the organization. There are several

classes of systems, ranging from very simple frameworks all the way to social

systems, which are the most complex. Organizations are, of course, social

systems.

Systems have inputs, processes, outputs and outcomes. To explain, inputs to the

system include resources such as raw materials, money, technologies and people.

These inputs go through a process where they're aligned, moved along and

carefully coordinated, ultimately to achieve the goals set for the system. Outputs

are tangible results produced by processes in the system, such as products or

services for consumers.

Another kind of result is outcomes, or benefits for consumers, e.g., jobs for

workers, enhanced quality of life for customers, etc. Systems can be the entire

organization, or its departments, groups, processes, etc.

Feedback comes from, e.g., employees who carry out processes in the

organization, customers/clients using the products and services, etc.

Feedback also comes from the larger environment of the organization, e.g.,

influences from government, society, economics, and technologies.

Each organization has numerous subsystems, as well. Each subsystem has its own

boundaries of sorts, and includes various inputs, processes, outputs and outcomes

geared to accomplish an overall goal for the subsystem.

Common examples of subsystems are departments, programs, projects, teams and

processes to produce products or services, etc.

Organizations are made up of people - who are also systems of systems of

systems - and on it goes. Subsystems are organized in a hierarchy needed to

accomplish the overall goal of the overall system.

Software Project Management (CS615)

195

© Copyright Virtual University of Pakistan

The organizational system is defined by, e.g., its legal documents (articles of

incorporation, by laws, roles of officers, etc.), mission, goals and strategies,

policies and procedures, operating manuals, etc.

The organization is depicted by its organizational charts, job descriptions,

marketing materials, etc.

The organizational system is also maintained or controlled by policies and

procedures, budgets, information management systems, quality management

systems, performance review systems, etc.

5.3 Structural Dimensions

The organization's structure, or design, is the overall arrangement of the

organization's various roles, processes and their relationships in the organization.

The design of an organization is a means to accomplishing the organization's

overall goal - the structure is not an end in itself.

In systems theory terms, the design ensures that the appropriate inputs go through

the necessary processes to produce the required outputs to produce the intended

outcomes.

􀂃 Centralization -the extent to which functions are dispersed in the

organization, either in terms of integration with other functions or

geographically

􀂃 Formalization - regarding the extent of policies and procedures in the

organization

􀂃 Hierarchy - regarding the extent and configuration of levels in the

structure

􀂃 Routinization - regarding the extent that organizational processes are

standardized

􀂃 Specialization - regarding the extent to which activities are refined

􀂃 Training - regarding the extent of activities to equip organization

members with knowledge and skills to carry out their roles.

5.4 Organizational Systems

Project-based organizations are those whose operations consist primarily of

projects. These organizations fall into two categories:

– Organizations that derive their revenue primarily from performing projects for

others—architectural firms, engineering firms, consultants, construction contractors,

government contractors, nongovernmental organizations, etc

– Organizations that have adopted management by projects, these organizations

Software Project Management (CS615)

196

© Copyright Virtual University of Pakistan

tend to have management systems in place to facilitate project management.

For example, their financial systems are often specifically designed for

accounting, tracking, and reporting on multiple simultaneous projects.

Non project-based organizations often lack management systems designed to

support project needs efficiently and effectively.

The absence of project-oriented systems usually makes project management more

difficult.

In some cases, non project-based organizations will have departments or other

subunits that operate as project-based organizations with systems to match.

The project management team should be acutely aware of how the organization’s

systems affect the project.

For example, if the organization rewards its functional managers for charging

staff time to projects, then the project management team may need to implement

controls to ensure that assigned staff members are being used effectively on the

project.

5.5 Organizational Cultures and Styles

Most organizations have developed unique and describable cultures. These

cultures are reflected in their:

– Shared values,

– Norms,

– Beliefs

– Expectations

– Policies and

– Procedures

– View of authority relationships and numerous other factors

Organizational cultures often have a direct influence on the project.

– A team proposing an unusual or high-risk approach is more likely to secure

approval in an aggressive or entrepreneurial organization.

– A project manager with a highly participative style is apt to encounter

problems in a rigidly hierarchical organization, while a project manager with

an authoritarian style will be equally challenged in a participative

organization.

The structure of the performing organization often constrains the availability of or

terms under which resources become available to the project.

Software Project Management (CS615)

197

© Copyright Virtual University of Pakistan

Organizational structures can be characterized as spanning a spectrum from

functional to projectized, with a variety of matrix structures in between.

The following table shows key project related characteristics of the major types of

enterprise organizational structures:

Table: Organizational Structure Influences on Projects

Matrix

Project

Characteristics

Organization

Structure

Functional

Weak Balanced Strong

Projectized

Project Manager’s Authority

Little or non

Limited

Low to

Moderate

Moderate

to High

High to

almost Total

Percent of Performing

Organization’s Personnel assigned

Full time to Project work

Virtually

None

0-25%

15-60%

50-95%

85-100%

Project Manager’s Role

Part-time

Part time

Full-time

Full-time

Full-time

Common Titles for Project

Manager’s Role

Project

Coordinator/

Project

Leader

Project

Coordinato

r/ Project

Leader

Project

Manager/Pr

oject

Officer

Project

Manager/

Program

Manager

Project

Manager/

Program

Manager

Project Management

Administrative Staff

Part-time

Part time

Part-time

Full-time

Full-time

5.6 Traditional Structures of Business Organization

i. Functional Structure

Most business organizations start out with a functional structure, or a small

variation of this structure. This is the basic "building block" for other structures.

In this structure, there is a central office which oversees various departments or

major functions, e.g., human resources, finances, sales, marketing, engineering,

etc.

Think of a picture that has a box at the top labeled "Central Office". Think of a

row of boxes underneath the top box. Each box is labeled, e.g., sales, engineering,

human resources, etc.

Software Project Management (CS615)

198

© Copyright Virtual University of Pakistan

Connect the boxes with lines coming down from the top box to each of the boxes

below. Use functional structures when the organization is small, geographically

centralized, and provides few goods and services.

When the organization experiences bottlenecks in decision making and

difficulties in coordination, it has outgrown its functional structure.

The classic functional organization is a hierarchy where each employee has one

clear superior. Staff members are grouped by specialty, such as production,

marketing, engineering, and accounting at the top level, with engineering further

subdivided into functional organizations that support the business of the larger

organization (e.g., mechanical and electrical).

Functional organizations still have projects, but the perceived scope of the project

is limited to the boundaries of the function: the engineering department in a

functional organization will do its work independent of the manufacturing or

marketing departments.

For example, when a new product development is undertaken in a purely

functional organization, the design phase is often called a design project and

includes only engineering department staff. If questions about manufacturing

arise, they are passed up the hierarchy to the department head, who consults with

the head of the manufacturing department. The engineering department head then

passes the answer back down the hierarchy to the engineering project manager.

ii. Projectized Structure

In this structure, there is a centralized corporate office and under it, are various

divisions each of which is dedicated to producing and / or selling a certain type of

business or product, e.g., product 1, product 2, etc.

Each division that is dedicated to a certain business or product is, in turn, is

organized as its own functional structure.

So, for example, the division dedicated to making product 1 has its own sales

department, human resources, etc. Basically, project structure is a bunch of

functional structures each of which reports to one central office.

Use a divisional structure when the organization is relatively large, geographically

dispersed, and/or produces wide range of goods/services.

In a projectized organization, team members are often collocated. Most of the

organization’s resources are involved in project work, and project managers have

a great deal of independence and authority.

Software Project Management (CS615)

199

© Copyright Virtual University of Pakistan

Projectized organizations often have organizational units called departments, but

these groups either report directly to the project manager or provide support

services to the various projects.

iii. Matrix Structure

Think of the functional structure. Imagine if you took someone from each of the

major functions in the functional structure (the boxes along the bottom of the

organization chart), e.g., people from sales, engineering, etc., and organized them

into a separate group intended to produce and sell one certain kind of product or

service.

Members of this group stay together until that product is produced or they

continue to sell and service it. This overall structure (made up of a functional

structure that also has groups assigned to products) is a matrix structure.

This structure is useful because it focuses highly skilled people from across the

organization to work on a complex product or service.

It can be difficult, though, because each person essentially reports to two

supervisors: the supervisor of the functional area (e.g., engineering) and the

product manager, as well.

When the organization needs constant coordination of its functional activities,

then lateral relations do not provide sufficient integration. Consider the matrix

structure.

To adopt the matrix structure effectively, the organization should modify many

traditional management practices.

Matrix organizations are a blend of functional and projectized characteristics.

Weak matrices maintain many of the characteristics of a functional organization,

and the project manager role is more that of a coordinator or expediter than that of

a manager.

In similar fashion, strong matrices have many of the characteristics of the

projectized organization—full-time project managers with considerable authority

and full-time project administrative staff.

Software Project Management (CS615)

200

© Copyright Virtual University of Pakistan

Figure 1: Weak Matrix Organization

Figure 2: Balanced Matrix Organization

Chief

Executive

Functional

Manager

Functional

Manager

Functional

Manager

Staff

Staff

Project

Manager

Staff

Staff

Staff

Staff

Staff

Staff

Chief

Executive

Functional

Manager

Functional

Manager

Functional

Manager

Staff

Staff

Staff

Staff

Staff

Staff

Staff

Staff

Staff

Project

Coordinatio

Project

Coordinatio

Software Project Management (CS615)

201

© Copyright Virtual University of Pakistan

Figure 3: Strong Matrix Organization

(Black boxes represent staff engaged in project activites)

iv. Project Office

There is a range of uses for what constitutes a project office. A project office may

operate on a continuum from providing support functions to project managers in

the form of training, software, templates, etc. to actually being responsible for the

results of the project.

Most modern organizations involve all these structures at various levels. For

example, even a fundamentally functional organization may create a special

project team to handle a critical project.

Such a team may have many of the characteristics of a project in a projectized

organization.

The team may include full-time staff from different functional departments, it

may develop its own set of operating procedures, and it may operate outside the

standard, formalized reporting structure.

Chief

Executive

Functional

Manager

Functional

Manager

Manager of

Project Managers

Staff

Staff

Staff

Staff

Staff

Staff

Project

Manager

Project

Manager

Project

Manager

Project

Coordinatio

Software Project Management (CS615)

202

© Copyright Virtual University of Pakistan

LECTURE # 28

5. ORGANIZATION

5.7 ORGANIZATIONAL PLANNING

Organizational planning involves identifying, documenting, and assigning

project roles, responsibilities, and reporting relationships.

Roles, responsibilities, and reporting relationships may be assigned to

individuals or to groups. The individuals and groups may be part of the

organization performing the project, or they may be external to it. Internal

groups are often associated with a specific functional department such as

engineering, marketing, or accounting.

On most projects, the majority of organizational planning is done as part

of the earliest project phases.

However, the results of this process should be reviewed regularly

throughout the project to ensure continued applicability. If the initial

organization is no longer effective, then it should be revised promptly.

Organizational planning is often tightly linked with communications

planning since the project’s organizational structure will have a major

effect on the project’s communications requirements.

5.7.1 Inputs to Organizational Planning

i. Project interfaces. Project interfaces generally fall into one of three categories:

– Organizational interfaces—formal and informal reporting relationships

among different organizational units. Organizational interfaces may be

highly complex or very simple. For example, developing a complex

telecommunications system may require coordinating numerous

subcontractors over several years, while fixing a programming error in a

system installed at a single site may require little more than notifying the

user and the operations staff upon completion.

– Technical interfaces—formal and informal reporting relationships among

different technical disciplines. Technical interfaces occur both within

project phases (e.g., the site design developed by the civil engineers must

be compatible with the superstructure developed by the structural

Software Project Management (CS615)

203

© Copyright Virtual University of Pakistan

engineers) and between project phases (e.g., when an automotive design

team passes the results of its work along to the retooling team that must

create the manufacturing capability for the vehicle).

– Interpersonal interfaces—formal and informal reporting relationships

among different individuals working on the project. These interfaces often

occur simultaneously, as when an architect employed by a design firm

explains key design considerations to an unrelated construction

contractor’s project management team.

ii. Staffing requirements. Staffing requirements define what kinds of competencies

are required from what kinds of individuals or groups and in what time frames.

Staffing requirements are a subset of the overall resource requirements identified

during resource planning.

iii. Constraints. Constraints are factors that limit the project team’s options. A

project’s organizational options may be constrained in many ways. Common

factors that may constrain how the team is organized include, but are not limited

to, the following:

– Organizational structure of the performing organization—an

organization whose basic structure is a strong matrix means a relatively

stronger role for the project manager than one whose basic structure is a

weak matrix.

– Collective bargaining agreements—contractual agreements with unions

or other employee groups may require certain roles or reporting

relationships (in essence, the employee group is a stakeholder).

– Preferences of the project management team—if members of the project

management team have had success with certain structures in the past,

then they are likely to advocate similar structures in the future.

– Expected staff assignment —how the project is organized is often

influenced by the competencies of specific individuals.

5.7.2 Tools and Techniques for Organizational Planning

i. Templates. Although each project is unique, most projects will resemble another

project to some extent. Using the role and responsibility definitions or reporting

relationships of a similar project can help expedite the process of organizational

planning.

ii. Human resource practices. Many organizations have a variety of policies,

guidelines, and procedures that can help the project management team with

various aspects of organizational planning. For example, an organization that

views managers as “coaches” is likely to have documentation on how the role of

“coach” is to be performed.

Software Project Management (CS615)

204

© Copyright Virtual University of Pakistan

iii. Organizational theory. There is a substantial body of literature describing how

organizations can and should be structured. Although only a small subset of this

body of literature is specifically targeted toward project organizations, the project

management team should be generally familiar with the subject of organizational

theory so as to be better able to respond to project requirements.

iv. Stakeholder analysis. The identification of stakeholders and the needs of the

various stakeholders should be analyzed to ensure that their needs will be met.

5.7.3 Outputs from Organizational Planning

i. Role and responsibility assignments. Project roles (who does what) and

responsibilities (who decides what) must be assigned to the appropriate project

stakeholders. Roles and responsibilities may vary over time. Most roles and

responsibilities will be assigned to stakeholders who are actively involved in the

work of the project, such as the project manager, other members of the project

management team, and the individual contributors. The roles and responsibilities

of the project manager are generally critical on most projects, but vary

significantly by application area. Project roles and responsibilities should be

closely linked to the project scope definition. A Responsibility Assignment

Matrix is often used for this purpose. On larger projects, RAM s may be

developed at various levels. For example, a high-level RAM may define which

group or unit is responsible for each component of the work breakdown structure,

while lower-level RAM s are used within the group to assign roles and

responsibilities for specific activities to particular individuals.

ii. Staffing management plan. The staffing management plan describes when and

how human resources will be brought onto and taken off of the project team. The

staffing plan may be formal or informal, highly detailed or broadly framed, based

on the needs of the project. It is a subsidiary element of the overall project plan.

The staffing management plan often includes resource histograms. Particular

attention should be paid to how project team members (individuals or groups) will

be released when they are no longer needed on the project. Appropriate

reassignment procedures may:

– Reduce costs by reducing or eliminating the tendency to “make work” to

fill the time between this assignment and the next.

– Improve morale by reducing or eliminating uncertainty about future

employment opportunities.

iii. Organization chart. An organization chart is any graphic display of project

reporting relationships. It may be formal or informal, highly detailed or broadly

framed, based on the needs of the project. For example, the organization chart for

a three- to four-person internal service project is unlikely to have the rigor and

detail of the organization chart for a 3,000-person disaster response team. An

Software Project Management (CS615)

205

© Copyright Virtual University of Pakistan

Organizational Breakdown Structure (OBS) is a specific type of organization

chart that shows which organizational units are responsible for which work

packages.

iv. Supporting detail. Supporting detail for organizational planning varies by

application area and project size. Information frequently supplied as supporting

detail includes, but is not limited to: Organizational impact—what alternatives are

precluded by organizing in this manner.

– Job descriptions—written outlines by job title of the competencies,

responsibilities, authority, physical environment, and other characteristics

involved in performing a given job. Also called position descriptions.

– Training needs—if the staff to be assigned is not expected to have the

competencies needed by the project, those competencies will need to be

developed as part of the project.

5.8 STAFF ACQUISITION

Staff acquisition involves getting the needed human resources (individuals or

groups) assigned to and working on the project. In most environments, the “best”

resources may not be available, and the project management team must take care

to ensure that the resources that are available will meet project requirements.

5.8.1 Inputs to Staff Acquisition

i. Staffing management plan. It includes the project’s staffing requirement

ii. Staffing pool description. When the project management team is able to influence

or direct staff assignments, it must consider the characteristics of the potentially

available staff. Considerations include, but are not limited to:

– Previous experience—have the individuals or groups done similar or related

work before? Have they done it well?

– Personal interests—are the individuals or groups interested in working on this

project?

– Personal characteristics—are the individuals or groups likely to work well

together as a team?

– Availability—will the most desirable individuals or groups be available in the

necessary time frames?

– Competencies and proficiency—what competencies are required and at what

level?

iii. Recruitment practices. One or more of the organizations involved in the project

may have policies, guidelines, or procedures governing staff assignments. When

they exist, such practices act as a constraint on the staff-acquisition process.

Software Project Management (CS615)

206

© Copyright Virtual University of Pakistan

5.8.2 Tools and Techniques for Staff Acquisition

i. Negotiations. Staff assignments must be negotiated on most projects. For

example, the project management team may need to negotiate with:

– Responsible functional managers to ensure that the project receives

appropriately competent staff in the necessary time frame.

– Other project management teams within the performing organization to

assign scarce or specialized resources appropriately.

The team’s influencing competencies play an important role in negotiating staff

assignments, as do the politics of the organizations involved. For example, a

functional manager may be rewarded based on staff utilization. This creates an

incentive for the manager to assign available staff who may not meet all of the

project’s requirements.

ii. Pre-assignment. In some cases, staff may be pre-assigned to the project. This is

often the case when a) the project is the result of a competitive proposal, and

specific staff was promised as part of the proposal, or b) the project is an internal

service project, and staff assignments were defined within the project charter.

iii. Procurement. Project procurement management can be used to obtain the

services of specific individuals or groups of individuals to perform project

activities. Procurement is required when the performing organization lacks the inhouse

staff needed to complete the project (e.g., as a result of a conscious decision

not to hire such individuals as full-time employees, as a result of having all

appropriately competent staff previously committed to other projects, or as a

result of other circumstances).

5.8.3 Outputs from Staff Acquisition

i. Project staff assigned. The project is staffed when appropriate people have been

reliably assigned to work on it. Staff may be assigned full time, part time, or

variably, based on the needs of the project.

ii. Project team directory. A project team directory lists all the project team

members and other stakeholders. The directory may be formal or informal, highly

detailed or broadly framed, based on the needs of the project.

5.9 TEAM DEVELOPMENT

Team development includes both enhancing the ability of stakeholders to

contribute as individuals as well as enhancing the ability of the team to function

as a team. Individual development (managerial and technical) is the foundation

necessary to develop the team. Development as a team is critical to the project’s

ability to meet its objectives.

Software Project Management (CS615)

207

© Copyright Virtual University of Pakistan

Team development on a project is often complicated when individual team

members are accountable to both a functional manager and the project manager.

Effective management of this dual reporting relationship is often a critical success

factor for the project, and is generally the responsibility of the project manager.

Team development occurs throughout the project.

5.9.1 Inputs to Team Development

i. Project staff. The staff assignments implicitly define the individual competencies

and team competencies available upon which to build.

ii. Project plan. The project plan describes the technical context within which the

team operates.

iii. Staffing management plan.

iv. Performance reports. Performance reports provide feedback to the project team

about performance against the project plan.

v. External feedback. The project team must periodically measure itself against the

expectations of those outside the project.

5.9.2 Tools and Techniques for Team Development

i. Team-building activities. Team-building activities include management and

individual actions taken specifically and primarily to improve team performance.

Many actions—such as involving non-management-level team members in the

planning process, or establishing ground rules for surfacing and dealing with

conflict— may enhance team performance as a secondary effect. Team-building

activities can vary from a five-minute agenda item in a regular status review

meeting to an extended, off-site, professionally facilitated experience designed to

improve interpersonal relationships among key stakeholders. There is a

substantial body of literature on team building. The project management team

should be generally familiar with a variety of team-building activities.

ii. General management skills. General management skills are of particular

importance to team development.

iii. Reward and recognition systems. Reward and recognition systems are formal

management actions that promote or reinforce desired behavior. To be effective,

such systems must make the link between project performance and reward clear,

explicit, and achievable. For example, a project manager who is to be rewarded

for meeting the project’s cost objective should have an appropriate level of

control over staffing and procurement decisions. Projects must often have their

own reward and recognition systems since the systems of the performing

Software Project Management (CS615)

208

© Copyright Virtual University of Pakistan

organization may not be appropriate. For example, the willingness to work

overtime to meet an aggressive schedule objective should be rewarded or

recognized; needing to work overtime as the result of poor planning should not

be. Reward and recognition systems must also consider cultural differences. For

example, developing an appropriate team reward mechanism in a culture that

prizes individualism may be very difficult.

iv. Co-location. Collocation involves placing all, or almost all, of the most active

project team members in the same physical location to enhance their ability to

perform as a team. Collocation is widely used on larger projects and can also be

effective for smaller projects (e.g., with a war room, where the team congregates

and posts schedules, updates, etc.). On some projects, collocation may not be an

option; where it is not viable, an alternative may be scheduling frequent face to

face meetings to encourage interaction.

v. Training. Training includes all activities designed to enhance the competencies

of the project team. Some authors distinguish among training, education, and

development, but the distinctions are neither consistent nor widely accepted.

Training may be formal (e.g., classroom training, computer-based training) or

informal (e.g., feedback from other team members). There is a substantial body of

literature on how to provide training to adults. If the project team members lack

necessary management or technical skills, such skills must be developed as part of

the project, or steps must be taken to re-staff the project appropriately. Direct and

indirect costs for training are generally paid by the performing organization.

5.9.3 Outputs from Team Development

i. Performance improvements. Team performance improvements can come from

many sources and can affect many areas of project performance; for example:

– Improvements in individual skills may allow a specific person to perform

assigned activities more effectively.

– Improvements in team behaviors (e.g., surfacing and dealing with conflict)

may allow project team members to devote a greater percentage of their

efforts to technical activities.

– Improvements in either individual or team competencies may facilitate

identifying and developing better ways of doing project work.

ii. Input to performance appraisals. Project staff should generally provide input to

the appraisals of any project staff members with whom they interact in a

significant way.

5.10 Organizational Management Tools

i. Management Development

– Responsibility

Software Project Management (CS615)

209

© Copyright Virtual University of Pakistan

– Authority

– Competence

– Resource Distribution

– Pre-requisites

– Constraints

– Calendar

ii. Supervisory Training

– Field/on site operations

– Concept clearance

– Procedural details

– Resource management

– Activity Scheduling

iii. Team Building

– Managers

– Professionals

– Technical support group

– Logistical support group

– Skill set evaluation

iv. Vital Statistics

– Historical facts

– Technical data

– Direct concerns

– Lesson learned

– Identification of missing links

– Reliability of data

– Relevance of data

v. Progress reporting

– Mandatory periodic reports

– Exception reports

– Event reporting

– Current status reporting

– Reporting formats

– Reporting frequency

– Report recipient

– Reporting officer

– Reporting Media

– Response analysis (of previous reporting)

– Review of Reports

– Signing of Reports

– Tracking of Reports

– Mitigations offered

– Corresponding the dead lines

Software Project Management (CS615)

210

© Copyright Virtual University of Pakistan

vi. Compliance of Rule of Business

– Financial

– Procedural

– Administrative

– Justifications for deviations

– Acceptance of derailments

vii. Trade Offs

– Trade off between DO or DON’T

– Quality of job (in the light of constraints)

– Limiting the scope/deliverables

– Meeting targets with minimum standards

– Unavoidable mandatory deliverables

viii. Quality Assurance

– Standard QA procedures

– Self defined measures

– Task-specific controls

ix. Beneficiaries Concern

– Acceptance

– Enthusiasm

– Adding comforts in terms of use, cost or time

– Confidence building-The Reliability

5.11 Contractual Obligations

A contract is a mutually binding agreement that obligates the seller to provide the

specified product and obligates the buyer to pay for it.

A contract is a legal relationship subject to remedy in the courts. The agreement

may be simple or complex, usually (but not always) reflecting the simplicity or

complexity of the product.

Contracts may be called, among other names, a contract, an agreement, a

subcontract, a purchase order, or a memorandum of understanding. Most

organizations have documented policies and procedures specifically defining who

can sign such agreements on behalf of the organization, typically called a

delegation of procurement authority.

Although all project documents are subject to some form of review and approval,

the legally binding nature of a contract usually means that it will be subjected to a

more extensive approval process. In all cases, a primary focus of the review and

approval process should be to ensure that the contract language describes a

product or service that will satisfy the identified need. In the case of major

Software Project Management (CS615)

211

© Copyright Virtual University of Pakistan

projects undertaken by public agencies, the review process may even include

public review of the agreement.

• Types of Contracts

Owing to the rapid advances in technology during the last several decades, it has

become increasingly necessary for high technology organizations to specialize in

specific, well-defined areas. Specialization has not only defined many new

branches of engineering, it has also defined areas of expertise within the

engineering disciplines. This is especially true of software engineering.

Frequently, organizations that do not specialize in software development hire

other organizations that do so to develop software for them. Even organizations

that do develop their own software may decide to hire outside specialists in

specific areas. IBM hired Microsoft to develop the PC-DOS operating system,

because Microsoft had experience in developing microcomputer systems and IBM

had not.

The development of software is much less deterministic and more risky than other

areas of technology. This often leads to misunderstandings and disagreements that

could have been avoided if they had been anticipated and contained early enough.

To standardize our terminology, the organization to whom, a proposal is being

submitted will be referred to as the customer, and the organization submitting the

proposal will be referred to as the pro-poser. Other terms commonly used

elsewhere for the pro-poser include bidder, vendor or contractor and for the

customer requestor or issuer. The organization submitting the winning proposal,

after being selected, will be referred to as the developer.

a) The cost-plus contract

Cost-plus is a contractual relationship where the developer is paid for the cost of

the service provided and in addition is allowed an agreed profit margin.

This is rather like renting a car the customer pays for the time that the car is used

(by the hour, day, week etc.), and for any other expenses such as insurance and

gasoline. Thus, in a cost-plus contract the total cost of the projects is only known

after the project has been completed.

As an example, company Alpha may contract software company Beta to develop

a system, company Beta will be paid $80 by company Alpha for each hour

invested by their engineers in the project. In additional 20 percent may then be

added to cover managerial, secretarial and other services. Additional expenses

incurred by company Beta for the benefit of the project would then be reimbursed

by company Alpha. These expenses might cover such areas as:

Software Project Management (CS615)

212

© Copyright Virtual University of Pakistan

• Special purpose development equipment (computers, compilers, networks

etc.)

• Travel expenses incurred by employees of company Beta for the benefit of

the project

• Target equipment procured by company Beta for the use of company

Alpha

• Services from other outside sources requested by company Beta for the

project

The customer company, Alpha, may require the developer, company Beta, to

receive prior authorization before incurring any single expense exceeding $250,

and any expense in excess of $6000 monthly total. Such authorization should

always be in writing. This defines a basic cost-plus contractual relationship

between the two companies.

In many cases, cost-plus can be the most appropriate way to contract development

work however, there are numerous potential problems. A conflict of interest may

arise due to the developer's lack of motivation to complete the project as quickly

as possible, or due to the customer's reluctance to authorize additional expenses.

Cost-plus is often appropriate for small undefined projects, when it is difficult to

identify the project's requirements in advance. In fact, in many cases the

requirements phase of a project is offered as a cost-plus contract, all the remaining

phases are contracted at a fixed price.

The requirements phase is then used to bring the rest of the project to a

sufficiently well-defined state from which it can then be contracted at a fixed

price. Occasionally, one company is awarded a cost-plus contract for the

requirements phase, and another company is awarded the remaining phases as a

fixed price contract.

Cost-plus may be preferred by the customer who wants to retain control of the

development process. In some cases, the developer is perceived as an extension of

the customer's organization, and the development activities are managed by the

customer. A cost-plus contract should cover the following issues:

• List of persons to be assigned to the project

• Work definition

• The assignment percentage for each person

• Hourly or daily work rate for each person

• Administrative overhead

• Authorized expenses to be reimbursed

• Billing procedure

• Payment procedure

• Termination procedure

Software Project Management (CS615)

213

© Copyright Virtual University of Pakistan

The assignment percentage refers to the amount of time each person will be

expected to devote to the project. This may be 100 percent for some engineers,

and 50-60 percent for experts in specific areas.

The assignment percentage may also be quoted in terms of maximum or

minimum, meaning that, for example, a quality assurance engineer will devote no

more than 20 hours a week to the project, and no fewer than 10 hours a week to

the project.

The billing rate may be a fixed rate for all persons assigned to the project, or

individual rates may be set for each person or class of people.

For example, for each hour worked on the project, the developer will bill $80,

irrespective of who, worked that hour. Or the contract may stipulate that design

engineers bill at $120 per hour, coders at $60 per hour, documentation writers at

$50 per hour, and so forth. The most difficult cost-plus contract billing rate

method is the individual billing method, where Frank Jones is billed at $90 per

hour, John Smith at $75 etc. This means that each time a person is replaced or

added to the project, the hourly rate must renegotiated.

For a software development organization, there can be real advantages in costplus

contracts these include:

• No financial or business risk

• Acquisition of knowledge and experience at the expense of another

organization

However, as in most cases, these advantages come with some disadvantages,

which include:

• Low business profit

• Possible staff discontent

• Reduced control of staff and development work

• Potential friction with the customer due to a lack of well-defined goals and

motivation factors

• Contract continuity is not assured

Most employees prefer a clear definition of the hierarchy to which they belong. In

a cost-plus contract the employee works within the customer's hierarchy, but

belongs to the developer's hierarchy, and this can cause discontent.

In general, from the developer's perspective, a cost-plus contract is a solid, low

profit, no risk business relationship.

From the customer's perspective, the advantages of a cost-plus contract are:

Software Project Management (CS615)

214

© Copyright Virtual University of Pakistan

• Retention of control over development

• No commitment needed for a full project contract

• A possible reduced business risk (due to the ability to terminate the

contract at any time

The customer's possible disadvantages are:

• Increased development costs

• Customer's assumption of development risks

• Increased involvement in development

• Potential friction with the developer due to a lack of well-defined goals

and motivation factors

For the customer, the desirability of a cost-plus contract is difficult to establish.

Clearly is dependent on the type of project and the conditions under which it will

be developed, as we as on other non-technical business considerations.

b) The fixed price contract

A fixed price contract is a commitment by the developer to provide an agreed

product or service for an agreed fee, within an agreed schedule.

This is similar to purchasing a bus ticket, when the bus company agrees to take

the customer to a specific destination within a published timetable, and for an

agreed fee. Of course, travelers can elect to rent a car, instead of purchasing a bus

ticket, and then drive to their destinations themselves. However, this may turn out

to be more expensive, and requires of the traveler some prior skills and

knowledge, such driving skills and knowledge of the route to the destination. So

travelers (or customers) must decide between providing the service themselves

and contracting someone else to provide the service.

A fixed price contract can only be applied to a well-defined project. Both

customer and developer must be able to define the final deliverable product or

service. Once this has been achieved, one of the main weaknesses of the fixed

price contract will have been removed. The advantages of a fixed price contract

for the developer include:

• Full control of the development process

• Possible higher business profit

• Commitment for a complete project

The commitment for a complete project is a significant advantage over cost-plus

contract that may end at any time, at the customer's discretion. Of course, fixed

price contracts also have some disadvantages for the developer, which include:

Software Project Management (CS615)

215

© Copyright Virtual University of Pakistan

• Assumption of business and development risks

• Potential friction with the customer due to:

− continuing requirement changes

− project completion criteria

− interpretation of requirements

A successful software organization will often prefer a fixed price contract. These

are usually the projects that build a company's professional reputation, and

generate profit to enable growth.

Unfortunately, these are also the projects that generate loss, and which often

severely harm a company. Stiff competition for an important contract

occasionally tempts a company to underbid, which ultimately generates losses for

the developer.

It is almost inevitable in any project that the developer will be requested to change

requirements during development. Such changes are usually associated with

additional cost the customer, and are invariably a cause of disagreement between

developer and customer.

This is often due to unclear or ambiguous requirements, which, in turn lead to

disagreement regarding the criteria for project completion. This, essentially,

returns the contract to insufficiently defined state.

From the customer's perspective, the advantages in a fixed price contract include:

• A fixed budget for the project.

• Most of the development risks are transferred to the developer

• Minimal involvement in the development process

The disadvantages to the customer are:

• Risk of late delivery by the developer

• Reduced control of the development process

• Potential friction with the developer due to:

− high cost of requirement changes

− unclear project completion criteria

− interpretation of requirements

Even though the interests of the developer and the customer may be different,

fixed price contracts are still often preferred by both parties. If the project is

sufficiently detailed and clear and if the relationship between the two parties is

Software Project Management (CS615)

216

© Copyright Virtual University of Pakistan

well defined, then fixed price contracts can be beneficial to both the developer

and the customer.

• The Cost-Plus Vs Fixed Price

There is often a real or imagined conflict of interest between the developer and

the customer. The customer wants to spend less and the developer wants to earn

more. As we shall see, a good relationship between developer and customer need

not necessarily lead to this conflict of interest.

There are basically two types of contractual relationship between the customer

and the Developer:

− Cost-plus (also called Time and material)

− Fixed price

Most other relationships are some kind of combination of these two

• Contract type selection:

Different types of contracts are more or less appropriate for different types of

purchases. Contracts generally fall into one of three broad categories:

􀂃 Fixed-price or lump-sum contracts—this category of contract involves a

fixed total price for a well-defined product. To the extent that the product is

not well defined, both the buyer and seller are at risk—the buyer may not

receive the desired product or the seller may need to incur additional costs to

provide it. Fixed-price contracts may also include incentives for meeting or

exceeding selected project objectives, such as schedule targets.

􀂃 Cost-reimbursable contracts—this category of contract involves payment

(Reimbursement) to the seller for its actual costs plus, typically, a fee

representing seller profit. Costs are usually classified as direct costs or

indirect costs. Direct costs are costs incurred for the exclusive benefit of the

project (e.g. salaries of full-time project staff). Indirect costs, also called

overhead costs, are costs allocated to the project by the performing

organization as a cost of doing business (e.g., salaries of corporate

executives). Indirect costs are usually calculated as a percentage of direct

costs. Cost-reimbursable contracts often include incentives for meeting or

exceeding selected project objectives, such as schedule targets or total cost.

􀂃 Time and Material (T&M) contracts—T&M contracts are a hybrid type of

contractual arrangement that contains aspects of both cost-reimbursable and

fixed-price-type arrangements. T&M contracts resemble cost-type

arrangements in that they are open ended, because the full value of the

arrangement is not defined at the time of the award. Thus, T&M contracts can

Software Project Management (CS615)

217

© Copyright Virtual University of Pakistan

grow in con-tract value as if they were cost-reimbursable-type arrangements.

Conversely, T&M arrangements can also resemble fixed-unit arrangements

when, for example, the unit rates are preset by the buyer and seller, as when

both parties agree on the rates for the category of “senior engineers.”

• Other Customer-Developer Relationships

Cost-plus and fixed price are two of the traditional contractual relationships

between developer and customer. There are many variations of these two

basic relationships, including various combinations that are tailored to suit

specific projects. Some of these relationships are associated with the roles of

customer and developer, and attempt to provide more incentives for the

developer to support the customer's objectives beyond contractual obligations.

Additional types of customer-developer relationship include:

• Combinations of fixed price and cost-plus

• Joint ventures

• Royalty agreements

• Long-term commitments

Joint ventures are instances where the customer-developer dividing line can

become hazy, and many of the previously discussed advantages and

disadvantages may not apply. There are many cases where some form of joint

venture may be desirable for both parties, such as when the developer wants to

retain rights to the product, or when the developer joins the customer in

funding part of the development effort.

One way the customer can offer the developer moderate participation in the

business aspect of the project is by substituting royalties as partial payment. This

generates an added dimension to the developer's interest in the success of the

project. The royalties are usually such that the failure of the project would

produce less revenue for the developer than a straightforward fixed price contract,

and the success of the project will increase the developer's revenue.

Long-term relationships are often important for the developer. In many cases,

long term commitments are also in the customer's interest. This occurs when the

developer, by being awarded the initial contract, gains, through acquired

knowledge, a major advantage over others for subsequent development work.

Clearly, when the developer successfully completes a large and complex project,

a significant advantage is then acquired over other companies with respect to

future extensions of the project. A long-term commitment may then be of mutual

interest to both parties, wherein the customer assures future services from the

developer and the developer assures a long term income commitment.

5.12 The statement of work (SOW)

Software Project Management (CS615)

218

© Copyright Virtual University of Pakistan

The statement of work is the basis of the contract between the pro-poser and the

customer, and is often incorporated into the contract. The SOW contains a

detailed list of all work to be performed by the pro-poser for the benefit of the

customer.

It is a narrative description of products or services to be supplied by the project.

For internal projects, the project initiator or sponsor provides the statement of

work based on business needs, or product or service requirements.

For external projects, the statement of work can be received from the customer as

part of a bid document, for example, request for proposal, request for

information, request for bid, or as part of a contract. The SOW indicates a:

􀂃 Business need - an organization’s business need, can be based on needed

training, market demand, technological advance, legal requirement, or

governmental standard.

􀂃 Product scope description - documents the product requirements and

characteristics of the product or service that the project will be undertaken

to create. The product requirements will generally have less detail during

the initiation process and more detail during later processes, as the product

characteristics are progressively elaborated. These requirements should

also document the relationship among the products or services being

created and the business need or other stimulus that causes the need.

While the form and substance of the product requirements document will

vary, it should always be detailed enough to support later project planning.

􀂃 Strategic plan - all projects support the organization’s strategic goals—the

strategic plan of the performing organization should be considered as a

factor in project selection decisions.

The SOW starts as a general list of required deliverables in the RFP. A more

detailed version t of the SOW is submitted as part of the proposal, and is still

considered only an initial description of the work to be performed. The blinding

version of the SOW is finalized during contract negotiations, or after the detailed

project requirements have been completed.

Following table presents an example of an SOW outline for a software project.

The list of items varies considerably, depending on the type of project being

developed; for example not all projects include the delivery of hardware

components, and not all projects require training or installation.

Software Project Management (CS615)

219

© Copyright Virtual University of Pakistan

Table: A sample SOW outline for a software project

14. Referenced documents

• requirements specification

• existing system description

• customer's RFP

• developer's proposal

• vendor's and developer's technical literature

15. Software deliverables

• functionality (as documented in the requirements specification)

• list of major software components

16. Equipment and hardware deliverables

• functionality (as documented in the requirements specification)

• list of major hardware components

17. Training

• user courses

• operator training

• installation training

18. Market research

19. Procurement

20. Supervision of subcontractors

21. Documentation

• development documentation

• user documentation

• maintenance documentation

• other technical documentation

22. Testing

• alpha testing

• beta testing

• acceptance tests (ATP)

23. Installation

24. Maintenance services

25. Other services and deliverable items

26. Method of delivery

• software

• documentation

• hardware

Software Project Management (CS615)

220

© Copyright Virtual University of Pakistan

The basic guideline for the preparation of the SOW is that any activity, service or

product required by the customer, and agreed to by the developer, must be

included. This means that there can be no binding work items that were

informally understood or agreed to verbally, which do not appear in the SOW.

The formal SOW must include all and only the work to be performed. This

condition prevents misunderstandings and disagreements later, after the project

begins.

The statement of work (SOW) describes the procurement item in sufficient detail

to allow prospective sellers to determine if they are capable of providing the item.

“Sufficient detail” may vary, based on the nature of the item, the needs of the

buyer, or the expected contract form.

Some application areas recognize different types of SOW. For example, in some

government jurisdictions, the term SOW is reserved for a procurement item that is

a clearly specified product or service, and the term Statement of Objectives (SOO)

is used for a procurement item that is presented as a problem to be solved.

The statement of work may be revised and refined as it moves through the

procurement process. For example, a prospective seller may suggest a more

efficient approach or a less costly product than that originally specified. Each

individual procurement item requires a separate statement of work. However,

multiple products or services may be grouped as one procurement item with a

single SOW.

The statement of work should be as clear, as complete, and as concise as possible.

It should include a description of any collateral services required, such as

performance reporting or post-project operational support for the procured item.

In some application areas, there are specific content and format requirements for a

SOW.

5.12.1 SOW Template

i. Scope of work: Describe the work to be done in detail. Specify the hardware and

software involved and the exact nature of the work.

ii. Location of Work: Describe where the work must be performed. Specify the

location of hardware and software and where the people must perform the work.

iii. Period of Performance: Specify when the work is expected to start and end,

working hours, number of hours that can be billed per week, where the work must

be performed, and related schedule information. Optional “Compensation”

section.

Software Project Management (CS615)

221

© Copyright Virtual University of Pakistan

iv. Deliverables Schedule: List specific deliverables, describe them in detail, and

specify when they are due.

v. Applicable Standards: Specify any company or industry-specific standards that

are relevant to performing the work. Often an Assumptions section as well.

vi. Acceptance Criteria: Describe how the buyer organization will determine if the

work is acceptable

vii. Special Requirements: Specify any special requirements such as hardware or

software certifications, minimum degree or experience level of personnel, travel

requirements, documentation, testing, support, and so on.

5.13 Software built around a Scheduling Engine

These packages were originally created to manage one project at a time, but over

the years have been enhanced to handle multiple projects.

Well known examples include:

1. Primavera

2. TurboProject

3. OpenPlan

4. Microsoft Project

5. AutoPlan

6. Project Scheduler 8

7. CA SuperProject

8. Timeline

Software Project Management (CS615)

222

© Copyright Virtual University of Pakistan

LECTURE # 29

6. ESTIMATION

6.1 Estimation - Concepts

Watts Humphrey in his book, Managing the Software process, has said, “If you

don’t know where you are, a map won’t help.” This saying is very relevant while

dealing with software project estimation. In a software project, unless you are sure

that your estimation is accurate, you cannot make much progress.

Estimation of factors such as cost, effort, risks, and resources is crucial. It gives

you a fair idea of the size of the project. You can use the information about size to

estimate the cost, effort, and duration of the project. This further helps plan for

resources and schedule the project.

In the early days of computing, software costs constituted a small percentage of

the overall computer-based system cost. An order of magnitude error in estimates

of software cost had relatively little impact.

Today, software is the most expensive element of virtually all computer-based

systems. For complex, custom systems, a large increased cost estimation error can

make the difference between profit and loss. Cost overrun can be disastrous for

the developer.

Software cost and effort estimation will never be an exact science. Too many

variables - human, technical, environmental, political - can affect the ultimate cost

of software and effort applied to develop it.

However, software project estimation can be transformed from a black art to a

series of systematic steps that provide estimates with acceptable risk.

To achieve reliable cost and effort estimates, a number of options arise:

1. Delay estimation until late in the project (obviously, we can achieve 100%

accurate estimates after the project is complete!).

2. Base estimates on similar projects that have already been completed.

3. Use relatively simple decomposition techniques to generate project cost and

effort estimates.

4. Use one or more empirical models for software cost and effort estimation.

Unfortunately, the first option, however attractive, is not practical. Cost estimates

must be provided 'up front.' However, we should recognize that the longer we

Software Project Management (CS615)

223

© Copyright Virtual University of Pakistan

wait, the more we know, and the more we know, the less likely we are to make

serious errors in our estimates.

The second option can work reasonably well, if the current project is quite similar

to past efforts and other project influences (e.g., the customer, business

conditions, the SEE, deadlines) are equivalent. Unfortunately, past experience has

not always been a good indicator of future results.

The remaining options are viable approaches to software project estimation.

Ideally, the techniques noted for each option should be applied in tandem; each

used as a cross-check for the other.

Software project estimation is a form of problem solving, and in most cases, the

problem to be solved (i.e., developing a cost and effort estimate for a software

project) is too complex to be considered in one piece. For this reason, we

decompose the problem, re-characterizing it as a set of smaller (and hopefully,

more manageable) problems.

Following are some points related to project estimation:

• Estimation is very difficult to do, but is often needed

• It is created, used or refined during

– Strategic planning

– Feasibility study and/or SOW

– Proposals

– Vendor and sub-contractor evaluation

– Project planning (iteratively)

• Basic process involves:

– Estimate the size of the product

– Estimate the effort (man-months)

– Estimate the schedule

– NOTE: Not all of these steps are always explicitly performed

6.2 Estimation – A Critical factor

In a software project, unless you are sure that your estimation is accurate, you

cannot make much progress.

Estimation of following factors are essential:

– Cost,

– Effort,

Software Project Management (CS615)

224

© Copyright Virtual University of Pakistan

– Risks

– Resources

Estimation gives you a fair idea of the size of the project. You can use the

information about size to estimate the cost, effort, and duration of the project.

This further helps plan for resources and schedule the project.

Estimation of resources, cost, and schedule for a software engineering effort

requires:

• Experience,

• Access to good historical information

• Courage to commit to quantitative predictions when qualitative

information is all that exists

Estimation carries inherent risk and this risk leads to uncertainty.

a) Project complexity

b) Project size

c) The degree of structural uncertainty

d) The availability of historical information

e) Risk

a) Project complexity has a strong effect on the uncertainty, inherent in planning.

Complexity, however, is a relative measure that is affected by familiarity with

past effort. The first-time developer of a sophisticated e-commerce application

might consider it to be exceedingly complex. However, a software team

developing its tenth e-commerce Web site would consider such work run of the

mill. A number of quantitative software complexity measures can be applied as

per the need of project. Such measures are applied at the design or code level and

are therefore difficult to use during Software planning (before a design and code

exist). However, other, more subjective assessments of complexity (e.g., the

function point complexity adjustment factors) can be established early in the

planning process.

b) Project size is another important factor that can affect the accuracy and efficacy

of estimates. As size increases, the interdependency among various elements of

the software grows rapidly. Problem decomposition, an important approach to

estimating, becomes more difficult because decomposed elements may still be

alarming. To paraphrase Murphy's Law: "What can go wrong will go wrong"- and

if there are more things that can fail, more things will fail.

c) The degree of structural uncertainty has an effect on estimation risk. In this

context, structure refers to the degree to which requirements have been solidified,

the ease with which functions can be compartmentalized and the hierarchical

nature of the information that must be processed.

Software Project Management (CS615)

225

© Copyright Virtual University of Pakistan

d) The availability of historical information has a strong influence on estimation

risk. By looking back, we can emulate things that worked and improve areas

where problems arose.

e) When comprehensive software metrics are available for past projects, estimates

can be made with greater assurance, schedules can be established to avoid past

difficulties, and overall risk is reduced.

f) Risk is measured by the degree of uncertainty in the quantitative estimates

established for resources, cost, and schedule. If project scope is poorly

understood or project requirements are subject to change, uncertainty and risk

become dangerously high.

The software planner should demand completeness of function, performance, and

interface definitions (contained in a System Specification). The planner, and more

important, the customer should recognize that variability in software requirements

means instability in cost and schedule.

Software Project Management (CS615)

226

© Copyright Virtual University of Pakistan

LECTURE # 30

6. ESTIMATION

6.3 Decomposition Techniques

Software project estimation is a form of problem solving, and in most cases, the

problem to be solved (i.e., developing a cost and effort estimate for a software

project) is too complex to be considered in one piece. For this reason, we

decompose the problem, re-characterizing it as a set of smaller (and hopefully,

more manageable) problems.

Before an estimate can be made, the project planner must understand the scope of

the software to be built and generate an estimate of its "size."

6.3.1 Software Sizing

The accuracy of a software project estimate is predicated on a number of things:

(1) The degree to which the planner has properly estimated the size of the product

to be built

(2) The ability to translate the size estimate into human effort, calendar time, and

dollars (a function of the availability of reliable software metrics from past

projects)

(3) The degree to which the project plan reflects the abilities of the software team

(4) The stability of product requirements and the environment that supports the

software engineering effort.

As project estimate is only as good as the estimate of the size of the work to be

accomplished, sizing represents the project planner's first major challenge.

In the context of project planning, size refers to a quantifiable outcome of the

software project. If a direct approach is taken, size can be measured in LOC. If an

indirect approach is chosen, size is represented as FP.

There are four different approaches to the sizing problem:

1. "Fuzzy logic” sizing: This approach uses the approximate reasoning

techniques that are the cornerstone of fuzzy logic. To apply this approach, the

planner must identify the type of application, establish its magnitude on a

qualitative scale, and then refine the magnitude within the original range.

Although personal experience can be used, the planner should also have

Software Project Management (CS615)

227

© Copyright Virtual University of Pakistan

access to a historical database of projects8 so that estimates can be com- pared

to actual experience.

2. Function point sizing: The planner develops estimates of the information

domain. Its characteristics will be discussed later in the session.

3. Standard component sizing: Software is composed of a number of different

"standard components" that are generic to a particular application area. For

example, the standard components for an information system are subsystems,

modules, screens, reports, interactive programs, batch programs, files, LOC,

and object-level instructions. The project planner estimates the number of

occurrences of each standard component and then uses historical project data

to determine the delivered size per standard component. To illustrate, consider

an information systems application. The planner estimates that 18 reports will

be generated. Historical data indicates that 967 lines of COBOL [PUT92) are

required per report. This enables the planner to estimate that 17,000 LOC will

be required for the reports component. Similar estimates and computation are

made for other standard components, and a combined size value (adjusted

statistically) results.

4. Change sizing: This approach is used when a project encompasses the use of

existing software that must be modified in some way as part of a project. The

planner estimates the number and type (e.g., reuse, adding code, changing

code, and deleting code) of modifications that must be accomplished. Using

an "effort ratio" [PUT92) for each type of change, the size of the change may

be estimated.

6.4 Estimation – Tools

i. Work Breakdown Structure (WBS)

a) Dividing into Logical Units/Tasks

To correctly estimate the effort, size, or cost of completing a project, it is

important to be aware of the multiple tasks that comprise a project. You can

divide a project into logical units or tasks by using the WBS technique.

Creating a WBS is a prerequisite for any estimation activity. It enables you to

conceptualize an abstract entity, such as a project, into distinct, independent units.

After dividing a project into tasks, you can categorize them as logical, broad

tasks. For example, tasks, such as drawing up a marketing strategy, planning a

phase-wise product release, and interacting with media agencies and the

production department can be compiled under a common category, Marketing.

b) Benefits of Using a WBS

Software Project Management (CS615)

228

© Copyright Virtual University of Pakistan

Using a WBS provides a number of benefits to the management and to the

development teams.

First, it gives the management an idea about the size and complexity of the

project.

Second, it helps in planning, scheduling, and monitoring a project realistically.

This is possible because all the tasks in the project can be preformed measurable

targets for each task.

To aid planning, scheduling, and monitoring a project, you can use tools such as:

– Program Evaluation and Review Techniques (PERT)

– Critical Path Method (CPM)

– Timeline charts

– Gantt charts

These tools use WBS as the fundamental basis for assessing resources to tasks,

computing the number of days needed, and the cost required to complete the

tasks.

ii. Measuring Effort for a Project

Measuring the effort for a project is a specialized activity. It enables you to derive

cost estimates that are critical for project management. An incorrect measurement

of effort at the beginning of project can result in inaccurate project plans and

frequent slippages. It can also lead to inaccurate cost estimates, which can cause

steep cost deviations between estimated and actual cost values.

There are many techniques that you can use to accurately estimate effort, such as:

a) Source lines of Code (SLOC)

b) Function Point (FP)

c) Constructive Cost Model (COCOMO)

These are quantitative estimation techniques because they rely on the use of

formulae to calculate effort.

In addition to quantitative estimation techniques, there is a human-based

technique known as:

d) Delphi technique

This technique is based on soft skills and relies more on human factors, such as

collecting information during group discussions.

Software Project Management (CS615)

229

© Copyright Virtual University of Pakistan

a) SLOC- Technique

At the beginning of a software project, it is important to determine the size of the

project. The project size helps determine the resources, effort, and duration of the

project.

There are many techniques to calculate the size of a software project. You can

calculate the size by using a directly measurable technique, the SLOC technique.

It is defined as the source lines of code that are delivered as part of the product.

The effort spent on creating the source lines of code is expressed in relation to

thousand lines of code (KLOC).

The SLOC technique is an objective method of estimating the size because there

are no multiple ways of calculating the lines of code. Therefore, the effort

estimate is close to being accurate.

This technique includes the calculation of lines of code, documentation of pages,

inputs, outputs, and components of a software program. Components are again of

multiple types, such as reports, screens, and files.

The SLOC technique is also used to directly calculate the effort to be spent on a

project.

Following figure is a simple example of counting source lines of code. The code

displayed here contains four lines of code.

If (emp_code<=1200)

Print (“Welcome to the Inventory database.”);

Else

Print (“Access denied to the Inventory databases.”);

– Counting SLOC

You can use the SLOC technique to estimate the effort required for a project

when the programming language and the technology to be used are predefined. In

addition to the programming language and technology, the complexity and effort

required to write a program should be easily predictable.

The use of the SLOC technique requires that the technology or language remain

unchanged throughout the project. Generally, you can use the SLOC technique

when you are using third-generation languages, such as FORTRAN or COBOL.

While counting the source lines of code, there are some general considerations

that you need to keep in mind. However, these can vary in every organization.

Software Project Management (CS615)

230

© Copyright Virtual University of Pakistan

The general considerations include the following:

• Only the delivered lines of code are included in SLOC calculation. For

example, test drivers and other support software are not part of the number of

lines developed for a project.

• Only the source lines of code written only by the development team as

counted. This excludes the code created by applications generators.

• Only declaration statements are counted as source lines of code. This

excludes comments inserted to improve the readability of programs.

– Disadvantages of Using SLOC

Despite being accurate in providing figures to calculate the effort required for a

project, the SLOC technique has a drawback.

The SLOC technique is language-dependent. The effort required to calculate

source lines of code may not be the same for all languages.

For example, to conceive and write 8 lines of code that accomplish a task in the

assembly language may require 15 minutes. However, you may need only five

minutes to complete the same lines of code if it is written in Visual Basic.

b) FP Technique

The FP technique is a direct indicator of the functionality of a software

application from the user's perspective. This is the most popular technique used to

estimate the size of a software project.

This fact is further supported by a quote of Capers Jones, chairman of Software

Productivity Research, Inc. in Burlington, Massachusetts, on page 1 of Computer

Finance brought out in November 1997. He quotes "80% of the Fortune 500, are

using function points, at least somewhere in their application development

organizations".

You use the FP technique to estimate the total size of a project. The total size of a

project is estimated as a single FP value. After calculating the total size of a

project in FP, you divide the total FP into the different phases of the SDLC. This

way, you can determine how much effort per FP is required in that particular

phase.

For example, the testing phase is planned for 20 FP of work. The project

managers, based on their past project experience, determine the amount of effort

in man/person months required in the testing phase.

Software Project Management (CS615)

231

© Copyright Virtual University of Pakistan

Function Points

Unadjusted Data Function

Points

Unadjusted Transaction

Function Points

Internal Files

External Interfaces

User Inputs

User Outputs

User Inquiries

Similarly, you can express the cost required to complete FP of work for a

particular phase. At the end of a project, you can also express the number of

defects reported in terms of per FP for a phase.

– Features of Function Points

The total size of a software project is expressed in total function points. It is

independent of the computer language, development methodology, technology, or

capability of the project team developing the software project.

The specific user functionality of the application is evaluated in terms of relation

to what is delivered by the application and, not how it is delivered. Only userrequested

and user-defined components are counted. To calculate FP for a project,

some major components are required.

The major components and their relationships are represented in following figure.

Figure: Function Points Components and their Relationship

You can calculate the function point estimates for a project or a particular phase

by following four steps:

1. Identify the unadjusted function points.

2. Calculate total GSC s.

3. Calculate Value Adjustment Factor (VAF)

4. Apply a formula to calculate Adjusted FP (AFP)

Software Project Management (CS615)

232

© Copyright Virtual University of Pakistan

– Advantages of Using Function Points

Function points are language-and technology-independent. Therefore, you can use

them to estimate any kind of project. They can also be used to estimate the effort,

cost, and schedules of projects that use the Prototyping and Spiral models because

such projects have uncertain user and project requirements.

In addition, you can use function points as a project estimation technique when

you anticipate changes in the middle of a project. These changes may disturb the

estimates if, you had used SLOC to estimate the effort, cost, or size of a project.

The FP estimation uses a subjective and holistic approach for project estimation.

Consequently, the estimates calculated by using the FP are unlikely to be

incorrect.

– Disadvantages of Using Function Points

Estimation by using FP generally uses data from past projects for assigning

weights to GSC s and the information domain values. To be able to do this

realistically, it is important for the organization to have developed similar projects

in the past.

The organization should also be prepared with adequate data and tools for FP

estimation of the new project.

In addition, FP provides a vague estimation. This characteristic of FP does not

usually provide precise or approximate estimates of the effort, cost and size of a

project.

Consequently, at the end of a project, deviations from the estimated to the actual,

values of each of the factors maybe quite extreme.

Software Project Management (CS615)

233

© Copyright Virtual University of Pakistan

LECTURE # 31

6. ESTIMATION

6.5 Estimation – Tools

iii. Measuring effort for a project

c) Constructive Cost Model (COCOMO)

The COCOMO technique is another popular estimation technique. Dr: Barry

Boehm propounded this technique in 1981. COCOMO uses cost driver attributes

to calculate the effort and duration of a project. The COCOMO technique has

three levels of implementation. With each level, the complexity of the model

increases. The levels of the COCOMO technique are:

i. Basic

ii. Intermediate

iii. Advanced

i. Basic COCOMO

The basic COCOMO technique estimates the effort and cost of a software project

by using only the lines of code. You, use basic COCOMO when you need a rough

estimate of effort, such as during maintenance projects. This is because in such

projects, a majority of the work is already completed. Estimating the effort in the

basic COCOMO technique involves three steps.

1. Estimating the total delivered lines of code

2. Determining the effort constants based on the type of the project

3. Substituting values for lines of code and effort constant in a formula

You have already seen how the total delivered lines of code are estimated. The

next step in the COCOMO model is to determine the type of the project being

developed. The basic COCOMO technique considers three types of projects to

calculate effort.

– Organic

– Embedded

– Semidetached

Organic projects have sufficient and defined objectives. The organizations that

undertake organic projects have ample experience in development and use small

development teams. These are simple business and financial applications; such as

a banking system and inventory system.

Software Project Management (CS615)

234

© Copyright Virtual University of Pakistan

Embedded projects have stringent and specialized hardware, software, and human

resources requirements. Organizations usually have less experience in developing

such projects. Examples of such projects include real-time operating systems

(RTOS), industrial automation systems, and sophisticated space and aviation

systems.

Semidetached projects are a combination of the preceding two types of software

projects. A new operating system and a database management system (DBMS)

are examples of such projects.

The last step in calculating effort by using the COCOMO technique is to

substitute the values of lines of code and effort constants in the following

formula:

Ej = a1 * (KLOC)a2

In the formula, Ei is the effort for a project. The effort constants, al and a2

depend on the type of project being developed.

ii. Intermediate COCOMO

Calculation of effort by using the intermediate COCOMO technique involves an

additional step of calculating the effort adjustment factor (EAF). The effort

adjustment factor is calculated by assigning ratings to 15 cost driver attributes.

These cost driver attributes relate to the various aspects of a software project, such

as project, product, personnel, and computer attributes. Using the intermediate

COCOMO technique, you can accurately estimate effort and cost required for a

project. Accurate estimates are very helpful to start new development projects.

Calculating the effort by using the intermediate COCOMO technique is a threestep

process:

1. Estimate the initial development effort by using SLOC. To do this, you use

the following formula:

Ei = a1 * (KLOC)a2

In the formula the initial development effort, KLOC refers to 1,000 lines of code.

The constant values a1 and a2 differ with every project.

2. The second step is to determine the relevant cost driver attributes that affect

your project intensively. This provides you with the value for EAF.

Software Project Management (CS615)

235

© Copyright Virtual University of Pakistan

Table 1 summarizes 15 commonly used projects, personnel, and product-related

cost driver attributes. The values for each cost driver under each rating are filled

in by an organization based on past experience.

Table 1: Cost Driver Attributes

Rating

Cost Drivers Negligible Low Average High Very

high

Extremely

critical

Analyst Capability (ACAP)

Programmer Capability (PCAP)

Programming Language

Experience (LEXP)

Virtual Machine

Experience(VEXP)

Required Software Reliability

(RELY)

Database Size (DATA)

Software Product Complexity

(CPLX)

Execution Time Constraint

(TIME)

Main Storage Constraint

(STOR)

Computer Turnaround Time

(TURN)

Virtual Machine Volatility

(VIRT)

Use of Software Tools (TOOL)

Modern Programming Practices

(MODP)

Required Development

Schedule (SCED)

3. Finally, you calculate the actual effort by multiplying the weighted cost driver

attributes with the initial effort estimate. Typically, the val1,les that rate each

cost driver attribute range from 0.9 through 1.4. For example, if software

reliability (RELY) is of prime importance according to the requirements

specifications, it is provided a rating of high or a value of 1.4. Similarly, if the

time to execute a software program is of negligible importance, you assign a

rating of low or a value of 0.9. For software attributes that are of mediocre

importance, you can assign a value between 0.9 and 1.4.

Software Project Management (CS615)

236

© Copyright Virtual University of Pakistan

Usually, in organizations, the average rating is assigned a static value of 1.0. To

calculate the estimated effort using the intermediate COCOMO technique, you

use the formula:

E = EAF * Ei

Consider an example for using the intermediate COCOMO technique to calculate

the estimated total effort of a project life cycle. In a customized insurance project,

there are four modules. The total effort estimate of the modules is 3.0 KLOC. The

management has identified four cost driver attributes with the respective

multiplying factors that might affect the project most. In this situation, the values

of al and a2 are 3.2 and 1.05, respectively, because the insurance project is an

organic project. Therefore, you apply the following formula to calculate the initial

effort estimate.

Ei = a1 (KLOC)a2

Ei =3.2 * 31.05

Ei = 3.2 * 3.16

Ei = 10.11

The values assigned to the cost driver attributes that are applicable to a particular

software application are displayed in Table 2. According to the table, the time to

execute a software program is of high importance. Therefore, the attribute TIME

is assigned a value of 1.35. In contrast, the software application does not require a

very high analyst involvement. Therefore, the value assigned to ACAP is very

low or 0.95. Using the same logic, the values for other cost driver attributes are

assigned.

Table 2: Applicable Cost Driver Attributes

Applicable cost driver attributes Rating Multiplying factors

CPLX High 1.2

TIME Very high 1.35

ACAP Low .95

MODP Average 1.00

Referring to Table 7.9, EAP can be calculated as,

EAF = 1.2 * 1.35 * 0.95 * 1.0 EAF = 1.53

After obtaining the values for the variables Ei and EAF, you can substitute these

values in the formula to calculate the total effort.

E = EAF * Ei

E = 1.53 * 10.11

Software Project Management (CS615)

237

© Copyright Virtual University of Pakistan

E = 15.5 person months

iii. Advanced COCOMO

The advanced COCOl\l10 technique uses the steps of the intermediate COCOMO

technique. In addition, it uses costs driver attributes assigned to each phase of the

SDLC such as analysis and design.

• Applicability of COCOMO

COCOMO is flexible and capable of using SLOC, FP, and even object points.

Object points are measurable code sections in an object-oriented programming

language, such as C++, Ada, and Java.

You can use COCOMO when the size of a project is extensive and the

requirements of the project are vague. In contrast, SLOC and FP can be used for

projects where either the requirements are more or less known or developers

possess the relevant experience in developing projects.

COCOMO is suitable for complex and sophisticated projects that are expected to

operate within intensive hardware, software, and personnel constraints.

Generally, you can use COCOMO when the software development environment

is new to an organization. In addition, you can use COCOMO when you do not

have baseline data about past projects. However, you need complete data about

your current project to assign weight age to each cost driver attribute. You can use

FP or SLOC techniques when you have enough past project data to assign

accurate weight age to the 14 GSC s and the various information domain value

elements.

d) Delphi Technique

The Delphi technique is a Human-based estimation technique. Human-based

estimation techniques use human experience and analytical skills to estimate the

size, productivity, and effort required for a project. This is a trusted technique and

is widely used in many established organizations to facilitate practical and

reasonable estimation.

The rationale of using the Delphi technique is that when many experts

independently arrive at the same estimate on the basis of similar assumptions, the

estimate is likely to be correct.

The Delphi technique has eight basic steps:

1. Identify the terms that need to perform the estimation activity. In an estimation

activity meeting, three distinct groups of people need to be present.

Software Project Management (CS615)

238

© Copyright Virtual University of Pakistan

• Estimation experts: They usually consist of groups of five or six experienced

project managers. The estimation values provided by the project managers are

based on past project history and their knowledge. However, only those

project managers should b~ invited for estimation whose experience of a past

project matches that of the current project. Otherwise, estimation values may

turn out to be far from realistic.

• Estimation coordinator: An estimation coordinator is very similar to a

moderator in a usual meeting. The coordinator facilitates the meeting and

ensures that the goals of the meeting are fully achieved.

• Author: An author is similar to a recorder of minutes in a meeting.

2. The author presents the project details including clients’ needs and system

requirements to the group of experts. The author also describes the expectations

from the group. The author and experts jointly identify the tasks that need to be

estimated. They also identify the valid assumptions that they need to consider

while estimating. For example, while estimating the effort needed to create a

high-level design, they can assume that the SRS document is approved by the

client.

3. The author and experts arrive at a consensus that any estimation with a specific

variance value will not be accepted. For example, they may decide that any

variance above 25 percent will not be accepted as an estimation value for

computing the project effort or the productivity.

4. The coordinator prepares a list of tasks jointly decided by the team and

distributes the list to all experts. These tasks comprise a project plan.

5. The experts independently make their estimates for each task. After recording

their estimates, they hand over their estimates to the coordinator. This is a critical

step. While making estimates, no discussions or consultations are permitted

because a mutual discussion may influence the estimation logic of the fellow

experts. The coordinator and the author jointly ensure this.

6. The coordinator prepares a summary of estimates for each task in a table as

represented in Table 7.10. After calculating the percentage of variance, the

coordinator marks each task as accepted or not accepted based on the agreed

accepted value.

7. The coordinator hands over the summary to the group of experts and the author.

The group of experts and the author discuss tasks and assumptions where the

percentage of variance is more than the acceptable level. The maximum and

minimum estimates of tasks are not disclosed or discussed. For example, in Table

7.10, the group and the coordinator do not accept the high-level design task

because it exceeds the agreed variance value of 25%. Therefore, the team would

discuss this task to estimate its maximum and minimum effort afresh. To resolve

Software Project Management (CS615)

239

© Copyright Virtual University of Pakistan

the high percentage of the variance value, some tasks may be broken down

further or combined. This activity of breaking down tasks into smaller levels

involves fresh estimates for those tasks at the smaller levels.

8. Revert to step 5 and repeat the steps. You do this until all tasks are assigned

estimates that have an acceptable percentage of variance value. Figure 7.4.

summarizes the steps of the Delphi technique in the form of a flowchart.

Identify the teams that will

estimate.

Present project details to the expert

group.

Finalize the acceptable variance

value.

Prepare a list of tasks.

Estimate done by the expert group

Prepare a summary of estimates

for each task.

Discuss tasks and assumptions for

not acceptable estimates.

Software Project Management (CS615)

240

© Copyright Virtual University of Pakistan

Figure 1: Steps of the Delphi Technique

The Delphi technique is a simple and subjective method of estimation. However,

it is a very effective method because most of the estimates are tried and tested.

You can use this method if the project is small or if you have the data and

expertise that can enable unambiguous estimates.

Repeat steps until all estimates are

finalized.

Software Project Management (CS615)

241

© Copyright Virtual University of Pakistan

LECTURE # 32

7. Work Breakdown Structure

7.1 WBS Preview

i. Salient features

Large, complex projects are organized and comprehended by breaking them into

progressively smaller pieces until they are a collection of defined "work

packages" that may include a number of tasks.

A $1,000,000,000 project is simply a lot of $50,000 projects joined together.

Work breakdown structure (WBS) is a technique to decompose the project for the

purpose of management and control. It provides the framework for organizing and

managing the work.

A project may be divided into subprojects. Subprojects are subdivided into

smaller, more manageable work components (work packages) at the lowest level.

The work packages may be further decomposed to project activities. It provides

the framework for organizing and managing the work.

A project may be divided into subprojects. Subprojects are subdivided into

smaller, more manageable work components (work packages) at the lowest level.

The work packages may be further decomposed to project activities.

The WBS is commonly used at the beginning of a project for defining project

scope, organizing Gantt schedules and estimating costs.

It lives on, throughout the project, in the project schedule and often is the main

path for reporting project costs.

WBS includes activities like management, procurement, installation, software

development etc.

Many of the WBS development tasks are derived from the development method

that will be used, and from the design and architecture of the system.

WBS is related to planning and scheduling a project

It is a functional decomposition of the tasks of the project.

Software Project Management (CS615)

242

© Copyright Virtual University of Pakistan

It starts with the end objective required and successively subdividing it into

manageable components in terms of size and complexity of:

– Program,

– Project,

– System,

– Subsystem,

– Components,

– tasks, subtasks, and

– work elements

The WBS is first and foremost a technical data gathering structure, developed so

that the achievement in technical progress can be measured and analyzed against a

formal baseline plan.

The WBS aids the customer in understanding the status of the project as time

elapses. The WBS aids the customer's customer in understanding the status of the

project.

All managers, internal and external need to use the planning and status

information within the WBS structure to:

– Aid in the adjustment to the current program paths and

– For maximizing the attainment of short term and long term goals

ii. WBS-What is it?

WBS is a definition of a project in terms of its work or a deliverable-oriented

grouping of project elements that organizes and defines the total scope of the

project.

Each descending level represents an increasingly detailed definition of the

project’s work.

It’s an outline of the work of the project, not the work itself, created by those

doing the work – that may include all functional stakeholders.

iii. WBS- What it contains?

– Maps all contractual obligations (SOW) regarding deliverables

– Details project objectives

– Detailed enough to meet performance (measurable) objectives

– Contains built-in WBS and Project Plan review and update

Software Project Management (CS615)

243

© Copyright Virtual University of Pakistan

iv. WBS- When is it produced?

The WBS is produced following the development of the scope statement, before

the schedule. It is a “bridging” document between the Scope and Schedule. (what

and when)

v. Uses of WBS

– Defines 100% of the scope and can communicate the scope of the project

without the presence of the scope statement or document.

– Communicates effectively to all stakeholders

– Defines and clarifies

– Boundaries (Life cycle of the project – not the product)

– Deliverables

– Refines Scope

Defines scope in project management language (perhaps down to work package

level which may lead to development of project schedule)

It’s not a single document that can be mistaken for the project plan, schedule or

scope statement

7.2 WBS- A Mandatory Management Tool

i. WBS as a Project Management Tool

A WBS is a valuable management tool that is used throughout all life-cycle

phases to:

a. Manage Risk

It helps in managing risk by providing insight into technical aspects of program

management.

b. Manage Costs

A WBS can be used to help make program management decisions.

For example, if the costs of an element in the WBS are too high, the WBS can be

used to identify possible tradeoffs. Identifying and analyzing tradeoffs can help

the manager decide how best to stay within budget.

c. Assign Work

The WBS is also useful for determining an acquisition strategy and/or assigning

work. The information contained in the WBS can help a Program Manager

Software Project Management (CS615)

244

© Copyright Virtual University of Pakistan

develop a statement of work that describes what products or services are to be

delivered.

d. Schedule and Track activities

A schedule of key events can be developed for each element in the WBS.

Completion of these key events is then tracked.

– Schedule and Track activities

– The work breakdown structure defines all tasks to be performed during the

development of the project. This will include tasks from such project

categories as:

􀂃 Software development

􀂃 Installation

􀂃 Maintenance

􀂃 Management

􀂃 Training

􀂃 Procurement

􀂃 Documentation

e. Align with Terms of Reference and scope of project

– At all times, any, work being performed by a member of the software project

team must be part of a WBS task: No member of the team should ever

perform any task that does not appear in the WBS list of tasks.

– The WBS is essentially a management tool that provides the ability to assign

well-define tasks to members of the development team.

– It is through the WBS that progress is monitored as tasks are completed and

potential problems are discovered.

– New tasks that were overlooked are identified, and estimates are revised based

on the actual resources used for completed tasks.

f. Report Expense

– The WBS is also a budgetary tool that provides a means of charging each

development activity to the appropriate section in the project budget.

– This is one of the basic methods for planning and monitoring project

expenditure.

– There are mainly computerized utilities available to support the maintenance

of the WBS.

– These utilities run both on small PC type computers and large mainframes.

Software Project Management (CS615)

245

© Copyright Virtual University of Pakistan

– WBS utilities are often available as part of a manager's general planning

utility, and provide other scheduling and monitoring features, such as PERT

analysis and report generation.

Software Project Management (CS615)

246

© Copyright Virtual University of Pakistan

LECTURE # 33

7. Work Breakdown Structure

7.3 WBS- A Mandatory Management Tool

i. The WBS as a project management tool

g) Mapping WBS for Cost Management

In a product-oriented WBS, functional categories of work may form "cost

accounts" within a WBS element. Cost account managers are responsible for a

functional area’s contribution to a WBS element. Cost accounts from several

departments or functions may combine into one WBS element.

Internal department planning for a cost account will be made up of individual

work packages. A work package will typically have its own budget and schedule.

Work packages should be small enough to be executed by individuals or small

groups in a single department, and they should be of relatively short schedule

duration. A small project might define a maximum work package size as two

weeks of effort. Larger projects will assemble larger work packages that can be

appropriately managed and controlled.

The project manager will have to decide to what degree employment of various

details of WBS implementation will benefit the efficient management of the

project. On a very small project, a formal WBS may serve no useful purpose, but

it can become valuable if project size or complexity start to increase.

As an organization’s project management environment matures, or as larger size

and complexity are encountered, application of the WBS concept can evolve from

an ad hoc list of tasks, to time-phased activity lists, task lists clustered by project

deliverables and services, or an end-product focused WBS fed by cost accounts

and work packages.

If you are using MS-Project or a similar project management software application,

you may encounter the WBS as a vertical list with indents to show structure. This

will be compatible with the Gantt View data entry screens. While some software

packages provide a separate WBS view, you could prepare your WBS in the

vertical format using a word processor, and then cut and paste your WBS into

your project management software package.

Software Project Management (CS615)

247

© Copyright Virtual University of Pakistan

WORD OF CAUTION

• The WBS is a useful tool provided it is constantly updated.

• It should be updated periodically together with the project development plan and

the project schedule.

• It is reasonable to expect the WBS list to have tasks added, modified or even

removed as project development progresses.

Hardware Software Systems

Engr.

Training

Info. Systems

Purchasing

Testing

Tech. Editors

Functional Areas

WBS Elements

Cost Account

Cost Account

Cost Account

Cost Account

Cost Account

Cost Account

Cost Account

Cost Account

Cost Account

Cost Account

Cost Account

Cost Account

Cost Account

Cost Account

Cost Account

Work

Packag

es

Software Project Management (CS615)

248

© Copyright Virtual University of Pakistan

LECTURE # 34

7. Work Breakdown Structure

7.4 WBS- A Mandatory Management Tool

h) Characteristics of a High-Quality WBS

a) Review and signoff from top to bottom

b) Includes logical flow and is hierarchical in nature

c) Clear and concise

d) Provides ability to roll-up information to higher levels

e) Receives 100% team buy-in

f) Should have at least 2 levels: Level 1 defines 100% of the service/product/result;

Level 2 defines the deliverables in terms of work (groupings)

g) Project Management (and sub-contract management) at Level 2.

h) The deliverables in the WBS must match the scope or contract (WBS should not

contain work that is not defined in the scope – Scope should not describe work

not contained in the WBS)

i) All deliverables should be accounted for regardless of responsibility

j) Every WBS element should be clearly defined – or should be clarified in the WBS

Dictionary

k) Features

– The WBS should contains 100% of the work defined by the scope or contract

– Development of WBS should involve the entire project team

– Should be deliverable-oriented

– Should captures all deliverables (Internal, External, Interim) in terms of work to

be completed

l) Usefulness

Software Project Management (CS615)

249

© Copyright Virtual University of Pakistan

– Should define the context of the project and clarifies the work

– Should communicates project scope to all stakeholders in terms of the

work to be completed

– Is “in sync” with the scope statement and project schedule

– Implies and allows for continual improvement/update of the WBS to

maintain current-ness and “vitality” within the project

m) WBS Is Not

– A single document that substitutes for the project schedule or project plan

– The project schedule

– A listing of tasks or activities

i) Types of WBS

The two types of Work Breakdown Structures are:

a) Program Work Breakdown Structures

b) Contract Work Breakdown Structures

a) Contract WBS

A Contract WBS extends the Program WBS to a lower level in order to provide

management and cost information to the Government. It includes all the elements

for products (e.g., hardware, software, data, or services) that are the responsibility

of the contractor. It must be consistent with the Program WBS.

Software Project Management (CS615)

250

© Copyright Virtual University of Pakistan

– Contract WBS: Contractor's Responsibility

Contractors may extend the work breakdown structure to whatever level they feel

is necessary to manage the program. Contractors also use the Contract WBS to

define work packages. Work packages are:

Discrete portions of the project that can be charged to a single organization.

Building blocks for program management and cost reporting.

Remember that a Contract WBS:

• Is prepared and maintained by each contractor working on different portions

of the program.

• Includes the number of levels thought sufficient by the contractor to manage

the program.

• Must be updated if changes are made to the Program WBS.

b) Program WBS

A Program WBS is defined as "the work breakdown that covers the acquisition of

a specific defense materiel item and is related to contractual effort."

A Program WBS is:

• Tailored to each specific program.

• Prepared and maintained by the Government.

• Provides a basis for developing the Contract WBS.

– Program WBS Levels

Software Project Management (CS615)

251

© Copyright Virtual University of Pakistan

Typically, a Program WBS consists of the upper three levels.

WBS Level 1: The entire defense materiel item.

WBS Level 2: Major elements of the defense materiel item, which are subordinate

to Level 1.

WBS Level 3: Elements subordinate to Level 2 elements.

j) Sample WBS

Design

&

Engineering

Project

Management

Documentation Training &

BPR

Software

System

Software

Project

Web based

Classroom

Hands-on

What About?

– Requirements

– Prototyping

– Testing

– User Acceptance

– Life-cycle Management

– Warranty

Sample 1: A Product WBS

Software Project Management (CS615)

252

© Copyright Virtual University of Pakistan

WBS Sample 2: System Development Projects

Project

Hardware

1.1

Software

1.2

System

Engr

1.3

Project

Mgt

1.4

System

Test

1.5

Data

Mgt

1.6

1.1.2

1.2.2

1.1.2.1

1.1.2.1.1 Level 5

Level 1

Level 2

Level 3

Level 4

Software Project Management (CS615)

253

© Copyright Virtual University of Pakistan

WBS Sample 3: Software/Hardware System Development

READING REFERENCE:

For detailed reading refer to:

(i) Chapter No. 6 entitled “How to handle large projects: Divide and

Conquer” of “Software Project management – A Practitioner

Approach by E. M. BENNATAN.

(ii) Chapter 5 entitled Software Project Planning” of: SE–A

Practitioner Approach by Roger S. Pressman.

(iii) Chapter 7 entitled “Software Project Estimation: Tools and

Techniques by NIIT

Project A

Project

Mgt. Systems

Engr.

Software Hardware Deliverables

Mgt.

System

Test

Support

Services

Installation

Software

Design

Software

Build

Unit

Testing

Level 1

Level 2

1.1 1.2 1.3 1.4 1.5 1.6 1.7 1.8

1.3.1

1.3.2

1.3.3

Level 3

Software Project Management (CS615)

254

© Copyright Virtual University of Pakistan

LECTURE # 35

7. Work Breakdown Structure

7.5 WBS- A Mandatory Management Tool

iv. Sample WBS

Sample 1: These two graphics illustrate approaching the WBS as a parts list or as a

process list

Software Project Management (CS615)

255

© Copyright Virtual University of Pakistan

Sample 2: WBS of Manufacturing of a Mountain Bike

Software Project Management (CS615)

256

© Copyright Virtual University of Pakistan

Sample 3: This illustrates an example of Ordnance System WBS

Software Project Management (CS615)

257

© Copyright Virtual University of Pakistan

The list of activities is often called a Work Breakdown Structure (WBS). The goal is to

integrate the WBS, the schedule, and the budget into a written plan.

The WBS reflects activities associated with overall project management, requirements,

design, implementation, transition management, testing, training, installation, and

maintenance. The project manager is responsible for defining all top level tasks

associated with a project and then further decomposing them as planning continues.

An activities list is typically shown in one of two ways. It can be shown as an outline or

it can be graphically presented. Two samples of an activities list (WBS) are shown

below.

1.0 MANAGEMENT

1.1 Plan Project

1.1.1 Develop Project Plan

1.1.2 Update Project Plan

1.2 Track Project

1.2.1 Prepare status reports

1.2.2 Collect/analyze project metrics

1.3 Perform Quality Activities

1.3.1 Prepare QA Plan

1.3.2 Conduct Reviews

1.3.3 Conduct Audits

1.4 Perform Configuration Management

1.4.1 Prepare CM Plan

1.4.2 Develop Project Library

1.4.3 Manage Change Board

1.4.4 Maintain Configuration Items

2.0 DESIGN

2.1 Prepare Preliminary Design

2.1.1 Develop Enterprise Architecture

2.1.2 Prepare Data Flow Diagrams

2.1.3 Prepare Logical Data Model

2.2 Prepare Detailed Design

2.2.1 Prepare Physical Data Model

2.2.2 Prepare Data Dictionary

2.3 Document Design

2.3.1 Develop Design Specification

2.4 Review Design

Software Project Management (CS615)

258

© Copyright Virtual University of Pakistan

3.0 DEVELOPMENT/INTEGRATION

3.1 Develop Software

3.1.1 Develop Server Application

3.1.2 Develop User Interface

3.1.3 Develop XYZ Interface

3.2 Procure Hardware

3.2.1 Procure Server

3.2.2 Procure Workstations

3.3 Procure Software Packages

3.3.1 Procure Database

3.3.2 Procure User Interface Building Tool

3.3.3 Procure Operating System

3.4 Perform Integration Testing

3.5 Convert Data

3.5.1 Develop Conversion Plan

3.6 Develop User Manual

3.7 Transition Management

4.0 ACCEPTANCE TESTING

4.1 Plan Acceptance Test

4.2 Conduct Acceptance Test

4.3 Develop Test Report

5.0 INSTALLATION

5.1 Develop Installation Plan

5.2 Site Preparation

5.3 Install at Locations

5.3.1 Headquarters

5.3.2 Site 1

6.0 MAINTENANCE

6.1 Hardware Maintenance

6.2 Software Maintenance

Software Project Management (CS615)

259

© Copyright Virtual University of Pakistan

Sample 4: Sometimes, instead of depicting the WBS as an outline, it is shown

graphically, as below:

WBS

Work Breakdown

Schedule (WBS)

Management

Plan Project

Track Project

Develop Project Plan

Update Project Plan

Prepare status report

Collect/analyze

project metrics

Perform Quality

Activities

Prepare QA Plan

Conduct Reviews

Perform CM

Prepare CM Plan

Develop Project Library

Conduct Audits

Manage Change Board

Maintain Configuration

Items

Design

Prepare

Preliminary

Design

Prepare Detailed

Design

Develop Enterprise

Architecture

Prepare Data

Flow Diagrams

Prepare Physical

Data Model

Prepare Data

Dictionary

Document

Design

Develop Design

Specification

Review Design

Prepare Logical

Data Model

Development/

Integration

Develop

Software

Procure

Hardware

Develop Server

Application

Develop User

Interface

Procure Server

Procure Workstations

Procure Software

Packages

Procure Databases

Perform

Integration

Testing

Develop XYZ

Interface

Procure User Interface

Building Tool

Procure Operating

System

Convert Data

Develop Conversation

Plan

Develop User

Manual

Acceptance

Testing

Plan Acceptance

Test

Conduct

Acceptance Test

Develop Test

Report

Installation

Develop

Installation Plan

Site Preparation

Maintenance

Hardware

Maintenance

Software

Maintenance

Install at

Locations

Headquarters

Site One

Transition

Management

Software Project Management (CS615)

260

© Copyright Virtual University of Pakistan

Sample 4: Chart WBS

Sample WBS - Outline Example-1

0.0 Retail Web Site

1.0 Project Management

2.0 Requirements Gathering

3.0 Analysis & Design

4.0 Site Software Development

4.1 HTML Design and Creation

4.2 Backend Software

4.2.1 Database Implementation

4.2.2 Middleware Development

4.2.3 Security Subsystems

4.2.4 Catalog Engine

4.2.5 Transaction Processing

4.3 Graphics and Interface

4.4 Content Creation

5.0 Testing and Production

Retail Web

Site

Project

Managemen

Requiremen

ts

Design and

Analysis

Site Software

Development

HTML

Design

Backend

Software

Graphics and

Interface

Content

Creation

Database

Implementat

Security

Subsystems

Catalog

Engine

3.

0

1.0 2.

0

Transaction

Processing

4.

0

5.0

4.

1

4.

2

4.2.1 4.2.2 4.2.3 4.2.4

4.3 4.4

0 0

Software Project Management (CS615)

261

© Copyright Virtual University of Pakistan

Sample WBS - Outline Example-2

1.10 MANAGEMENT

1.1 Plan Project

1.1.1 Develop Project Plan

1.1.2 Update Project Plan

1.2 Track Project

1.2.1 Prepare status reports

1.2.2 Collect/analyze project metrics

1.3 Perform Quality Activities

1.3.1 Prepare QA Plan

1.3.2 Conduct Reviews

1.3.3 Conduct Audits

1.4 Perform Configuration Management

1.4.1 Prepare CM Plan

1.4.2 Develop Project Library

1.4.3 Manage Change Board

1.4.4 Maintain Configuration Items

2.0 DESIGN

2.1 Prepare Preliminary Design

2.1.1 Develop Enterprise Architecture

2.1.2 Prepare Data Flow Diagrams

2.1.3 Prepare Logical Data Model

2.2 Prepare Detailed Design

2.2.1 Prepare Physical Data Model

2.2.2 Prepare Data Dictionary

2.3 Document Design

2.3.1 Develop Design Specification

2.4 Review Design

3.0 DEVELOPMENT/INTEGRATION

3.1 Develop Software

3.1.1 Develop Server Application

3.1.2 Develop User Interface

3.1.3 Develop XYZ Interface

3.2 Procure Hardware

3.2.1 Procure Server

3.2.2 Procure Workstations

3.3 Procure Software Packages

3.3.1 Procure Database

3.3.2 Procure User Interface Building Tool

3.3.3 Procure Operating System

3.4 Perform Integration Testing

3.5 Convert Data

Software Project Management (CS615)

262

© Copyright Virtual University of Pakistan

3.5.1 Develop Conversion Plan

3.6 Develop User Manual

3.7 Transition Management

4.0 ACCEPTANCE TESTING

4.1 Plan Acceptance Test

4.2 Conduct Acceptance Test

4.3 Develop Test Report

5.0 INSTALLATION

5.1 Develop Installation Plan

5.2 Site Preparation

5.3 Install at Locations

5.3.1 Headquarters

5.3.2 Site 1

6.0 MAINTENANCE

6.1 Hardware Maintenance

6.2 Software Maintenance

Sample WBS - Outline Example-3

Step Description Estimate

1. Preparation

1.1. Developer orientation TBD

1.2. Requirements gathering

1.2.A. Use Cases TBD

1.2.B. Changes to data model TBD

1.2.C. Non-functional requirements TBD

1.2.D. Requirements validation TBD

1.3. Design

1.3.A. Software architecture TBD

1.3.B. User interface design TBD

1.4. Development tools TBD

2. Construction

2.1.A. System implementation

2.1.A.1 Unit tests TBD

2.1.A.2 Production code TBD

Software Project Management (CS615)

263

© Copyright Virtual University of Pakistan

2.1. A.3. Integrate Components

(mostly done during component implementation)

TBD

2.1.B. Maintenance documentation TBD

2.1.C. User documentation TBD

3. Quality assurance

3.1. Fixing defects reported by users TBD

3.2. Testing

3.2. D.1. Test planning TBD

3.2. D.2. Test implementation TBD

3.2. D.3. Test execution TBD

3.3. Reviews of design and code TBD

3.4. Fixing defects found by testing and review TBD

4. Transition

4.A. Release packaging TBD

4.B. Documentation for other groups TBD

5. Reflection

5.1. Postmortem report TBD

Total fixed costs TBD

• Tasks shown as blue are fixed costs of the project. These should be

estimated soon.

• Tasks shown as black are proportional to the size of the requirements. A

more detailed work breakdown structure will be produced for these tasks

when the requirements are better known.

• Tasks shown as red depend on the defect rate in the delivered code. These

will be estimated after 12 months experience.

TIP: Label each step uniquely to show its position in the WBS, e.g.,

Step 1.1.4.A. Use numbers for steps that you intend to do in

sequence, and use letters for steps that you intend to do in parallel.

E.g., Step 1.1 comes before Steps 1.2.A and 1.2.B, but those two

steps may be done in parallel, and Step 1.3 will be done after all 1.2.*

steps have been finished. Don't worry about renumbering if you delete

a step.

Software Project Management (CS615)

264

© Copyright Virtual University of Pakistan

7.7 WBS- Major Steps

a) Project Decomposition

Many complex objects can be viewed as a collection of numerous simpler objects.

An appropriate example would be a complex chemical compound that is formed

by various molecules, each of which is formed by combining various atoms. The

atom, though itself divisible, can be regarded as the smallest particle of a

chemical substance.

In a similar way, a complex project can be divided into simpler components.

While the full project may be difficult to manage, each component will be easier

to handle. Software projects can be decomposed into smaller components in order

to provide better estimates of the amount of work involved, or in order to monitor

the activities of the various development teams.

The decomposition of a software project is one of the software project manager's

first tasks. However, the method of decomposition may differ, depending on the

project manager's actual objective. A functional decomposition of a project may

not be the same as design decomposition. A functional decomposition divides the

project into its basic components from a user's perspective, while design

decomposition divides a project into its basic programming components or

modules.

Intuitively, it would not appear reasonable to attempt to identify all project

components in a single step. Clearly, an iterative procedure that would gradually

provide more detail would be easier to use. Iterative methods of this kind are

called stepwise refinement, as the decomposition is further refined in each

succeeding step.

Figure 1 presents a general illustration of stepwise refinement. The system is

initially divided into three top level components. In turn each top level component

is further divided into lower level components, and so forth, until the lowest

decomposition level is reached.

In a stepwise decomposition of a project, each component decomposes into the

components directly below it, so that each step of the decomposition describes the

full system, but at a different level of detail. In Fig.1, components 1, 2 and 3

comprise the complete system. For more detail we take the next decomposition

step, and find that components 1.1, 1.2, 2.1, 2.2, 2.3, 3.1 and 3.2 now represent

the whole system.

Software Project Management (CS615)

265

© Copyright Virtual University of Pakistan

System

Component

1

Component

2

Component

3

1.1 1.2 2.1 2.2 2.3 3.1 3.2

2.1.1

2.1.2

2.2.3

2.2.1 2.2.2 2.3.1 2.3.2

Figure 1: Software decomposition by stepwise refinement

A stepwise refinement diagram looks similar to a hierarchical system chart.

However, it is important to understand that stepwise refinement is basically

different because the diagram's building blocks are different A hierarchical

system diagram describes the hierarchical relationship between components, so

that each component in the diagram actually corresponds to a real component in

the system. However, in a stepwise refinement diagram, a higher level component

is only a name conveniently given to a group of real components that appear

below it.

In Fig. 2(a) the Controlled access system software has five low level software

components:

Visitor identification, Door lock-control, Access file-manager, Illegal access

identification and Alarm activation. Each of these five modules may correspond

to an actual software module1. The two high level components, Access control

and Alarm system, do not exist as actual software modules, and only appear as

names given to the two groups of lower level components.

Figure 2(b) describes the same Controlled access system software, but this time it

is represented as a hierarchical chart. Here, each component in the diagram

represents a real software component.

Software Project Management (CS615)

266

© Copyright Virtual University of Pakistan

The System executive main Loop component calls three other components:

Visitor identification, Door lock control and Alarm activation: The Visitor

identification component calls two components: Illegal access identification and

Access file manager.

Figure 2: (a) Decomposition of high level components into low level components; (b) a

hierarchical structure chart

Controlled

Access

system

Software

Access

Control

Alarm

System

Visitor

Identification

Door lock

Control

Access

File

Manager

Illegal

Access

Identification

Alarm

Activation

(a)

System

Executive

Main loop

Visitor

Identification

Door lock

Control

Alarm

Activation

Illegal

Access

Identification

Access

File

Manager

(b)

Software Project Management (CS615)

267

© Copyright Virtual University of Pakistan

Just like any other large complex task, the development of a software project is

more easily managed with the divide and conquer approach.

Stepwise refinement, when applied to a software project, produces all the low

level work tasks and includes

– development tasks

– managerial tasks

– support tasks and

– administrative tasks

The WBS list of project tasks is derived from the project's statement of work (the

SOW) that defines the scope of the project. The SOW is usually prepared before

the official launching of the project, and is often part of the project contract

between the customer and the developer.

For internal projects, when an organization is funding its own development work,

the SOW becomes synonymous with the Project definition specification or a

similar document that defines the scope of work for the software project manager.

b) Functional Decomposition

The functional decomposition of a software project is a division of the system into

its operational components as they are seen by the user. Functional decomposition

is part of the requirements phase of a project. The objective of this phase is to

define air the characteristics of the system from the user's perspective.

Let us consider an automatic bank teller system. The ability to communicate online

between the remote automatic tellers and the bank's central computer in order

to provide updated account information is a functional characteristic or the

system.

This will usually be defined during the requirements phase of the development

cycle. However, the method of transmission between the automatic teller and the

central computer is not a functional characteristic of the system, as this is internal

to the design and implementation of the system and is not apparent to the user.

The method of transmission, including the communications protocol, will usually

be defined during the design phase of the development of the system.

Figure 3 presents an example of the functional decomposition of an automatic

bank teller system into lower levels of functional components. In Fig. 3 we have

determined that there will be a customer data base, which could be viewed as a

design decision.

Software Project Management (CS615)

268

© Copyright Virtual University of Pakistan

This is unavoidable. The functional decomposition is rarely completely devoid of

all design considerations. As we will see, the functional decomposition is often a

starting point for the initial design of the system.

Figure 3: Automatic teller system - functional decomposition diagram

Just as the requirements phase precedes the design phase, so the functional

decomposition of a software system will usually precede the design

decomposition.

The functional decomposition will often provide much of the information

necessary for the subsequent division of the system into the implementation

components.

In fact, the functional decomposition is often a good place to start when designing

a software system, as the major functional components of a system will often

correspond to the initial division of the system into subsystems or high level

components.

Automatic

Bank teller

System

Automatic

Teller

Services

Central

Computer

Services

User

Services

Central

Computer

Query and

Update

Teller

Machine

Interface

Functions

Report

Generator

Customer

Data base

Manager

Operator

Services

Software Project Management (CS615)

269

© Copyright Virtual University of Pakistan

c) Design Decomposition

The design decomposition of a software system is a division of the system into

lower level components that coincide with the actual software components of the

system. In a full design decomposition of a software system, the lowest

components correspond to programming modules (usually procedures,

subroutines or program functions).

The work breakdown structure (WBS) is the decomposition of a software project

into low level work tasks.

An important point to remember is that in design decomposition, only the lower

level components are actually implemented. Higher level components represent a

group of lower level components.

Design decomposition basically produces two types of system component:

• high level components and

• low level modules

Different software development standards use different terminology to identify

the various levels of decomposition.

Figure 4 presents an example of the design decomposition of an automatic bank

teller system into lower levels of design components. On the third level, the

Automatic teller component decomposes into the Hardware interfaces, and the

Teller logic. The next level may then decompose the Hardware interfaces into the

Keyboard driver, the Display driver, the Printer, driver and the Beeper. At this

level, these drivers may represent actual software modules.

Software Project Management (CS615)

270

© Copyright Virtual University of Pakistan

Figure 4: Automatic teller system -design decomposition diagram

A fully decomposed system, with all its low level components, is not always easy

to grasp. This is especially true during the presentation of the system at a project

review, when the system needs to be quickly understood by people who have not

been involved in its design.

On such occasions, the stepwise refinement technique is a convenient method for

gradually presenting progressive detail by initially showing the first

decomposition level, and then slowly revealing subsequent levels. This is

demonstrated in figure 5.

At a convenient intermediate decomposition step we can divide the design in two:

the upper levels and the lower levels. This is used particularly when the design

phase is implemented in two distinct stages: top level design and detailed design

(see Fig.5).

Automatic

Bank teller

System

Wide area

Network

Interface

Automatic

Teller

Central

Computer

Teller

Communications

Interface

Central

Computer

Communications

Interface

Hardware

Interfaces

Teller

Logic

Keyboard

Driver

Display

Driver

Printer

Driver

Beeper

Driver

Customer

Data base

Manager

Teller

Interface

Logic

System

Component

1

Component

2

Component

3

Software Project Management (CS615)

271

© Copyright Virtual University of Pakistan

Initial top level decomposition

Intermediate level decomposition – top level design

Low level decomposition – detailed design

Figure 5: Software decomposition by stepwise refinement

System

Component

1

Component

2

Component

3

1.1 1.2 2.1 2.2 2.3 3.1 3.2

System

Component

1

Component

2

Component

3

1.1 1.2 2.1 2.2 2.3 3.1 3.2

Software Project Management (CS615)

272

© Copyright Virtual University of Pakistan

d) Develop Project Tasks

WBS tasks are developed by asking, “What tasks need to be done to accomplish

the project objective?” The choice of WBS structure is subjective and reflects the

preferences and judgment of the project manager.

As levels of the WBS become lower, the scope, complexity, and cost of each

subtask become smaller. The lowest level tasks, or work packages, are

independent, manageable units that are planned, budgeted, scheduled, and

controlled on their own.

As efforts of similar scope and type are planned, the basic WBS tasks remain

fairly similar, but each project requires a specific set of tasks that address the

uniqueness of the project's requirements. Certain top level elements, such as

project management, are included in the WBS of every project, regardless of its

type, size, or complexity. Other items, like installation, may not apply to every

project.

The initially developed WBS evolves over the course of the planning. It is highly

probable that it will look quite different as the scheduling, estimation, and

resource allocation portions of the plan are completed.

One of the difficult parts of talking about IT projects generically is the wide range

of such projects. Typically, in a small project, there is a single project

development phase.

In large or complex systems, however, there are often multiple development

phases, where different functional requirements are met.

Sometimes these phases are driven by the need to achieve certain levels of

functionality prior to the availability of the complete system.

Other times, the phases are defined to partition the development effort and to

reduce the risks associated with larger project efforts.

Software Project Management (CS615)

273

© Copyright Virtual University of Pakistan

LECTURE # 36

7. Work Breakdown Structure

7.8 WBS- Major Steps

e) Define Project Development Phases

For large systems, the decomposition of the system into smaller components

needs to be done early in the planning cycle.

The rationale for the decomposition must be known, otherwise, different results

derived from different reasons for the system decomposition may occur.

For example, if a phase is defined to accommodate user needs, the phase may

cross multiple functional areas of the system. If, on the other hand, a system is

divided into phases simply to reduce risk, a functional division might occur where

the phases represent completion of entire functional areas of the system.

The way in which the phases are handled, differs with each application. Often,

phases are handled as top level WBS elements, with tasks associated with each

phase defined.

f) Define Task Relationships

If a project is broken down into phases, be sure that the WBS reflects this. The

WBS structure denotes a hierarchy of task relationship.

Subtask completion eventually rolls up into task completion, which ultimately

results in project completion.

There can, however, also be relationships between tasks that are not within the

outlined hierarchy.

These relationships need to be noted, and the ultimate structuring of the tasks

optimized to favor a minimum of horizontal dependencies and relationships. If the

tasks are not organized efficiently, it becomes difficult to schedule and allocate

resources to the tasks.

The project scope of work is an iterative process that is generally done by the

project team with the use of a Work Breakdown Structure (WBS), allowing the

team to capture and then decompose all of the work of the project.

Software Project Management (CS615)

274

© Copyright Virtual University of Pakistan

A WBS is a deliverable-oriented grouping of project components that organizes

and defines the total scope of the project; work not in the WBS is outside the

scope of the project.

As with the scope statement, the WBS is often used to develop or confirm a

common understanding of project scope. Each descending level represents an

increasingly detailed description of the project deliverables.

A WBS is normally presented in chart form, however, the WBS should not be

confused with the method of presentation—drawing an unstructured activity list

in chart form does not make it a WBS.

g) Defining Deliverables

Deliverables associated with each task are shown in the WBS and are reflected in

the Deliverables portion of the Project Plan. A sample of a Deliverables template

is shown next. All deliverables are listed as they are identified.

As the schedule is completed, the due date is filled in, and responsibility for the

deliverable is assigned as it is known (typically when the organization chart is

defined). The date delivered is a field that is filled in as deliveries are made.

Over the course of the project, a comparison of the due date and the date delivered

provides a metric for how well deliverable dates are met by the project team.

While the deliverables list is a compilation of information identified in the WBS

and the project schedule, it is useful to maintain a separate list since deliverable

completion can be a key metric of project progress. Separate tracking of

deliverables can help keep a project on track. It also serves as a useful

communication tool with both stakeholders and the project team.

Product

Name

Due

Date

Date

Delivered

Author/

POC

Requirement

Specification

4/1/96 4/1/96 ABC

Design Specification 8/1/96 XYZ

Test Plan 8/1/96 DEF

Implementation Plan 11/1/96 …

Software Project Management (CS615)

275

© Copyright Virtual University of Pakistan

Source Code 12/1/96 …

Test Report 1/30/97 …

h) Creating a Work Breakdown Structure

A project can be compared to a large system. A large system consists of multiple,

independent subsystems that achieve a common goal. Similarly, a project consists

of small, independent tasks.

Each task can be subdivided into sub tasks. Fro example, in a general software

project, a task is to perform project analysis. You may also consider studying the

organizational objectives and preparing a project proposal to present to the client.

Therefore, in a project analysis task, there are three subtasks. A subtask is also

known as a work package. A work package is a unit-level entity in a project

system.

You can create a WBS by following the three steps listed below. These are

general steps, and they can vary in relation to an individual or an organization.

a) Brainstorm to arrive at board tasks for a project

b) Refine the board tasks

c) Categorize tasks into logical task headers

a) Brainstorming to Arrive at Broad Tasks

The first step in creating a WBS is to organize a meeting of all senior managers,

system analysts, and prospective developers. The objective of the meeting is to

brainstorm and come up with a set of broad tasks that need to be performed in a

project. During the brainstorming session, you can make a note of all possible

tasks.

Subsequently, the feasibility of each task is assessed. In addition, any conflict of

common tasks can be eliminated. To enable you to perform this activity better,

you can arrange tasks as and when they are brainstormed.

For example, XYZ Inc. conducts a brainstorming session to divide the tasks into

multiple subtasks that are performed during the analysis phase of a project.

During the session the project managers and the analysts come up with tasks on

the basis of prior project experience. These include tasks such as determining the

scope of a project, drafting the software specifications, and securing resources for

the project.

Software Project Management (CS615)

276

© Copyright Virtual University of Pakistan

Some additional tasks are also determined based on client requirements. Preparing

the initial project budget and estimating the approximate project timeline are

examples of such tasks. In addition, personnel responsible to complete each task

are also determined.

The subtasks are subsequently arranged in the order in which they are executed.

Figure 6 depicts the subtasks in the analysis phase. Note that after a questionnaire

is prepared, you can either arrange to meet the client or document the feedback

collected by the questionnaire. It is clear from the figure that preparation of the

SRS document can begin only after the preceding three tasks are complete.

Figure 6: WBS Activity

Dividing a main task into multiple subtasks also enables you to estimate the

duration and the effort required for individual tasks.

Subsequently, at the end of the phase, you can evaluate the actual effort and

duration. This helps you compare the estimated values with the actual values and

prepare a schedule for the subsequent phases.

The duration of each task affects the total duration of a phase. This, in turn,

affects the schedule of the subsequent phases. You can make similar deductions

while comparing the estimated costs with the actual costs of a task.

b) Refining Broad Tasks

Prepare a Client

questionnaire.

Arrange for

meetings with

li t

Document client

feedback

Prepare a Software

Requirements Specification

(SRS) document.

Software Project Management (CS615)

277

© Copyright Virtual University of Pakistan

In the second step of creating a WBS, you refine the list of tasks that was

compiled during brainstorming.

Refining the tasks may include adding more tasks or combining the existing ones.

During this step, you may also change the arrangement of tasks.

A change in the arrangement of tasks can occur on the basis of two theories of

WBS.

• Deliverable-based theory

• Project life-cycle-based theory

You use the deliverable-based theory when the deliverables of a project are more

important than its phases. This normally happens when the deliverables are

decided before the project begins.

However, if the phases of a project are completely defined, you use the project

life-cycle-based theory. You can use the project life-cycle-based theory to arrange

the tasks in a project.

c) Categorizing Tasks into Logical Headers

Finally, after defining tasks and arranging them, you categorize each task into a

logical task header.

For example, preparing test plans and test cases and drawing up the test plans can

be categorized as Testing.

This activity provides another chance to ensure that you have not missed any task

during brainstorming.

In addition, you can also consult an expert such as a senior manager to review and

validate the tasks identified.

7.8 WBS Implementation

i. Implementation Strategy

When you set up a project WBS, think about how you will be using it later in the

project. Consider how you will organize the WBS, schedule format, manager

assignments, and charge numbers, in your early project planning. It will be

helpful if you can map the charge numbers, managers, and task groups to each

other. This will help you track costs and progress for each manager.

Software Project Management (CS615)

278

© Copyright Virtual University of Pakistan

If your project schedule will on MS-Project, you may want to insert "text"

columns into your schedule (Gantt View) for project charge numbers and

manager names.

Some project management environments have definite conventions for grouping

items in a WBS. The best method is to have a WBS that works for your particular

project environment. The WBS should be designed with consideration for its

eventual uses.

Your WBS design should try to achieve certain goals:

– Be compatible with how the work will be done and how costs and

schedules will be managed,

– Give visibility to important or risky work efforts,

– Allow mapping of requirements, plans, testing, and deliverables,

– Foster clear ownership by managers and task leaders,

– Provide data for performance measurement and historical databases, and

– Make sense to the workers and accountants

There are usually many ways to design a WBS for a particular project, and there

are sometimes as many views as people in the process.

Experience teaches that everyone takes a slightly different slice of the apple, so

make sure WBS arguments seeking metaphysical certainty are quickly brought to

closure.

ii. Methodology

– PM must map activities to chosen lifecycle as each lifecycle has different sets

of activities.

– Integral process activities occur for all Planning, configuration and testing.

– Operations and maintenance phases are not normally in plan (considered

post-project)

– Some models are “straightened” for WBS:

• Spiral and other iterative models

• Linear sequence several times

– Deliverables of tasks vary by methodology

7.9 Guidelines for decomposition of work tasks

Software Project Management (CS615)

279

© Copyright Virtual University of Pakistan

i. General Guidelines

– A WBS should be easy to understand. Some companies have corporate

standards for these schemes. Some top-level items, like Project Mgmt. are in

WBS for each project. Others vary by project

– What often hurts most is what’s missing. Break down until you can generate

accurate time & cost estimates. Ensure each element corresponds to a

deliverable.

– How detailed should it be?

• Not as detailed as the final MS-Project plan

• Each level should have no more than 7 items

• It can evolve over time

– What tool should you use?

• Excel, Word, Project

• Org chart diagramming tool (Visio, etc)

• Specialized commercial apps

– Re-use a “template” if you have one. Although each project is unique, WBS

can often be “reused” since most projects will resemble another project to

some extent.

• Ex: Most projects within a given organization will have the same or similar

project life cycles, and will thus have the same or similar deliverables required

from each phase.

– Many application areas or performing organizations have standard or semistandard

WBS s that can be used as templates.

• Ex: Financial Management System etc

– Identify major elements of the project. In general, the major elements will be

project deliverables and project management.

– Decide if adequate cost and duration estimates can be developed at this level

of detail for each deliverable.

– Identify constituent components of the deliverable. Constituent components

should be described in terms of tangible, verifiable results to facilitate

performance measurement.

– Verify the correctness of the decomposition: are the low-level items both

necessary and sufficient for completion of the decomposed item? Is each item

clearly and completely defined? Can each item be appropriately scheduled and

Software Project Management (CS615)

280

© Copyright Virtual University of Pakistan

budgeted?

– The WBS is not a decomposition of the software produced by the project. It is

a decomposition of the project itself, and includes such activities as

management, procurement, installation and, of course, software development.

– Each low level module may be assigned three basic work tasks:

• module design,

• coding and

• unit testing

– Additional development tasks such as prototyping, testing, and integration are

derived from the other development phases.

ii. A typical list of high level WBS tasks

Following table contains a typical list of high level WBS tasks to be included in

the formal WBS task list.

– This is not an exhaustive list of all project development tasks, and not all

projects will require all the tasks described.

– However, this table will be useful as a checklist to assist in locating tasks that

may have been overlooked.

Table: High level WBS structure tasks

Software development

Requirements analysis

Prototype development

Prototype specification

Prototype design

Prototype implementation

Design

Top level design

Detailed design

Implementation

Coding

Unit test

Integration

Software integration

Hardware/software integration

Testing

Alpha testing

Beta testing

Software Project Management (CS615)

281

© Copyright Virtual University of Pakistan

Acceptance

Installation / Maintenance

Error correction

Software enhancement

Management

Planning

Staffing

Administration and services

Budget administration

Personnel management

Quality assurance

Configuration management

Training / Procurement

Acquisition of development tools

Acquisition of system components (off the shell)

Equipment selection

Vendor selection

Ordering procedure

Inventory control

Documentation

Technical writing

Project publishing activities

Development documentation

Non-deliverable development documentation

Deliverable development documentation

Maintenance documentation / User documentation

iii. Management and Administration Tasks

– Non-development activities, such as high level management WBS tasks, are

standard, to a large extent, and any variance is determined by either the

magnitude of the project, or the introduction of a new management model.

– An example of a list of management WBS tasks appears in the following

Table.

– This list contains many of the most important management tasks required for

most software development projects.

– Those tasks that are mandatory for all projects are marked as such in the list.

Table: Management and administration tasks

Mandatory Management task

√ 1. Planning

√ 2. Preparation or estimates

Software Project Management (CS615)

282

© Copyright Virtual University of Pakistan

√ 3. Risk analysis and risk management

√ 4. Scheduling

5. Staffing

6. Budget analysis and administration

√ 7. Personnel management

√ 8. Task assignment

√ 9. Delegation of authority

√ 10. Assignment of development resources

11. Supervision of development equipment maintenance

12. Supervision and control of development

13. Organization of reviews and formal presentations

14. Establishment of standards and methods

√ 15. Quality assurance and control

√ 16. Configuration management and control

17. Supervision of subcontractors and vendors

√ 18. Higher management interface and coordination

19. Customer interface and coordination

√ 20. Reporting

21. Administration and services

– Note that budget analysis and administration is not a mandatory management

task, simply because not all projects administer their own budget. Some

organizations have a financial officer responsible for the administration of

project budgets.

– Customer interface is also not a mandatory management task because not all

projects have a customer. In the case of company internal projects, high level

management, together with the designated users of the system being

developed, play the role of customer. It is usually they who specify the initial

project requirements, and it is to them that the project manager must come for

final approval and for final system acceptance.

– Break down the work until accurate estimates of cost and resources needed to

perform the task are provided.

– Ensure that clearly defined starting and ending events are defined for the task.

This may be the production of a deliverable or the occurrence of an event.

– Verify that the lowest level tasks can be performed within a “reasonable”

period of time. Each state organization must define “reasonable.”

– If the time period to complete a task is too long, an accurate project status in

the implementation phase may not be possible.

– An industry standard rule of thumb is to make work packages that can be

Software Project Management (CS615)

283

© Copyright Virtual University of Pakistan

completed in timeframes of two weeks.

– Verify that people assigned to the project are all assigned a WBS task. Have a

firm rule: if the task is not on WBS, it is not worked on.

– The work breakdown structure and any support documentation should be easy

to understand.

– The work should not be subdivided arbitrarily to the lowest possible level.

Work breakdown structure elements at the lowest control level should

typically range from 0.5% to 2.5% of total project budget.

– Furthermore, you should be aware that the work breakdown structure can be

developed to reflect the trust that you have in specific line groups, by leaving

them the autonomy over specific areas of work.

– Finally, always remember that projects are dynamic working environments -

so try to maintain flexibility in the work breakdown structure.

– As a general guideline, no single functional decomposition should be selected

just because it was conceived first. The functional decomposition of a

software system may be substantially different from the design decomposition

of the system. However, a good functional decomposition will have taken into

account design as the next development phase, and will often be a good

starting point for the division of the system into high level design components.

The high level design components are then further decomposed into

successive lower levels that ultimately produce programming modules. A

good modular design produces small, simple, independent modules.

Software Project Management (CS615)

284

© Copyright Virtual University of Pakistan

LECTURE # 37

8. Scheduling

8.1 Understanding Schedule

i. Salient Features:

Fred Brooks, the well-known author of The Mythical-Man-Month [BRO95],

was once asked how software projects fall behind schedule. His response was

as simple as it was profound: "One day at a time."

The reality of a technical project (whether it involves building a hydroelectric

plant or developing an operating system) is that hundreds of small tasks must

occur to accomplish a larger goal.

Some of these tasks lie outside the mainstream and may be completed without

worry about impact on project completion date, Other tasks lie on the

"critical" path, these "critical" tasks fall behind schedule, the completion date

of the entire project is 'put into jeopardy,

The project manager's objective is to define all project tasks build a network

that depicts their interdependencies, identify the tasks that are critical within

the network, and then track their progress to ensure that delay is recognized

"one day at a time." To accomplish this, the manager must have a schedule

that has been defined at a degree of resolution that enables the manager to

monitor Progress and control the project.

Software project scheduling is an activity that distributes estimated effort

across the planned project duration by allocating the effort to specific software

engineering tasks.

It is important to note, however, that the schedule evolves over time. During

early stages of project planning, a macroscopic schedule is developed. This

type of schedule identifies all major software engineering activities and the

product functions to which they are applied.

As the project gets under way, each entry on the macroscopic schedule is

refined into a detailed schedule. Here specific software tasks (required to

accomplish an activity) are identified and scheduled.

Scheduling for software engineering projects can be viewed from two rather

different perspectives. In the first, an end-date for release of a computer-based

system has already (and irrevocably) been established.

Software Project Management (CS615)

285

© Copyright Virtual University of Pakistan

The software organization is constrained to distribute effort within the

prescribed time frame. The second view of software scheduling assumes that

rough chronological bounds have been discussed but the end-date is set by the

software engineering organization. Effort is distributed to make best use of

resources and an end-date is defined after careful analysis of the ware.

Unfortunately, the first situation is encountered far more frequently than the

second.

As a project manager, you need to assign durations to all activities and

monitor their progress.

You also need to plan the order in which the activities will be performed as

well as the start and end dates for each activity. In short, you need to create a

project schedule.

The plan includes not only the scheduling of development activities, but also

the scheduling of project resources, particularly people. To accomplish this,

the manager must have a schedule that has been defined at a degree of

resolution that enables the manager to monitor Progress and control the

project. The project schedule is one of the most important parts of the project

development plan.

The project schedule reflects the start dates and end dates for each activity in

the project. It also reflects the resources required to complete the activities. To

create a schedule, you can use project management tools.

To create a schedule, you can use project management tools, e.g.:

• Gantt charts

• Network-scheduling techniques

No matter how well the project schedule is prepared, that schedule is useless

unless it is adhered to. It is the project manager's responsibility to withstand

pressure and to assure that the project is developed in an orderly fashion,

according to the schedule. Whenever circumstances change, the project

schedule should then be updated to reflect the new situation.

ii. Need for Project Scheduling

Software project have a tendency to get out of control because of the multiple

activities that need to be monitored, tracked, and controlled. When a project

goes out of control, the original deadlines, the budget, and the effort required

overshoot the initial estimates. This not only impacts the product, but also the

credibility of the development team.

Software Project Management (CS615)

286

© Copyright Virtual University of Pakistan

iii. What Delays Software Projects

There are various reasons why a software project is delayed. Some of the

reasons are listed below:

• The initial estimate of the effort and resources required to complete the

software project was incorrect. (An honest underestimate of the amount of

effort and/or the number of resources that will be required to do the job).

• Changing customer requirements that are not reflected in schedule

changes.

• Known risks were not mitigated. (Predictable and/or unpredictable risks

were not considered when the project commenced).

• Technical difficulties surfaced during software product development.

(Technical difficulties could not have been foreseen in advance).

• Human difficulties, such as interpersonal problems and team attitude,

became unmanageable. (Human difficulties that could not have been

foreseen in advance, e.g., Miscommunication among project staff resulting

in delays).

• A failure by project management to recognize that the project is falling

behind schedule and a lack of action to correct the problem.

• The initial deadline set for the project was unrealistic. (An unrealistic

deadline established by someone outside the software development group

and forced on managers and practitioners within the group).

Aggressive (read “unrealistic") deadlines are a fact of life in the software

business Sometimes such deadlines are demanded for reasons that are

legitimate, from the point of view of the person who sets the deadline. But

common sense says that legitimacy must also be perceived by the people

doing the work.

iv. How to Prevent Delays

While most of the above reasons result in project delays, unrealistic deadlines

cause the maximum damage. Unrealistic deadlines are caused either by the

client wanting a quick delivery or the management wanting a return business

nom a client.

Software Project Management (CS615)

287

© Copyright Virtual University of Pakistan

However, unrealistic deadlines are the norm for software projects. You need

to resolve the conflict between an unrealistic deadline and the constraints of

the software development team.

As a project manager you need to balance the limited resources and the final

deliverable committed to the client. To do this, you can follow the points

listed below:

a) Study similar past projects for the method of dealing with similar

situations. Use the historical information to project time and effort

estimates for the current software project.

b) Use an incremental process model to create a schedule to deliver the

required functional module of the software product.

c) Present the schedule created on the basis of past projects to the client.

Explain the projected delays and the reasons for the same.

d) Present the incremental model as a strategy for developing the software

product.

All the strategies have their advantages and disadvantages. If the schedule

created using inputs from the past project does not help meet the deadline, you

can use the incremental model. In the incremental model, the strategy is to

deliver each module as and when it is completed. However, historical trends

show that clients opt for either strategy if provided reasonable time and effort

estimates.

8.2 Scheduling Fundamentals

i. Scheduling Basics

Only a small percentage of all the activities in a software project have a direct

impact on the on-time completion of the software project. Therefore, you need

to identify the activities that are critical to the completion of the project. In

addition, you ensure that all inputs are available to complete the critical

activities. This is where a software project schedule comes into the picture.

The goal of a software project schedule is to determine the duration of the

software project and the phases within the project. A software project

schedule enables you to distribute the estimated effort to be spent in

performing the critical activities.

There are a few basic principles that determine how a software project

schedule is created. To create a project schedule, first you group similar

activities together. Then, you determine the dependencies of the different

activities. Next, you allocate the estimated time and resources to each activity.

Finally, you define the roles and responsibilities and the output and validation

criteria.

Software Project Management (CS615)

288

© Copyright Virtual University of Pakistan

Some of the guidelines for creating a software project schedule are discussed

below:

a) Classification

b) Interdependence

c) Time and effort allocation

d) Validation criteria

e) Defined responsibilities and outputs

a) Classification

While managing a software project, you need to group similar tasks and

activities so that they are completed successfully. The primary tools used to

group similar tasks are the WBS and decomposition technique. Using these

tools, you can divide a software project into different phases. The phases can

be further subdivided into activities. The software project schedule is prepared

according to the arrangement of the phases.

b) Interdependence

As you have seen, a software project is composed of multiple phases and each

phase is composed of multiple activities. Although each activity is treated

separately, it is linked to other activities. As a project manager, you determine

the interdependence and sequence of activities. For example, some activities

can be completed without any inputs from other activities, whereas other

activities cannot start unless a preceding activity is completed.

c) Time and Effort Allocation

Each activity in a software project needs a certain amount of time and effort

for completion. To manage the project, you assign start and end dates to each

activity. You also need to allocate appropriate effort to each activity. Most

software projects operate with time and effort constraints. Therefore,

managing within the available resources is very important for a software

project manager.

d) Validation Criteria

You also determine the validation criteria for time and effort allocation in a

software project. Determining the validation criteria allows you to ensure that

the optimal level of resources is available for a particular activity. Suppose 5

people are assigned to an activity that requires an effort of 3.5 person days.

This means resources allocated are more than the actual requirement.

e) Defined Responsibilities and outputs

As a software project manager, you assign roles and responsibilities to all

people assigned to a software project. This defines the hierarchy in the

development team. You also define the outputs from each activity. This helps

in identifying the results expected at the end of every activity. Next, you link

the roles to the outputs. When each role is linked to the expected results, you

Software Project Management (CS615)

289

© Copyright Virtual University of Pakistan

can track each person's effort and the progress of each activity towards

closure.

Software Project Management (CS615)

290

© Copyright Virtual University of Pakistan

LECTURE # 38

8. Scheduling

8.3 Scheduling Tools

i. GANTT CHARTS

There are various tools that help you create a schedule. One of the simplest

project management tools used to represent the timeline of activities is the Gantt

chart.

Long before the advent of computers, Henry L. Gantt lent his name to a simple

and very useful graphical representation of a project development schedule.

The Gantt chart shows almost all of the information contained in the schedule

activity list, but in a much more digestible way. The schedule information is more

easily grasped and understood, and the activities can be easily compared. The

Gantt chart enables us to see at any given time, which activities should be

occurring in the project.

A Gantt chart has horizontal bars plotted on a chart to represent a schedule. In a

Gantt chart, you plot time on the horizontal axis and activities on the vertical axis.

You represent an activity by a horizontal bar on the Gantt chart. The position of a

horizontal bar shows the start and end time of an activity and the length of the bar

show its duration. You can have one look at the Gantt chart and make out the

progress of the project. Figure 1 displays a sample Gantt chart.

Software Project Management (CS615)

291

© Copyright Virtual University of Pakistan

Figure 1: Example Gantt Chart

In Figure 1, activity D starts on day 1 of the project. The planned duration of this

activity is 20 days. The planned duration is shown in a lighter shade on the Gantt

chart. This is done to differentiate planned duration from the current status of the

activity. In the case of activity D, the current duration of the activity is 19 days.

Therefore, activity D is still one day short of completion. This can be discerned

from the length of the gray and black bars. Activity C, planned for completion on

day 40, is much behind schedule. This can be observed from the smaller length of

the black bar in the Gantt chart.

To understand how you can use a Gantt chart to schedule a project, consider an

example. Table 1 display a set of activities in a software project and the start and

end time for each activity.

D

C

B

A

10 20 30 40 50 60

Time (Person days)

Activities

PLANNED

ACTUAL

Software Project Management (CS615)

292

© Copyright Virtual University of Pakistan

Table 1: Project Activities and Time Allocation Details

Tasks Time Allocation

(person days) Planned Start Planned End

Requirement analysis and project planning 10 01/01/2002 01/14/2002

Setting up the environment 6 01/01/2002 01/08/2002

Software construction 80 01/15/2002 05/15/2002

Unit testing 30 05/16/2002 06/28/2002

User training 5 07/22/2002 07/26/2002

System testing 15 07/01/2002 07/19/2002

User documentation 30 01/15/2002 02/28/2002

Data migration 20 01/15/2002 02/15/2002

Conducting user acceptance test 20 08/01/2002 08/31/2002

Using the data shown in the Table 1, you can create a Gantt chart. The Gantt chart

is displayed in Figure 2.

In Figure 2, the Gantt chart displays the week-wise status of a software project. A

vertical dotted line is drawn through the chart to represent the current date. This

Figure 2: Gantt Chart for Activities of Table 1

Software Project Management (CS615)

293

© Copyright Virtual University of Pakistan

line indicates the status of the project on a specific day. The left side of the line

indicates the tasks that are completed. On-going activities run across the line. The

future activities lie completely to the right of the line. After drawing the Gantt

chart you can extend the bars every week to a length proportional to the work

completed during the week. Therefore, the bars describe the status of the-project

at any point of time.

This process of creating a Gantt chart as discussed above is manual. Nowadays,

automated tools are available for creating Gantt charts. For example, you can use

Microsoft® ProjectTM 2000 developed by Microsoft to create a project schedule

automatically.

Figure 3 is another example of a Gantt chart. The symbols used in the chart are

widely accepted, though not standardized. The inverted triangle, for example, is

commonly used to represent a significant event, such as a major milestone.

The Gantt chart in Fig. 3 demonstrates the ease with which important schedule

information can be quickly perceived. We can immediately see that, except for the

maintenance phase, all phases overlap, and that from November to mid-December

1992 three high level activities overlap.

Major milestones

SRR = Software requirements review

POR = Preliminary design review

COR = Critical design review

TRR = Test readiness review

ATP = Acceptance test procedure

Software Project Management (CS615)

294

© Copyright Virtual University of Pakistan

Figure 3: High level Gantt chart -project development schedule.

More detailed charts can also include the names of the engineers assigned to each

activity, and the equipment that will be needed for each activity. This information

can be added next to the activity time lines in the graph, or as an inserted

reference table (similar to the list of major milestones in fig 10.1). Some

variations of the Gantt chart do include this type of information on the chart, but

this can cause clutter, which is contrary to the main objective of the chart; to

enable important schedule information to be grasped quickly.

It is also important to understand what Gantt charts do not provide. In a Gantt

chart, it is difficult to provide information on the amount of resources required to

complete each activity. A common mistake is to conclude that if five engineers

are assigned to integration, and the integration activity starts in mid-September

1992 and ends in mid-January 1993 (four months), then integration requires 20

work months. In fact, integration may start with only one engineer, with one more

joining during the second month, and the remaining three engineers joining during

the third month. The integration team may then be reduced to three engineers

during the fourth integration month.

Figure 3 includes only seven activities. As more detail becomes available, lower

level activities can be included on the chart. When the chart has more activities

than it can reasonably carry (a subjective decision), additional charts may be

Jan Feb Mar Apr May Jun Jul Aug Sep Oct Nov Dec Jan Feb Mar Apr

May Jun

SPR

CDR

ATP

TRR

PDR

1992

1993

Major milestones

SRR = Software requirements review

PDR = Preliminary design review

CDR = Critical design review

TRR = Test readiness review

ATP = Acceptance test procedure

Requirements

analysis

Top level design

Detailed design

Implementation

Integration

Testing

Maintenance

Software Project Management (CS615)

295

© Copyright Virtual University of Pakistan

added. For example, the design activity can be presented on a separate Gantt chart

(see Fig. 4).

Figure 4 presents both high and low level activities. For example, 'Integrate phase

1 model' contains three low level activities: 'Integrate executive', 'Integrate

operating system' and 'Integrate user interface'. This provides the continuity link

between the detailed Gantt chart (Fig. 4) and the higher level chart (Fig. 3).

Figure 4: Detailed Gantt chart -integration schedule

Note that each period of one month in Fig. 3 has been divided into four weeks.

Though not completely accurate, this is a common approximation, used also in

estimation and apart from being convenient; it also provides some slack for minor

scheduling adjustments.

Similar detailed Gantt charts can be prepared for each of the major project

development phases. Non-development activities will also appear on the Gantt

chart, such as 'Procurement of development tools', or 'Market research'. This is

particularly useful when certain development activities are dependent on other

non-development activities, such as the procurement of development tools (e.g. a

compiler) that need to be completed before the implementation activities can

begin. In cases where such dependent relationships may have been overlooked,

they will often emerge from' a review of the Gantt chart. This type of dependence

Sep 15 Oct Nov Dec Jan

1992 1993

TRR

Set up

integration site

Integrate phase

I model

Integrate

executive

Integrate

operating

system

Integrate user

interface

Integrate phase

II model

Software Project Management (CS615)

296

© Copyright Virtual University of Pakistan

between activities is best presented in another type of chart, called a Network

precedence chart or a PERT chart.

Network Scheduling Techniques

To plan the activities in a project, you can also use network-scheduling

techniques. Network scheduling techniques use network schedules to trace the

completion of predetermined activities.

There are two basic network-scheduling techniques:

• PERT and

• CPM

You can use either of these techniques to analyze a wide variety of projects. Each

technique depicts a project as a sequence of activities. This helps you perform an

analysis of individual activities or the complete project.

The network-scheduling techniques also enable you to analyze the dependencies

that exist between the activities.

Using PERT and CPM, individually or in combination, helps you complete a

project on time. By using these techniques, you can determine the latest time by

when an activity should start to be completed on time.

Despite the different approaches followed by PERT and CPM, both techniques

have some common components. These include:

a) Activities

b) Nodes

c) Network

d) Critical path

a) Activities

Activities are the basic building blocks of network schedules. An activity is

defined as a task that consumes time, effort, money, or any other resource. It is

necessary to specify all the activities of a project by breaking down a project into

several steps.

You need to define the steps in such a way that they are distinct, homogeneous

tasks for which you can estimate resource requirements.

Each activity is represented on a network schedule by using an arrow with its

head indicating the direction in which the project will progress. Each activity is

identified by a description or an alphabet. In addition, the estimated duration of

Software Project Management (CS615)

297

© Copyright Virtual University of Pakistan

1 2

each activity is placed below the activity. Figure 5 shows an activity with

expected duration of 15 days.

A

15 Days

Figure 5: An Activity

After identifying all the activities in a project, it is necessary to schedule them.

This enables you to arrange the activities in the order of completion. You

sequence the activities based on their types.

The different activities that are possible in a project are predecessor, successor,

and concurrent activities.

Predecessor activities need to end before the next can begin. After a predecessor

activity is completed, the successor activity becomes the predecessor for another

activity. However, unlike the predecessor arid successor activities, the concurrent

activities can be completed simultaneously with other activities.

Some activities in a project, irrespective of whether they are predecessor,

successor, or concurrent, may depict a float period. Float is the amount of time by

which an activity may be delayed without affecting the completion date of the

entire project. However, the complex dependencies that exist between activities

result in sequencing constraints for projects. To a large extent, these constraints

limit the flexibility that you may otherwise have in project planning.

b) Nodes

A node on a network schedule is that point in time at which an activity either

begins or ends. The point where an activity begins is called a tail node and the

point where it end is called its head node. On a network schedule, a circle

represents a node. A number identifies each node in a network schedule. Figure 6

represents the tail and head nodes for the activity of interviewing clients in a

project.

Figure 6: An Activity Connecting Two Nodes

c) Network

Software Project Management (CS615)

298

© Copyright Virtual University of Pakistan

1

2

3

4

5

1

2

3

4

5

A network is the graphic representation of the activities in a project. It depicts all

the activities and nodes in the project. On- a network, the arrows terminating at a

node need to be completed before the following activity can begin. Figure 7

shows a sample network consisting of five activities in a project.

Figure 7: Sample Network Schedule

d) Critical Path

The critical path is the longest path through a network. It consists of those

activities that cannot be completed concurrent1y. In other words, the critical path

represents the maximum duration for a project. You can determine the maximum

duration by adding the duration of each activity on the critical path. Typically, a

double line in a network schedule represents the critical path for that project.

Figure 8.6 shows the critical path for a network.

1

2

3

4

5

6

Software Project Management (CS615)

299

© Copyright Virtual University of Pakistan

1 2

3

Figure 8: Network Schedule with Critical Path Identified

All the activities on the critical path are critical for a project. If an activity on the

critical path is delayed, the entire project is delayed by the same amount of time.

You need to monitor the activities on the critical path because the project depends

on the successful completion of these activities. If required, additional resources

can be applied to these activities to shorten the project duration. However, some

of these activities may also depict a float period.

8.6 Rules for Creating a Network Schedule

There are a few basic rules that are followed while constructing a network

schedule.

1. Each activity has a preceding node and a succeeding node.

2. Each node has a distinct number. As a convention, the number that is assigned

to the head of the arrow is greater than the number that is assigned to the tail.

3. The network schedule has no loops. For example, in Figure 9, activity 1 is the

predecessor of both activity 2 and activity 3. This places activities l, 2, and 3

in a loop.

Fig 9: A loop is not permitted

4. Each activity has a unique preceding and succeeding event associated with it.

For example, in Figure 10, activities A and B have common preceding and

succeeding events associated with them. This is not allowed in a network

schedule.

Software Project Management (CS615)

300

© Copyright Virtual University of Pakistan

1 2

3

4

Figure 10: Activities with Common Preceding and Succeeding Events

At times, you need to introduce a dummy activity in a network schedule. This is

an imaginary activity that enables the network schedule to display parallel

activities. For example, in Figure 11, consider A and B as two parallel activities

that can be executed simultaneously. Both A and B must end so that activity C

can begin. A dummy activity is introduced as a dashed arrow to mark the start of

activity C. The dummy activity is introduced to show the dependency between

activities in the network schedule and does not have a description or duration.

B

A C

Figure 11: Dummy Activity

1 2

A

B

Software Project Management (CS615)

301

© Copyright Virtual University of Pakistan

8.7 Using PERT to Schedule a Project

PERT was developed in 1957 to cater to the needs of the Polaris Fleet Ballistic

Missile project of the US government. PERT uses a probabilistic approach to time

estimates. You normally apply it to projects that are characterized by uncertainty.

For example, in a complex software project where you require research to identify

activities. PERT allows you to account for the uncertainties that are common to

most software projects. PERT uses the network schedule to represent a project

schedule while taking the uncertainties into account.

i. Time Estimates in PERT

PERT is a probabilistic technique that uses three time estimates: It assumes

that activity times are represented by a probability distribution. To finish an

activity, it bases the probability distribution of activity time on three time

estimates:

• Optimistic time

• Pessimistic time

• Most likely time

The optimistic time is the shortest time period within which an activity can

end if everything goes well.

The pessimistic time is the time that an activity takes to complete if

everything that can go wrong goes wrong. This is the longest time that an

activity can take to complete.

The most likely time is the estimate of the normal time that an activity takes to

complete.

From these three estimates, you derive the expected time to complete an

activity. The expected time is also referred to as the average time for the

activity.

To calculate the expected time for each activity, you use the following

equation:

6

4 0 p m

e

T T T

T

+ +

=

Where Te is the expected time, T0 is the optimistic time, Tm is the most likely

time, and Tp is the pessimistic time required to complete an activity.

Software Project Management (CS615)

302

© Copyright Virtual University of Pakistan

According to this equation, you calculate the expected time for an activity as a

weighted mean of the optimistic, most likely, and pessimistic times. The

weights attached to these times are 1, 4, and 1, respectively.

Consider the example of the activities in a software project as given in Table

1. The time estimates provided in Table 1 are the estimated times for each

activity. Table 2 provides the break-up of the estimated times into the

optimistic, pessimistic, and most likely times for each activity.

Table 2: Optimistic, Most Likely Time, and Pessimistic Estimates for Activities

Tasks

Optimistic Time

Estimates

(person days)

Most Likely

Time Estimates

(person days)

Pessimistic

Time Estimates

(person days)

Requirement analysis and project planning 7 10 13

Setting up the environment 3 6 9

Software construction 48 83 100

Unit testing 20 28 33

User training 4 5 6

System testing 10 15 20

User documentation 23 28 45

Data migration 18 18 30

Conducting user acceptance test 14 21 22

Using the formula for calculating estimated time for an activity, the estimated

time for requirements analysis and project planning is:

persondays T e 10 6 / 60

6

13 ) 10 ( 4 7 = =

+ +

=

Similarly, you can calculate the estimated times for all the activities in Table 2

using the above formula.

Figure 12 shows the PERT network schedule created using the time estimates.

Software Project Management (CS615)

303

© Copyright Virtual University of Pakistan

Figure 12: PERT Network Schedule for Activities

ii. PERT packages and enhancements

Some enhanced versions of the PERT chart support additional planning

activities, such as personnel assignment, resource allocation and cost analysis.

The chart can then draw attention to situations where personnel are assigned

more responsibilities than they can handle, or where allocation of resources

conflicts.

An interesting adaptation of PERT, called flow graph representation, which

was developed by Riggs and Jones (1990), uses precedence networks to

perform project life cycle cost analysis. The flow graph technique analyzes

project costs based on relationships between quantities, unit cost, time

variables, staffing costs and learning etc., all of which are represented on the

PERT- like chart.

The flow graph representation technique places a significant amount of

information on the network graph. This information, just like the basic PERT

information, must be kept constantly updated. A small change to a large PERT

chart can require the complete redrawing of the chart and the recalculation of

the critical path. The resulting tedium does not promote much enthusiasm for

10

User

Documentation

User

Acceptance

Testing

Requirements

Analysis and

Project

Planning

2

1

3

4 7

5

6

8

9

10

Software

Construction Unit Testing

System

Testing

User Training

Data

Migration

20

6

80 30 15

20 5

30

Node Activity

Number

Dummy

Activity

Software Project Management (CS615)

304

© Copyright Virtual University of Pakistan

keeping the chart updated. For this reason, many computerized PERT utilities

have been developed.

PERT software packages have been available for many years, but it is only

during the past few years that good professional PERT packages have become

available on PCs and other small computers. These packages take much of the

tedium out of the preparation of PERT charts, and also come with additional

features such as various planning analyzers for activity assignment, what if

scenarios and resource allocation.

Computer utilities have been developed to perform flow graph representation

analysis which produces scheduled costs for major project activities2. These

utilities have proven invaluable for project managers and release managers

from laborious desk work, providing them with more time to actively manage

the project.

Software Project Management (CS615)

305

© Copyright Virtual University of Pakistan

LECTURE # 39

9. Risk and Change Management

9.1 Risk is defined as the possibility of loss. It is the inability to achieve program

objectives within defined cost, schedule, and technical constraints. Risk

management is a set of actions that helps the project manager plan an approach to

deal with uncertain occurrences.

A software project encounters two types of risks, development process risks and

product- related risks. Some of the development process risks are developer

errors, natural disasters, disgruntled employees, and poor management objectives.

Some project related risks are incomplete requirements, unclear project

deliverables and objectives, and complexity of the product.

The steps of risk management involve risk identification, risk analysis, and risk

mitigation. Risk identification involves identifying risks. Risks are identified after

discussion with team members about the requirements documents, available

technology, resources, and other project-related factors.

Contingency planning involves maintaining an alternative plan if the original plan

fails. Contingency plans are put to use when risks become a reality.

What is it? Risk analysis and management are a series of steps that help a

software team to understand and manage uncertainty. Many problems can plague

a software project A risk is a potential problem - it might happen, it might not But

regardless of the outcome, it's a really good idea to identify it, assess its

probability of occurrence, estimate its impact, and establish a contingency plan

should the problem actually occur.

Who does it? Everyone involved in the software process – managers, software

engineers and customers - participate in risk analysis and management

Why is it important? Think about the Boy Scout motto: "Be prepared" Software is

a difficult undertaking. Lots of things can go wrong, and frankly, many often do.

It's for this reason that being prepared, understanding the risks and taking

preventive measures to avoid or manage them is a key element of good software

project management.

What are the steps? Recognizing what can go wrong is the first step, called -

risk identification. Next, each risk is analyzed to determine the likelihood that it

will occur and the damage that it will do if it does occur. Once this information is

established, risks are ranked by probability and impact. Finally, a plan is

developed to manage those risks with high probability and high impact.

Software Project Management (CS615)

306

© Copyright Virtual University of Pakistan

What is the work product? A risk mitigation monitoring and management

(RMMM) plan or a set of risk information sheets is produced. How do I ensure

that I've done it right? The risks that are analyzed and managed should be derived

from thorough study of the people, the product, the process and the project. The

RMMM should be revisited as the project proceeds to ensure that risks are kept up

to date. Contingency plans for risk management should be realistic.

9.2 Risk Management Concepts

Ever wondered why people insure their lives, their homes, their cars, or their

valuables? Suppose your house, along with all the valuables, is burgled. You will

be definitely disheartened. However, you will suffer less if all your valuables are

insured. At times such as these, you realize the importance of planning in advance

for the uncertain events in your life. Just as you plan for unforeseen events in your

life, project managers also need to prepare for uncertainties affecting projects. All

project management skills of a project manager can fall in the face of

uncertainties and unplanned problems.

Robert Charette [CHA89] presents a conceptual definition of risk:

• First, risk concerns future happenings, Today and yesterday are beyond active

concern, as we are already reaping what was previously sowed by our past

actions, The question is, can we, therefore, by changing our actions today,

create an opportunity for a different and hopefully better situation for

ourselves tomorrow

• This means, second, that risk involves change, such as in changes of mind,

opinion, actions, or places

• Third risk involves choice, and the uncertainty that choice itself entails, thus

paradoxically, risk, like death and taxes, is one of the few certainties of life,

When risk is considered in the context of software engineering, Charette's three

conceptual underpinnings are always in evidence. The future is our concern –

what risks might cause the software project to go awry? Change is our concern -

how will changes in customer requirements, development technologies, target

computers, and all other entities connected to the project affect timeliness and

overall success? Last, we must grapple with choices - what methods and tools

should we use, how many people should be involved, how much emphasis on

quality is "enough"?

Any project can encounter uncertainties in the form of increased costs, schedule delays,

and diminished qualities. Unless tackled, these uncertainties can lead to major project

disasters. The uncertainties encountered during project execution are the potential project

risks. Every software project has to grapple with the new risks threatening information

Software Project Management (CS615)

307

© Copyright Virtual University of Pakistan

security along with the conventional risks, such as hardware failure, time and cost

escalation, defects, or resource crunch. Risk can be defined as the possibility of loss. Risk

arises due to the inability to achieve objectives within defined cost, schedule, and

technical constraints. Risk has two components. The possibility of not achieving a

particular outcome is one, and the result of failing to achieve the outcome is the other.

The former is the probability of loss, and the latter is the loss. Software project

management deals with managing both these components of risk.

According to the risk management guru Barry Boehm, “Risk management focuses the

project manager’s attention on those portions of the project most likely to cause trouble

and compromise participants’ win conditions.” In other words, risk management is a set

of actions that helps the project manager plan to deal with uncertain occurrences. It is

through risk management that project managers assess risks and manage to reduce risks

to an acceptable level.

Software risk management is not about managing risks faced by a software organization.

Here, the focus is on managing risks encountered during software development process.

Therefore, the concern is about managing the future of a software project.

In this chapter, you will 1ook at the unforeseen events that might affect a software

project. You will also learn about the steps for managing and mitigating software project

risks.

Types of Risks

To be able to manage project risks, you must first understand what constitutes, a risk. All

uncertain occurrences are not risks. Only those occurrences that have an adverse impact

on the progress of a project are risks to the project. Risk is not a bad thing. Risk is bad

only when it results in loss for an organization. Unless there is a potential for loss, there

is no risk. Moreover, loss can be interpreted as either a bad outcome or a lost opportunity.

The tendency of most project managers is to jump at the statement this is a risk.

However, the desired reaction is to pre-empt all possible outcome and plan for them.

Project risks can be broadly categorized into development process risks and product risks.

Development Process Risks

The risks encountered during product development are categorized as development

process risks. These comprise developer errors, natural disasters, disgruntled employees,

and poor management objectives.

Developer errors could be attributed to poor training due to budgetary constraints and

inadequate skills and software tools. Ergonomic problems, environment problems, and

interruptions or distractions at office also account for developer risks. Other risks in this

category include problems in personnel acquisition and retention.

Similarly, natural disasters such as flood, cyclone, fire, storm, and snowfall are also risks

to a project.

Disgruntled employees can also become a risk to an organization. For example, a sacked

employee can use password snuffers to gain unauthorized access. A dismissed person can

Software Project Management (CS615)

308

© Copyright Virtual University of Pakistan

flood the system with senseless messages. A disgruntled employee can also try to

sabotage the project work by destroying files and programs.

A poorly defined management objective is another development process risk. If the

language in the management objective is ambiguous and not stated clearly, the risk

management program will not function properly. Narrowly focused and changing

objectives that are not updated can also be counted as risks. Lack of contingency plans,

incomplete cost estimates, and unrealistic schedules are also potential risks in a project.

Similarly, unrealistic performance standards are also potential risks to the development

process. Other possible risks include contractual risks, technological risks, and

inadequate documentation of other concurrent projects.

Product Risks

Product risks crop up in the form of changing requirements during product development.

Incomplete and unclear requirements are a risk to the product during development.

Similarly, problems in meeting design specifications can also be categorized as risk to

product development.

Risks could arise if the project deliverables or objectives are not clearly defined or if

technical data is missing. The possibility of several alternatives at any given time during

the project is also a cause of concern. If errors are not recognized during the design

phase, they could turn into risks for the project. Similarly, risks could arise due to the size

and complexity of the product or while achieving client acceptance of the product.

Note:

The key idea in risk management is not to wait for a risk to materialize and

become a problem. The objective of risk management is to ensure that for each

perceived risk, you know well in advance how to tackle it.

Risk Management Process

Project Risk Management includes the processes concerned with conducting risk

management planning, identification, analysis, responses, and control on a project. The

objectives of Risk Management are to increase the probability and impacts of positive

events and decrease the probability and impacts of events adverse to project objectives.

The process of risk management begins during the analysis phase of software

development life cycle. However, the actual process of managing risks continues

throughout the product development phase. Risk management is a dynamic process

because it deals with the activities that are yet to happen. Risk management has a twofold

agenda. First, deciding actions for preventing risks from happening, and second,

deciding actions for tackling risks that materialize. Therefore, risk management is all

about pre-empting a risk, coming up with a plan for resolving the risk, and finally

executing the plan.

Figure 6.1 displays the steps of the risk management process. Formally, articulated, risk

management process consists of three steps:

1. Risk identification

2. Risk analysis

Software Project Management (CS615)

309

© Copyright Virtual University of Pakistan

Risk Management

Risk Identification Risk

Analysis

Risk

Mitigation

Risk Probability

Risk Impact

Risk Factor

Risk Avoidance

Risk Monitoring

Contingency Planning

3. Risk mitigation

Figure 6.1: Risk Management Process

Risk Identification

In this step, the project manager gathers information about the potential risks in the

project. The project manager plans the strategies for avoiding risks or controlling them.

The project team conducts brainstorming sessions and discussions among team members

about the requirements document. They discuss the available technology, manpower,

prevailing environment, and all project-related factors. The project manager picks up the

thread from these and creates a risk log. After the risk log is prepared, the project

manager calls a meeting within the team and technical experts to discuss the risk log and

the mitigation plans. An effective way of identifying' risks is using a questionnaire.

Table 6.1 displays a sample risk identification questionnaire.

Table 6.1: Sample Risk Identification Questionnaire

SN Risk Description Yes/No/Not Applicable

(NA)

A. Product Engineering

1) Are requirements changing continuously during

product development?

2) Do the changing requirements affect each of the

following:

Quality

Functionality

Schedule

Integration

Design

Testing

Software Project Management (CS615)

310

© Copyright Virtual University of Pakistan

3) Are the external interfaces changing?

4) Are the requirements missing or incompletely

specified?

5) Are there any missing requirements?

6) Can these requirements be incorporated into the

system?

7) Does the client have unwritten requirements or

expectations?

8) Is there a way to capture these requirements?

9) Are requirements unclear or in need of interpretation?

10) Are you able to understand the requirements as

written?

11) Will the requirements lead to the product the client

wants?

12) Are there any requirements that may not specify what

the client really wants?

B. Product Design

1) Do you encounter problem in meeting functionality

requirements?

2) Are there any specified algorithms that may not

satisfy the requirements?

3) Will the design and/or implementation be difficult to

achieve?

4) Are there any requirements or functions that are

difficult to design?

C. Reusability

1) Are you reusing the program?

2) Do you foresee any problems in documentations?

3) Do you foresee any problems in performance?

4) Do you foresee any problems in functionality?

The sample questionnaire in Table 6.1 includes an exhaustive list of risks that might be

encountered during the progress of a project. The answers to the questions in the risk

identification questionnaire enable the project manager to estimate the impact of risks. In

the sample questionnaire Table 6.1, the risks are categorized under product engineering,

product-design, and reusability. From this table, you obtain a list of risks that are relevant

to each category. You compare the information obtained from this table with past results

and estimate the criticality of risk. In short, during risk identification, you obtain answers

to the following queries:

• Why is the risk important?

• What information is needed to track the status of the risk?

• Who is responsible for the risk management activity?

• What resources are needed to perform the activity?

• What is the detailed plan to improve the risk and / or mitigate it?

Software Project Management (CS615)

311

© Copyright Virtual University of Pakistan

Risk Analysis

After identifying the risks, the project manager needs to analyze the risks. Uncertainty

and loss are the two characteristics of risk. The uncertainty factor in risk means that the

unknown event mayor may not happen. While analyzing risks, the project manager needs

to quantify the level of uncertainty and the degree of loss. Based on this, the project

manager plans schedules and costs. During analysis, information on risk is converted into

information on decision-making. Analysis provides the basis for the project manager to

work on the “right” risks.

Table 6.2: Risk Analysis Table

Risk

Description

Probability of

Occurrence

(0 – 1)

Impact on

Project

(1 – 10)

Risk Factor

(Probability x

Impact)

Table 6.2 displays a risk analysis format. There are various tasks involved in risk

analysis. First, the WBS elements are identified. One of the tasks in the risk analysis

phase is to describe the risk. The risk can be product-related, process-related,

organization-related, client-related, or infrastructure-related.

Second, the WBS elements are evaluated to determine the risk events. Then the project

manager quantifies the probability of occurrence of risk. The project manager can assign

probability values between 0 and 1. For example, a risk with a low probability of

occurrence is marked 0.2 while that with a high probability of occurrence is marked 0.8.

The reason why a particular risk has a high or low probability depends on the actual

circumstance of the project.

Third, the risks are rated depending on their probability of occurrence. Based on the

probability of risk, the project manager identifies the impact of the risk. The impact of

risk on cost, schedule, and quantity needs to be calculated and graded. The impact of risk

can be graded on a scale of 1 to 10, 1 being the lowest, and 10 being the highest.

Then the risk factor is calculated by multiplying the probability of risk and the impact of

risk. Finally, each risk is prioritized relative to other risks. The risk factor is used to

prioritize the identified risks. For example, the risk with a probability value 0.1 and an

impact value 2 will have minimal impact. While risks close to probability value 0.8 and

with an impact value 9 will have greater impact. Therefore, the project manager can

prioritize risks based on the probability and the impact of risks. A risk that has a high

impact and low probability will not absorb a significant amount of the project manager's

time. However, high-impact risks with moderate to high probability will catch the

attention of the project manager.

Software Project Management (CS615)

312

© Copyright Virtual University of Pakistan

Risk Mitigation

Risk mitigation is the best possible approach adopted by the project manager to avoid

risks from occurring. The probability of the risk occurring and the potential impact of the

risk can be mitigated by dealing with the problem early in the project. Essentially, risk

mitigation involves three possibilities and the project manager needs to adopt a risk

mitigation strategy aimed at them. The three possibilities include:

• Risk avoidance

• Risk monitoring

• Contingency planning

Risk Avoidance

To avoid risks from occurring, the project team prepares the risk plan before the

commencement of the project. The project team identifies the potential risks and

prioritizes them based on their probability of occurrence and impact. Then, the team

prepares a plan for managing risks. In most software projects, this plan is popularly called

the risk management plan. Table 6.3 displays the format of a risk management plan.

Table 6.3: Risk Management Plan

Risk

Description

Probability

of

Occurrence

(0 – 1)

Impact

on

Project

(1 –

10)

Risk

Factor

(Probability

x Impact)

Mitigation

Steps Responsibility Start

Date

End

Date

To prepare the risk management plan, the project team first identifies and assesses the

risks associated with the project. Then, the probability of occurrence of each risk is

estimated and the possible impact is calculated. In the plan, the probable cost and damage

is also quantified. The project team also identifies the contingency plans for all the

identified risks. The contingency plan for each risk is based on the project's defined

operational software process. The plan is modified throughout the software development

life cycle of the project based on the changes taking place. The contingency plan also

includes the cost, in terms of effort, in carrying out the plan. The software risks identified

are tracked, reassessed, and re-planned at the end of each phase. The project manager

revisits the plan if significant changes are introduced in the software project.

Risk Monitoring

As the project proceeds, risk-monitoring activities commence. It is not possible to

monitor closely all the risks that are identified for the project. For example, if 100 risks

are identified for a project, only top 20 risks are monitored. There are re-planning

checkpoints where the information obtained from monitoring the risks is used to refine

the risk assessments and management plan. The project manager monitors the top 20

Software Project Management (CS615)

313

© Copyright Virtual University of Pakistan

percent of the factors that may indicate the status of the risks in the project. In the case of

large teams, the project manager also needs to monitor the attitude of the team members

and their problems. This helps the project manager monitor any possible team-related

risks.

Besides monitoring the top 20 percent of the risks, the project manager needs to monitor

the mitigation steps also. Consider an example. To ensure that particular software is

browser- independent, the software is created on the lowest compatible browser. Such

software will work on any browser thus making it browser-independent. Therefore,

mitigating a project risk involves working hard at reducing the possibility that the risk

will ever occur. Mitigation includes nearly all actions that a project team takes to

overcome risks. For example, choosing a more expensive but proven technology over, a

newer, less expensive technology is a step toward mitigating project risks.

Contingency Planning

The possibility of contingency planning arises when mitigation efforts fail and risk

becomes a reality. Contingency planning is used to monitor risks and invoke a

predetermined response. According to the plan, a trigger is set up. If the trigger is

reached, the contingency plan is put into effect. Contingency planning involves

maintaining an alternative plan if the original plan fails. A simple example could be the

savings people make for a rainy day. Contingency plans are a must for the top 20 percent

of the risks identified. These plans are put to use after the risks become a reality. The

importance of contingency planning can be realized from this example. Despite the

massive attack on WTC, the stock markets in the US resumed functioning within a few

days. This was possible because the finance companies had backed up their data and

information on computers elsewhere. The contingency planning of finance companies

prevented the risk of huge data loss for the stock market.

Managing Risks: Case Study

Consider a scenario. Your organization is a vendor of software solutions. A bus transport

company the US wants you to develop a Schedule Adherence system. The team that will

develop this software is new and the platform selected for development is also new to

your organization. The project team needs to be trained intensively for this.

During this project, the team is expected to manage a large volume of data. The team has

never had any experience in managing such a large volume of data. The system also

needs to use this data to generate various MIS reports related to delays or adherence of

bus services.

The performance requirement is less than fifteen seconds for all popular browsers. Your

organization is anticipating numerous requirement changes during the development

process. The system needs to be implemented across several states in the country. The

data related to the system is highly confidential because it can provide an edge to the

competitors.

Now, as a project manager, you need to prepare a risk management plan for this project.

The project starts on May 15 and should be completed on November 15.

Software Project Management (CS615)

314

© Copyright Virtual University of Pakistan

First, you need to identify the potential risks involved in the project. The potential risks to

the project are described in Table 6.4.

Table 6.4: Potential Risks to a Project

Risk Description

Inexperienced staff

Performance risk due to high volume of data to be processed

Cross-browser compatibility

Involvement of new technology

Design changes during development

After identifying the risks, you need to estimate the probability of their occurrence and

their impact on product development. Based on this, you calculate the risk factor and plan

the mitigation steps.

Your risk management plan is displayed in Table 6.5.

Table 6.5: The Risk Management Plan for Building a Schedule Adherence System

Risk

Description

Probability

of

Occurrence

(0 – 1)

Impact

on

Project

(1 –

10)

Risk

Factor

(Probability

x Impact)

Mitigation

Steps Responsibility Start

Date

End

Date

Inexperience

Staff 0.8 3 2.4 Project

Manager

Conducting

training

sessions before

the need

commencement

of project

May

15

July

15

Performance

risk due to

high volume

of data to be

processed

0.6 7 4.2 Architect

Massive tuning

of architecture

during the

design phase

and conducting

a proof of

concepts for

the design

May

15

Till

the

end of

the

project

Crossbrowser

0.6 5 3.0 Developer Using the

lowest

May

15

Till

the

Software Project Management (CS615)

315

© Copyright Virtual University of Pakistan

compatibility compatible

browser for

development

end of

the

project

Involvement

of new

technology

0.5 5 2.5 Project

Manager

Ensuring all

details

pertaining to

the technology

is available and

keeping in

close touch

with the

technology

vendor

May

Till

the

end of

the

project

Design

changes

during

development

0.6 8 4.8 Architect

Designing a

flexible

architecture

that can

accommodate

future changes

and

enhancement

May

15

Till

the

end of

the

project

In Table 6.5, the risk factors with high values are the high priority risks. Here, the high

priority risks are design changes during development, performance risk due to high

volume of data to be processed, and cross-browser compatibility. The high priority risks

need to be monitored closely and continuously. The rest of the risks can be monitored

periodically. Certain risks need contingency planning despite being low in the priority

list. For example, the risk due to involvement of new technology is a low priority risk.

However, the probability of occurrence of this risk is 0.5, which is fairly high. This calls

for contingency planning because you may not be aware of all the details of the new

technology. Suppose the system fails to respond if the number of users exceeds a certain

number. In such a situation, you need to have a contingency plan ready. You need to

discuss with the vendor regarding a workaround for such a situation. The workaround

should be ready in the case of failure of the system.

Robert Charette [CHA89] presents a conceptual definition of risk:

First, risk concerns future happenings, Today and yesterday are beyond active concern, as

we are already reaping what was previously sowed by our past actions, The question is,

can we, therefore, by changing our actions today, create an opportunity for a different and

hopefully better situation for ourselves tomorrow, This means, second, that risk involves

change, such as in changes of mind, opinion, actions, or places…[Third] risk involves

choice, and the uncertainty that choice itself entails, Thus paradoxically, risk, like death

and taxes, is one of the few certainties of life,

Software Project Management (CS615)

316

© Copyright Virtual University of Pakistan

When risk is considered in the context of software engineering, Charette's three

conceptual underpinnings are always in evidence. The future is our concern – what risks

might cause the software project to go awry? Change is our concern -how will changes in

customer requirements, development technologies, target computers, and all other entities

connected to the project affect timeliness and overall success? Last, we must grapple with

choices - what methods and tools should we use, how many people should be involved,

how much emphasis on quality is "enough"?

What is it? Risk analysis and management are a series of steps that help a software team

to understand and manage uncertainty. Many problems can plague a software project A

risk is a potential problem - it might happen, it might not But regardless of the outcome,

it's a really good idea to identify it, assess its probability of occurrence, estimate its

impact, and establish a contingency plan should the problem actually occur.

Who does it? Everyone involved in the software process – managers, software engineers

and customers - participate in risk analysis and management

Why is it important? Think about the Boy Scout motto: "Be prepared" Software is a

difficult undertaking. Lots of things can go wrong, and frankly, many often do. It's for

this reason that being prepared, understanding the risks and taking preventive measures to

avoid or manage them is a key element of good software project management.

What are the steps? Recognizing what can go wrong is the first step, called - risk

identification. Next, each risk is analyzed to determine the likelihood that it will occur

and the damage that it will do if it does occur. Once this information is established, risks

are ranked by probability and impact. Finally, a plan is developed to manage those risks

with high probability and high impact.

What is the work product? A risk mitigation monitoring and management (RMMM)

plan or a set of risk information sheets is produced.

How do I ensure that I've done it right? The risks that are analyzed and managed

should be derived from thorough study of the people, the product, the process and the

project. The RMMM should be revisited as the project proceeds to ensure that risks are

kept up to date. Contingency plans for risk management should be realistic.

6.1 REACTIVE VS. PROACTIVE RISK STRATEGIES

Reactive strategies have been laughingly called the “Indiana Jones School of risk

management” [THO92]. In the movies that carried his name, Indiana Jones, when faced

with overwhelming difficulty, would invariably say, “Don’t worry, I’ll think of

something!” Never worrying about problems until they happened, Indy would react in

some heroic way.

Sadly, the average software project manager is not Indiana Jones and the members of the

software project team are not his trusty sidekicks. Yet, the majority of software teams

rely solely on reactive risk strategies. At best, a reactive strategy monitors the project for

likely risks. Resources are set aside to deal with them, should they become actual

problems. More commonly, the software team does nothing about risks until something

goes wrong. Then, the team flies into action in an attempt to correct the problem rapidly.

Software Project Management (CS615)

317

© Copyright Virtual University of Pakistan

This is often called a fire fighting mode. When this fails, “Crisis Management” [CHA92]

takes over, and the project is in real jeopardy.

A considerably more intelligent strategy for risk management is to be proactive. A

proactive strategy begins long before technical work is initiated. Potential risks are

identified, their probability and impact are assessed and they are ranked by importance.

Then, the software team establishes a plan for managing risk. The primary objective is to

avoid risk, but because not all risks can be avoided, the team works to develop a

contingency plan that will enable it to respond in a controlled and effective manner.

6.2 SOFTWARE RISKS

Although there has been considerable debate about the proper definition for software risk,

there is general agreement that risk always involves two characteristics [HIG 95]:

• Uncertainty - the risk may or may not happen; that is, there are no 100 % probable

risks.

• Loss - if the risk becomes a reality, unwanted consequences or losses will occur.

When risks are analyzed, it is important to quantify the level of uncertainty and the

degree of loss associated with each risk. To accomplish this, different categories of risks

are considered.

Project risks threaten the project plan. That is, if project risks become real, it is likely that

project schedule will slip and that costs will increase. Project risks identify potential

budgetary, schedule, personnel (staffing and organization), resource, customer, and

requirements problems and their impact on a software project. In Chapter 5, project

complexity, size, and the degree of structural uncertainty were also defined as project

(and estimation) risk factors.

Technical risks threaten the quality and timeliness of the software to be produced. If a

technical-risk becomes a reality, implementation may become difficult or impossible.

Technical risks identify potential design, implementation, interface, verification, and

maintenance problems. In addition, specification ambiguity, technical uncertainty,

technical obsolescence, and "leading-edge" technology are also risk factors. Technical

risks occur because the problem is harder to solve than we thought it would be.

Business risks threaten the viability of the software to be built. Business risks often

jeopardize the project or the product. Candidates for the top five business risks are (1)

building a excellent product or system that no one really wants (market risk), (2) building

a product that no longer fits into the overall business strategy for the company (strategic

risk), (3) building a product that the sales force doesn't understand how to sell, (4) losing

the support of senior management due to a change in focus or a change in people

(management risk), and (5) losing budgetary or personnel commitment (budget risks). It

is extremely important to note that simple categorization won't always work. Some risks

are simply unpredictable in advance.

Software Project Management (CS615)

318

© Copyright Virtual University of Pakistan

Another general categorization of risks has been proposed by Charette [CHA89J. Known

risks are those that can be uncovered after careful evaluation of the project plan, the

business and technical environment in which the project is being developed, and other

reliable information sources (e.g., unrealistic delivery date, lack of documented

requirements or software scope, poor development environment). Predictable risks are

extrapolated from past project experience (e.g., staff turnover, poor communication with

the customer, dilution of staff effort as ongoing maintenance requests are serviced).

Unpredictable risks are the joker in the deck. They can and do occur, but they are

extremely difficult to identify in advance.

6.3 RISK IDENTIFICATION

Risk identification is a systematic attempt to specify threats to the project plan (estimates,

schedule, resource loading, etc.). By identifying known and predictable risks, the project

manager takes a first step toward avoiding them when possible and con- trolling them

when necessary.

There are two distinct types of risks for each of the categories that have been presented in

Section 6.2: generic risks and product-specific risks. Generic risks are a potential threat to

every software project. Product-specific risks can be identified only by those with a clear

understanding of the technology, the people, and the environment that is specific to the

project at hand. To identify product -specific risks, the project plan and the software

statement of scope are examined and an answer to the following question is developed:

What special characteristics of this product may threaten our project plan?

One method for identifying risks is to create a risk item checklist. The checklist can be

used for risk identification and focuses on some subset of known and predictable risks in

the following generic subcategories:

• Product size-risks associated with the overall size of the software to be built or

modified.

• Business impact-risks associated with constraints imposed by management or the

marketplace.

• Customer characteristics-risks associated with the sophistication of the customer

and the developer's ability to communicate with the customer in a timely manner.

• Process definition-risks associated with the degree to which the software process

has been defined and is followed by the development organization.

• Development environment-risks associated with the availability and quality of the

tools to be used to build the product.

• Technology to be built-risks associated with the complexity of the system to be

built and the newness of the technology that is packaged by the system.

• Staff size and experience-risks associated with the overall technical and project

experience of the software engineers who will do the work.

Software Project Management (CS615)

319

© Copyright Virtual University of Pakistan

The risk item checklist can be organized in different ways. Questions relevant to each of

the topics can be answered for each software project. The answers to these questions

allow the planner to estimate the impact of risk. A different risk item checklist format

simply lists characteristics that are relevant to each generic subcategory. Finally, a set of

"risk components and drivers” [AFC88] are listed along with their probability of

occurrence. Drivers for performance, support, cost, and schedule are discussed in answer

to later questions.

A number of comprehensive checklists for software project risk have been proposed in

the literature (e.g., [SEI93], [KAR96]). These provide useful insight into generic risks for

software projects and should be used whenever risk analysis and management is

instituted. However, a relatively short list of questions [KEI98] can be used to provide a

preliminary indication of whether a project is "at risk."

6.3.1 Assessing Overall Project Risk

The following questions have derived from risk data obtained by surveying experienced

software project managers in different part of the world [KEI98]. The questions are

ordered by their relative importance to the success of a project.

1. Have top software and customer managers formally committed to support the project?

2. Are end-users enthusiastically committed to the project and the system/product to be

built?

3. Are requirements fully understood by the software engineering team and their

customers?

4. Have customers been involved fully1n the definition of requirements?

5. Do end-users have realistic expectations?

6. Is project scope stable?

7. Does the software engineering team have the right mix of skills?

8. Are project requirements stable?

9. Does the project team have experience with the technology to be implemented?

10. Is the number of people on the project team adequate to do the job?

11. Do all customer/user constituencies agree on the importance of the project and on the

requirements for the system/product to be built?

If anyone of these questions is answered negatively, mitigation, monitoring, and

/management steps should be instituted without fail. The degree to which the project is at

risk is directly proportional to the number of negative responses to these questions.

6.3.2 Risk Components and Drivers

The U.S. Air Force [AFC88j has written a pamphlet that contains excellent guidelines (or

software risk 1dentification and abatement. The Air Force approach requires that the

project manager identify the risk drivers that affect software risk components-

Performance, cost, support, and schedule. In the context of this discussion, the risk

components are defined in the following manner:

Software Project Management (CS615)

320

© Copyright Virtual University of Pakistan

• Performance risk - the degree of uncertainty that the product will meet its

requirements and be fit for its intended use.

• Cost risk - the degree of uncertainty that the project budget will be maintained.

• Support risk - the degree of uncertainty that the resultant software will be easy to

correct, adapt, and enhance.

• Schedule risk - the degree of uncertainty that the project schedule will be

maintained and that the product will be delivered on time.

The impact of each risk driver on the risk component is divided into one of four impacts

categories-negligible, marginal, critical, or catastrophic. Referring to Figure 6.1

[BOE89], a characterization of the potential consequences of errors (rows labeled 1) or a

failure to achieve a desired outcome (rows labeled 2) are described. The impact category

is chosen based on the characterization that best fits the description in the table.

Figure 6.1 Impact assessment

Components/Category Performance Support Cost Schedule

1 Failure to meet the

requirement would result in

mission failure

Failure results in

increased costs and

schedule delays with

expected values of $500

K

Catastrophic

2 Significant

degradation to

non

achievement

of technical

performance

Non

responsive or

unsupportable

software

Significant

financial

shortages,

budget

overrun

likely

Unavoidable

IOC

1 Failure to meet the

requirement would degrade

system performance to a point

where mission success is

questionable

Failure results in

operational delays and/or

increased costs with

expected $100 K to $ 500

K

Critical

2 Some

reduction in

technical

performance

Minor delays

in software

modification

Some

shortage of

financial

resources,

possible

overruns

Possible

slippage in

IOC

Marginal 1 Failure to meet the

requirement would result in

degradation of secondary

mission

Costs, impacts and / or

recoverable schedule slips

with expected value of $ 1

K to $ 100 K

Software Project Management (CS615)

321

© Copyright Virtual University of Pakistan

2 Minimal to

small

reduction in

technical

performance

Responsive

software

support

Sufficient

financial

resources

Realistic

achievable

schedule

1 Failure to meet the

requirement would create

inconvenience or non

operational impact

Error results in minor cost

and / or schedule impact

with expected value of

less than $ 1 K

Negligible

2 No reduction

in technical

performance

Easily

supportable

software

Possible

budget

under run

Early

achievable

IOC

Note:

(1) The potential consequence of undetected software errors or faults.

(2) The potential consequence if the desired outcome is not achieved.

6.4 RISK PROJECTION

Risk projection, also called risk estimation, attempts to rate each risk in two ways-the

likelihood or probability that the risk is real and the consequences of the problems

associated with the risk, should it occur. The project planner, along with other managers

and technical staff, performs four risk projection activities:

(1) Establish a scale that reflects the perceived likelihood of a risk,

(2) Delineate the consequences of the risk,

(3) Estimate the impact of the risk on the project and the product, and

(4) Note the overall accuracy of the risk projection so that there will be no

misunderstandings.

6.4.1 Developing a Risk Table

A risk table provides a project manager with a simple technique for risk projection. A

sample risk table is illustrated in figure 6.2.

Figure 6.2 Sample risk table prior to sorting

Risks Category Probability Impact RMMM

Size estimate may be significantly low

Larger number of users than planned

Less reuse than planned

End-users resist system

Delivery deadline will be lightened

Funding will be lost

Customer will change requirements

Technology will not meet expectations

Lack of training on tools

PS

PS

PS

BU

BU

CU

PS

TE

DE

60%

30%

70%

40%

50%

40%

80%

30%

80%

2

3

2

3

2

1

2

1

3

Software Project Management (CS615)

322

© Copyright Virtual University of Pakistan

Staff inexperienced

Staff turnover will be high

ST

ST

80%

60%

2

2

Impact values:

l- Catastrophic

2- Critical

3- marginal

4- Negligible

A project team begins by listing all risks (no matter how remote) in the first column of

the table. This can be accomplished with the help of the risk item check-lists referenced

in Section 6.3. Each risk is categorized in the second column (e.g., PS implies a project

size risk, BU implies a business risk). The probability of occurrence of each risk is

entered in the next column of the table. The probability value for each risk can be

estimated by team members individually. Individual team members are polled in roundrobin

fashion until their assessment of risk probability begins to converge.

Next, the impact of each risk is assessed. Each risk component is assessed using the

characterization presented in Figure 6.1, and an impact category is determined. The

categories for each of .the four risk components - performance, support, cost, and

schedule - are averaged to determine an overall impact value.

Figure 6.3 Risk and management concern

Once the first four columns of the risk table have been completed, the table is sorted by

probability and by impact. High-probability, high-impact risks percolate to the top of the

Disregard

risk factor

1.0

Very

h h

High

Management

concern

Impact

Probability

Of occurrence

Very

low

0

Software Project Management (CS615)

323

© Copyright Virtual University of Pakistan

table, and low-probability risks drop to the bottom. This accomplishes first order risk

prioritization. The project manager studies the resultant sorted table and defines a cutoff

line. The cutoff line (drawn horizontally at some point in the table) implies that only risks

that lie above the line will be given further attention. Risks that fall below the line are reevaluated

to accomplish second-order prioritization. Referring to Figure 6.3, risk impact

and probability have a distinct influence on management concern. A risk factor that has a

high impact but a very low probability of occurrence should not absorb a significant

amount of management time. However, high-impact risks with moderate to high

probability and low-impact risks with high probability should be carried forward into the

risk analysis steps that follow.

All risks that lie above the cutoff line must be managed. The column labeled RMMM

contains a pointer into Risk Mitigation, Monitoring and Management Plan or

alternatively, a collection of risk information sheets developed for all risks that lie above

the cutoff. The RMMM plan and risk information sheets are discussed in Sections 6.5 and

6.6.

Risk probability can be determined by making individual estimates and then developing a

single consensus value. Although that approach is workable, more sophisticated

techniques for determining risk probability have been developed [AFC88]. Risk drivers

can be assessed on a qualitative probability scale that has the following values:

impossible, improbable, probable, and frequent. Mathematical probability can then be

associated with each qualitative value (e.g., a probability of 0.7 to 1.0 implies a highly

probable risk).

6.4.2 Assessing Risk Impact

Three factors affect the consequences that are likely if a risk does occur: its nature, its

scope, and its timing. The nature of the risk indicates the problems that are likely if it

occurs. For example, a poorly defined external interface to customer hardware (a

technical risk) will preclude early design and testing and will likely lead to system

integration problems late in a project. The scope of a risk combines the severity (just how

serious is it?) with its overall distribution (how much of the project will be affected or

how many customers are harmed?). Finally, the timing of a risk considers when and for

how long the impact will be felt. In most cases, a project manager might want the "bad

news" to occur as soon as possible, but in some cases, the longer the delay, the better.

Returning once more to the risk analysis approach proposed by the U.S. Air Force

fAFC88), the following steps are recommended to determine the overall consequences of

a risk:

1. Determine the average probability of occurrence value for each risk component.

2. Using Figure 6.1, determine the impact for each component based on the criteria

shown.

3. Complete the risk table and analyze the results as described in the preceding sections. .

Software Project Management (CS615)

324

© Copyright Virtual University of Pakistan

The overall risk exposure, RE, is determined using the following relationship [HAL98]:

RE=P x C.

where P is the probability of occurrence for a risk, and C is the cost to the project should

the risk occur.

For example, assume that the software team defines a project risk in the following

manner:

Risk identification. Only 70 percent of the software components scheduled for reuse

will, in fact, be integrated into the application. The remaining functionality will have to

be custom developed.

Risk probability. 80% (likely).

Risk impact. 60 reusable software components were planned. If only 70 percent can be

used, 18 components would have to be developed from scratch (in addition to other

custom software that has been scheduled for development). Since the average component

is 100 LOC and local data indicate that the software engineering cost for each LOC is

$14.00, the overall cost (impact) to develop the components would be 18 x 100 x 14 =

$25,200.

Risk exposure. RE = 0.80 x 25,200 - $20,200.

Risk exposure can be computed for each risk in the risk table, once an estimate of the cost

of the risk is made. The total risk exposure for all risks (above the cutoff in the risk table)

can provide a means for adjusting the final cost estimate for a project. It can also be used

to predict the probable Increase In staff resources required at various points during the

project schedule.

The risk projection and analysis techniques described in Sections 6.4.1 and 6.4.2 are

applied iteratively as the software project proceeds. The project team should revisit the

risk table at regular intervals, re-evaluating each risk to determine when new

circumstances cause its probability and impact to change. As a consequence of this

activity, it may be necessary to add new risks to the table, remove some risks that are no

longer relevant, and change the relative positions of still others.

6.4.3 Risk Assessment

At this point in the risk management process, we have established a set of triplet of the

form [CHA89]:

[rj, lj, xj]

where rj is risk, lj is the likelihood (probability) of the risk, and xj is the impact of the risk.

During risk assessment, we further examine the accuracy of the estimates that were made

during risk projection, attempt to rank the risks that have been uncovered, and begin

thinking about ways to control and/or avert risks that are likely to occur.

Software Project Management (CS615)

325

© Copyright Virtual University of Pakistan

Figure 6.4 Risk referent level

For assessment to be useful, a risk referent level [CHA89] must be defined. For most

software projects, the risk components discussed earlier - performance, cost, support, and

schedule also represent risk referent levels: That is, there is a level for performance,

degradation, cost overrun, support difficulty, or schedule slippage (or any combination of

the four) that will cause the project to be terminated. If a combination of risks create

problems that cause one or more of these referent levels to be exceeded, work will stop.

In the context of software risk analysis, a risk referent level has a single point, called the

referent point or break point, at which the decision to proceed with the project or

terminate it (problems are just too great) are equally weighted. Figure 6.4 represents this

situation graphically.

In reality, the referent level can rarely be represented as a smooth line on a graph. In most

cases it is a region in which there are areas of uncertainty; that is, attempting to predict a

management decision based on the combination of referent values is often impossible.

Therefore, during risk assessment, we perform the following steps:

1. Define the risk referent levels for the project.

2. Attempt to develop a relationship between each (rj, lj, xj) and each of the referent

levels.

3. Predict the set of referent points that define a region of termination, bounded by a

curve or areas of uncertainty.

4. Try to predict how compound combinations of risks will affect a referent level.

6.5 RISK REFINEMENT

Projected

schedule

overrun

Referent point (cost value, time value)

Project termination will

Projected cost overrun

Software Project Management (CS615)

326

© Copyright Virtual University of Pakistan

During early stages of project planning, a risk may be stated quite generally. As time

passes and more is learned about the project and the risk, it may be possible to refine the

risk into a set of more detailed risks, each somewhat easier to mitigate, monitor, and

manage.

One way to do this is to represent the risk in condition-transition-consequence (CTC) II

format [GLU94). That is, the risk is stated in the following form:

Given that <condition> then there is concern that (possibly) <consequence>.

Using the CTC format for the reuse risk noted in Section 6.4.2, we can write:

Given that all reusable software components must conform to specific design standards

and that some do not conform, then there is concern that (possibly) only 70 percent of the

planned reusable modules may actually be integrated into the as-built system, resulting in

the need to custom engineer the remaining 30 percent of components. This general

condition can be refined in the following manner:

Sub condition 1. Certain reusable components were developed by a third party with no

knowledge of internal design standards.

Sub condition 2. The design standard for component interfaces has not been solidified

and may not conform to certain existing reusable components.

Sub condition 3. Certain reusable components have been implemented in a language that

is not supported on the target environment.

The consequences associated with these refined sub conditions remains the same (i.e., 30

percent of software components must be customer engineered), but the refinement helps

to isolate the underlying risks and might lead to easier analysis and response.

6.6 RISK MITIGATION, MONITORING, AND MANAGEMENT

All of the risk analysis activities presented to this point have a single goal to assist the

project team in developing a strategy for dealing with risk. An effective strategy must

consider three issues:

􀂙 risk avoidance

􀂙 risk monitoring

􀂙 risk management and contingency planning

􀂙

If a software team adopts a proactive approach to risk, avoidance is always the best

strategy. This is achieved by developing a plan for risk mitigation. For example, assume

that high staff turnover is noted as a project risk, rl Based on past history and

management intuition, the likelihood, ll of high turnover is estimated to be 0.70 (70 per

cent, rather high) and the impact, xl is projected at level 2. That is, high turnover will

have a critical impact on project cost and schedule.

To mitigate this risk, project management must develop a strategy for reducing turnover.

Among the possible steps to be taken are

Software Project Management (CS615)

327

© Copyright Virtual University of Pakistan

o Meet with current staff to determine causes for turnover (e.g., poor working

conditions, low pay, and competitive job market).

o Mitigate those causes that are under our control before the project starts.

o Once the project commences, assume turnover will occur and develop techniques to

ensure continuity when people leave.

o Organize project teams so that information about each development activity is widely

dispersed.

o Define documentation standards and establish mechanisms to be sure that .documents

are developed in a timely manner.

o Conduct peer reviews of all work (so that more than one person is “up to speed").

o Assign a backup staff member for every critical technologist.

As the project proceeds, risk monitoring activities commence. The project manager

monitors factors that may provide an indication of whether the risk is becoming more or

less likely. In the case of high staff turnover, the following factors can be monitored:

• General attitude of team members based on project pressures.

• The degree to which the team has jelled.

• Interpersonal relationships among team members.

• Potential problems with compensation and benefits.

• The availability of jobs within the company and outside it.

In addition to monitoring these factors, the project manager should monitor the

effectiveness of risk mitigation steps. This is one mechanism for ensuring continuity,

should a critical individual leave the project. The project manager should monitor

documents carefully to ensure that each can stand on its own and that each imparts

information that would be necessary if a newcomer were forced to join the software team

somewhere in the middle of the project.

Risk management and contingency planning assumes that mitigation efforts have failed

and that the risk has become a reality. Continuing the example, the project is well

underway and a number of people announce that they will be leaving. If the mitigation

strategy has been followed, backup is available, information is documented, and

knowledge has been dispersed across the team. In addition, the project manager may

temporarily refocus resources (and readjust the project schedule) to those functions that

are fully staffed, enabling newcomers who must be added to the team to "get up to

speed." Those individuals who are leaving are asked to stop all work and spend their last

weeks in "knowledge transfer mode. This might include video-based knowledge capture,

the development of "commentary documents," and/or meeting with other team members

who will remain on the project.

It is important to note that RMMM steps incur additional project cost. For example,

spending the time to "backup" every critical technologist costs money. Part of risk

management, therefore, is to evaluate when the benefits accrued by the RMMM steps are

outweighed by the costs associated with implementing them. In essence, the project

Software Project Management (CS615)

328

© Copyright Virtual University of Pakistan

planner performs a classic cost/benefit analysis. If risk aversion steps for high turnover, it

will increase both project cost and duration by an estimated 15 percent, but the

predominant cost factor is "backup," management may decide not to implement this step.

On the other hand, if the risk aversion steps are projected to' increase costs by 5 percent

and duration by only 3 percent management will likely put all into place.

For a large project, 30 or 40 risks may be identified. If between three and seven risk

management steps are identified for each, risk management may become a project in

itself! For this reason, we adapt the Pareto 80-20 rule to software risk. Experience

indicates that 80 percent of the overall project risk (i.e., 80 percent of the potential for

project failure) can be accounted for by only 20 percent of the identified risks. The work

performed during earlier risk analysis steps will help the planner to determine which of

the risks reside in that 20 percent (e.g., risks that lead to the highest risk exposure. For

this reason, some of the risks identified, assessed, and projected may not make it into the

RMMM plan - they don't fall into the critical 20 percent (the risks with highest project

priority).

6.7 SAFETY RISKS AND HAZARDS

Risk is not limited to the software project itself. Risks can occur after the software has

been successfully developed and delivered to the customer. These risks are typically

associated with the consequences of software failure in the field.

In the early days of computing, there was reluctance to use computers (and soft- ware) to

control safety critical processes such as nuclear reactors, aircraft flight control, weapons

systems, and large-scale industrial processes. Although the probability .of failure of a

well-engineered system was small, an undetected fault in a computer- based control or

monitoring system could result in enormous economic damage or, worse, significant

human injury or loss of life. But the cost and functional benefits of Computer-based

control and monitoring far outweigh the risk. Today, computer hardware and software are

used regularly to control safety critical systems.

When software is used as part of a control system, complexity can increase by an order of

magnitude or more. Subtle design faults induced by human error-some- thing that can be

uncovered and eliminated in hardware-based conventional control-become much more

difficult to uncover when software is used.

Software safety and hazard analysis [LEV95] are software quality assurance activities

(Chapter 8) that focus on the identification and assessment of potential hazards that may

affect software negatively and cause an entire system to fail. If hazards can be identified

early in the software engineering process, software design features can be specified that

will either eliminate or control potential hazards.

6.8 THE RMMM PLAN

Software Project Management (CS615)

329

© Copyright Virtual University of Pakistan

A risk management strategy can be included in the software project plan or the risk

management steps can be organized into a separate Risk Mitigation, Monitoring and

Management Plan. The RMMM plan documents all work performed as part of risk

analysis and are used by the project manager as part of the overall project plan.

Some software teams do not develop a formal RMMM document. Rather, each risk is

documented individually using a risk information sheet (RIS) [WIL97]. In most cases, the

RIS is maintained using a database system, so that creation and information entry,

priority ordering, searches, and other analysis may be accomplished easily. The format of

the RIS is illustrated in Figure 6.5.

Once RMMM has been documented and the project has begun, risk mitigation and

monitoring steps commence. As we have already discussed, risk mitigation is a problem

avoidance activity. Risk monitoring is a project tracking activity with three primary

objectives: (I) to assess whether predicted risks do, in fact, occur; (2) to ensure that risk

aversion steps defined for the risk are being properly applied; and (3) to collect

information that can be used for future risk analysis. In many cases, the problems that

occur during a project can be traced to more than one risk. Another job of risk monitoring

is to attempt to allocate origin (what risk(s) caused which problems throughout. the

project).

Risk management is not as well developed as are some of the more traditional project

management disciplines. Some organizations feel that risk management is too specialized

or

advanced for them. Others believe that risk management is optional. Others fear that risk

management may expose flaws in their project plans and strategies that will hurt them in

the competitive world. Certainly these organizations will not talk openly and honestly

about risk and will “shoot the messenger” that brings risk to their attention.

Risk-mature organizations overcome the barriers to practicing effective risk management

in their approach to projects.

_Their organizational culture becomes “risk friendly.”

_Risk management gains priority to rank along with cost, time and scope management.

_Decisions are made and resources are allocated based on the results of risk analysis.

_The highest quality data are used for risk analysis and resources are committed to the

efforts.

_Risk management is viewed as a career path in the organization and those that practice

it are treated as professionals.

_Risk analysis functions are given independence in the organization even though that

may make it hard to “control.”

_Mature risk management organizations look to the best in class to benchmark their risk

management processes.

_They use modern tools and are not disdainful of sophisticated and proven approaches.

_They measure their effectiveness with metrics.

_Project decisions are made on a “risk-adjusted” basis.

_Continuous improvement is achieved through regular repetition.

Software Project Management (CS615)

330

© Copyright Virtual University of Pakistan

_They participate in professional interchanges through conferences and journals, sharing

what they have learned.

Project risk is an uncertain event or condition that, if it occurs, has a positive or a

negative effect on at least one project objective. A risk may have one or more causes and,

if it occurs, one or more impacts. For example, a cause may be requiring an

environmental permit to do work or having limited personnel assigned to design the

project. The risk event is that the permitting agency may take longer than planned to issue

a permit for some reason, or the design personnel available and assigned may not be

adequate for the task. If either of these uncertain events occurs, there may be an impact

on the project cost, schedule, or performance. Risk conditions could include aspects of

the project’s or organization’s environment that may contribute to project risk, such as

poor project management practices, lack of integrated management systems, concurrent

multiple projects, or dependency on external participants who cannot be controlled.

Project risk has its origins in the uncertainty that is present in all projects. Known risks

are those that have been identified and analyzed, and it may be possible to plan for those

risks using the processes described in this chapter. Unknown risks cannot be managed

proactively, and a prudent response by the project team can be to allocate general

contingency against such risks, as well as against any known risks for which it may not

be cost-effective or possible to develop a proactive response.

Organizations perceive risk as it relates to threats to project success or to opportunities to

enhance chances of project success. Risks that are threats to the project may be accepted

if the risk is in balance with the reward that may be gained by taking the risk. For

example, adopting a fast track schedule (Section 6.4) that may be overrun is a risk taken

to achieve an earlier completion date. Risks that are opportunities, such as work

acceleration that may be gained by assigning more expert staff, may be pursued to benefit

the project’s objectives.

Individuals, and by extension organizations, have attitudes toward risk that affect both the

accuracy of the perception of risk and the way they respond. Attitudes about risk should

be made explicit wherever possible. A consistent approach to risk that meets the

organization’s requirements should be developed for each project, and communication

about risk and its handling should be open and honest. Risk responses reflect an

organization’s balance between risk-taking and risk-avoidance.

To be successful, the organization must be committed to addressing the management of

risk proactively and consistently throughout the project.

Software Project Management (CS615)

331

© Copyright Virtual University of Pakistan

Figure: Project Risk Management Flow

Software Project Management (CS615)

332

© Copyright Virtual University of Pakistan

LECTURE # 40

9. Risk and Change Management

9.1 Fundamentals

• What is it?

Change Management is the process by which changes to the Project’s scope,

deliverables, timescales or resources are formally defined, evaluated and

approved prior to implementation.

A core aspect of the Project Manager’s role is to manage change within the

project successfully. This is achieved by understanding the business and system

drivers requiring the change, documenting the benefits and costs of adopting the

change and formulating a structured plan for implementing the change.

To formally request a change, it is often necessary to complete a Change Form.

The change request details may then be recorded within a Change Register.

Risk Management is the process by which risks to the project (e.g. to the scope,

deliverables, timescales or resources) are formally identified, quantified and

managed during the project.

A project risk may be identified at any stage of the project by completing a Risk

Form and recording the relevant risk details within the Risk Register.

First, risk concerns future happenings. Today and yesterday are beyond active

concern, as we are already reaping what was previously sowed by our past

actions. The question is; can we, therefore, by changing our actions today, create

an opportunity for a different and hopefully better situation for ourselves

tomorrow.

This means, second, that risk involves change, such as in changes of mind,

opinion, actions, or places…

[Third] risk involves choice, and the uncertainty that choice itself entails. Thus

paradoxically, risk, like death and taxes, is one of the few certainties of life.

• Who does it?

Everyone involved in the software process – managers, software engineers and

customers - participate in risk analysis and management

• Why is it important?

Software Project Management (CS615)

333

© Copyright Virtual University of Pakistan

Think about the Boy Scout motto: "Be prepared" Software is a difficult

undertaking. Lots of things can go wrong, and frankly, many often do. It's for this

reason that being prepared, understanding the risks and taking preventive

measures to avoid or manage them is a key element of good software project

management.

• What are the steps?

Recognizing what can go wrong is the first step, called - risk identification. Next,

each risk is analyzed to determine the likelihood that it will occur and the damage

that it will do if it does occur. Once this information is established, risks are

ranked by probability and impact. Finally, a plan is developed to manage those

risks with high probability and high impact.

• What is the work product?

A risk mitigation monitoring and management (RMMM) plan or a set of risk

information sheets is produced.

• How do I ensure that I've done it right?

The risks that are analyzed and managed should be derived from thorough study

of the people, the product, the process and the project. The RMMM should be

revisited as the project proceeds to ensure that risks are kept up to date.

Contingency plans for risk management should be realistic.

9.2 Risk & Change Management Concepts

Foresight is an excellent management quality that can often be cultivated with

experience. Indeed, in many cases, problems can be anticipated.

In such cases, the manager can plan for the possibility that a problem will occur

by estimating its probability, evaluating its impact, and preparing solutions in

advance. This is referred to as an effective means of combating potential

development problems.

Performing risk analysis means being prepared. It is a form of insurance, the basic

idea being that if a problem occurs, a solution is readily available. Like all

insurance, risk analysis usually comes with a price.

The cost of preparing for the occurrence of a problem is primarily the cost of

having the alternative solution at hand while the problem may or may not occur.

In some cases, the cost may be minimal, the time needed to analyze and document

the solution, and the time to track the problem.

In other cases the cost may be substantial, for example, the price of an alternative

piece of development equipment.

Software Project Management (CS615)

334

© Copyright Virtual University of Pakistan

In any case, a problem that has been analyzed and resolved ahead of time is far

simpler to resolve than a problem that occurs unexpectedly.

When risk is considered in the context of software engineering, three conceptual

underpinnings are always in evidence:

– The future is our concern – what risks might cause the software project to go

awry?

– Change is our concern -how will changes in customer requirements,

development technologies, target computers, and all other entities connected

to the project affect timeliness and overall success?

– Last, we must grapple with choices - what methods and tools should we use,

how many people should be involved, how much emphasis on quality is

"enough"?

Risk analysis and management are a series of steps that help a software team to

understand and manage uncertainty. Many problems can plague a software project

A risk is a potential problem - it might happen, it might not But regardless of the

outcome, it's a really good idea to identify it, assess its probability of occurrence,

estimate its impact, and establish a contingency plan should the problem actually

occur.

Any project can encounter uncertainties in the form of increased costs, schedule

delays, and diminished qualities. Unless tackled, these uncertainties can lead to

major project disasters.

The uncertainties encountered during project execution are the potential project

risks. Every software project has to grapple with the new risks threatening

information security along with the conventional risks, such as hardware failure,

time and cost escalation, defects, or resource crunch.

Risk can be defined as the possibility of loss. Risk arises due to the inability to

achieve objectives within defined cost, schedule, and technical constraints.

Risk has two components:

– The possibility of not achieving a particular outcome is one, and

– The result of failing to achieve the outcome is the other

The former is the probability of loss, and the latter is the loss. Software project

management deals with managing both these components of risk.

Risk management focuses the project manager’s attention on those portions of the

project most likely to cause trouble and compromise participants’ win conditions.

Software Project Management (CS615)

335

© Copyright Virtual University of Pakistan

In other words, risk management is a set of actions that helps the project manager

plan to deal with uncertain occurrences. It is through risk management that project

managers assess risks and manage to reduce risks to an acceptable level.

9.3 Types of Risks

To be able to manage project risks, you must first understand what constitutes, a

risk. All uncertain occurrences are not risks.

Only those occurrences that have an adverse impact on the progress of a project

are risks to the project.

Risk is not a bad thing. Risk is bad only when it results in loss for an organization.

Unless there is a potential for loss, there is no risk.

Moreover, loss can be interpreted as either a bad outcome or a lost opportunity.

The tendency of most project managers is to jump at the statement this is a risk.

However, the desired reaction is to pre-empt all possible outcome and plan for

them. Project risks can be broadly categorized into development process risks and

product risks.

i. Development Process Risks

The risks encountered during product development are categorized as

development process risks.

These comprise developer errors, natural disasters, disgruntled employees,

and poor management objectives.

Developer errors could be attributed to poor training due to budgetary

constraints and inadequate skills and software tools.

Ergonomic problems, environment problems, and interruptions or distractions

at office also account for developer risks.

Other risks in this category include problems in personnel acquisition and

retention.

Similarly, natural disasters such as flood, cyclone, fire, storm, and snowfall

are also risks to a project.

Disgruntled employees can also become a risk to an organization. For

example, a sacked employee can use password snuffers to gain unauthorized

access. A dismissed person can flood the system with senseless messages. A

Software Project Management (CS615)

336

© Copyright Virtual University of Pakistan

disgruntled employee can also try to sabotage the project work by destroying

files and programs.

A poorly defined management objective is another development process risk.

If the language in the management objective is ambiguous and not stated

clearly, the risk management program will not function properly.

Narrowly focused and changing objectives that are not updated can also be

counted as risks.

Lack of contingency plans, incomplete cost estimates, and unrealistic

schedules are also potential risks in a project.

Similarly, unrealistic performance standards are also potential risks to the

development process.

Other possible risks include contractual risks, technological risks, and

inadequate documentation of other concurrent projects.

ii. Product Risks

Product risks crop up in the form of changing requirements during product

development.

Incomplete and unclear requirements are a risk to the product during

development.

Similarly, problems in meeting design specifications can also be categorized

as risk to product development.

Risks could arise if the project deliverables or objectives are not clearly

defined or if technical data is missing.

The possibility of several alternatives at any given time during the project is

also a cause of concern. If errors are not recognized during the design phase,

they could turn into risks for the project.

Similarly, risks could arise due to the size and complexity of the product or

while achieving client acceptance of the product.

Note:

The key idea in risk management is not to wait for a risk to materialize and

become a problem. The objective of risk management is to ensure that for

each perceived risk; you know well in advance how to tackle it.

Software Project Management (CS615)

337

© Copyright Virtual University of Pakistan

Risk Management

Risk

Identification

Risk

Analysis

Risk

Mitigation

Risk Probability

Risk Impact

Risk Factor

Risk Avoidance

Risk Monitoring

Contingency

Planning

9.4 Risk Management Process

The process of risk management begins during the analysis phase of software

development life cycle. However, the actual process of managing risks continues

throughout the product development phase.

Risk management is a dynamic process because it deals with the activities that are

yet to happen.

Risk management has a two-fold agenda. First, deciding actions for preventing

risks from happening, and second, deciding actions for tackling risks that

materialize.

Therefore, risk management is all about pre-empting a risk, coming up with a plan

for resolving the risk, and finally executing the plan.

Figure 1 displays the steps of the risk management process. Formally, articulated,

risk management process consists of three steps:

4. Risk identification

5. Risk analysis

6. Risk mitigation

Figure 1: Risk Management Process

Software Project Management (CS615)

338

© Copyright Virtual University of Pakistan

LECTURE# 41

9. Risk and Change Management

9.4 Risk Management Process

i. Risk Identification

Risk Identification involves:

– Identifying risks that may occur on a particular project

– Determining which risks might affect the project

– Documenting their characteristics

Participants in risk identification activities can include the following, where

appropriate:

• Project manager

• Project team leaders

• Project team

• Risk management team if assigned

• Subject matter experts from outside the project team

• Customers

• End users

• Other project managers

• Stakeholders

• Outside risk management experts

Risk Identification is an iterative process because new risks may become known

as the project progresses through its life cycle. The frequency of iteration and who

participates in each cycle will vary from case to case.

The project team should be involved in the process so that they can develop and

maintain a sense of ownership of and responsibility for the risks and associated

risk response actions. Persons outside the team may provide additional objective

information.

The Risk Identification process usually leads to the Qualitative Risk Analysis

process. Alternatively, it can lead directly to the Quantitative Risk Analysis

process when conducted by an experienced risk manager. On some occasions

simply the identification of a risk may suggest its response, and these should be

recorded for further analysis and implementation in the Risk Response Planning

process.

Software Project Management (CS615)

339

© Copyright Virtual University of Pakistan

In this step, the project manager gathers information about the potential risks in

the project. The project manager plans the strategies for avoiding risks or

controlling them.

The project team conducts brainstorming sessions and discussions among team

members about the requirements document. They discuss the available

technology, manpower, prevailing environment, and all project-related factors.

The project manager picks up the thread from these and creates a risk log.

After the risk log is prepared, the project manager calls a meeting within the team

and technical experts to discuss the risk log and the mitigation plans. An effective

way of identifying' risks is using a questionnaire.

One method for identifying risks is to create a risk item checklist. The checklist

can be used for risk identification and focuses on some subset of known and

predictable risks in the following generic subcategories:

a) Product size-risks associated with the overall size of the software to be

built or modified.

b) Business impact-risks associated with constraints imposed by

management or the marketplace.

c) Customer characteristics-risks associated with the sophistication of the

customer and the developer's ability to communicate with the customer in

a timely manner.

d) Process definition-risks associated with the degree to which the software

process has been defined and is followed by the development

organization.

e) Development environment-risks associated with the availability and

quality of the tools to be used to build the product.

f) Technology to be built-risks associated with the complexity of the

system to be built and the newness of the technology that is packaged by

the system.

g) Staff size and experience-risks associated with the overall technical and

project experience of the software engineers who will do the work.

The risk item checklist can be organized in different ways. Questions relevant to

each of the topics can be answered for each software project.

Software Project Management (CS615)

340

© Copyright Virtual University of Pakistan

The answers to these questions allow the planner to estimate the impact of risk. A

different risk item checklist format simply lists characteristics that are relevant to

each generic subcategory.

Finally, a set of "risk components and drivers” are listed along with their

probability of occurrence.

A number of comprehensive checklists for software project risk have been proposed

in the literature (e.g., [SEI93], [KAR96]). These provide useful insight into

generic risks for software projects and should be used whenever risk analysis and

management is instituted. However, a relatively short list of questions [KEI98]

can be used to provide a preliminary indication of whether a project is "at risk."

During risk identification, you obtain answers to the following queries:

a. Why is the risk important?

b. What information is needed to track the status of the risk?

c. Who is responsible for the risk management activity?

d. What resources are needed to perform the activity?

e. What is the detailed plan to improve the risk and / or mitigate it?

Table 1 displays a sample risk identification questionnaire.

Table 1: Sample Risk Identification Questionnaire

SN Yes/No/Not Applicable

(NA)

A. Risk Description

1) Are requirements changing continuously during

product development?

2) Do the changing requirements affect each of the

following:

Quality

Functionality

Schedule

Integration

Design

Testing

3) Are the external interfaces changing?

4) Are the requirements missing or incompletely

specified?

5) Are there any missing requirements?

6) Can these requirements be incorporated into the

system?

7) Does the client have unwritten requirements or

expectations?

Software Project Management (CS615)

341

© Copyright Virtual University of Pakistan

8) Is there a way to capture these requirements?

9) Are requirements unclear or in need of interpretation?

10) Are you able to understand the requirements as

written?

11) Will the requirements lead to the product the client

wants?

12) Are there any requirements that may not specify what

the client really wants?

B. Product Design

1) Do you encounter problem in meeting functionality

requirements?

2) Are there any specified algorithms that may not

satisfy the requirements?

3) Will the design and/or implementation be difficult to

achieve?

4) Are there any requirements or functions that are

difficult to design?

C. Reusability

1) Are you reusing the program?

2) Do you foresee any problems in documentations?

3) Do you foresee any problems in performance?

4) Do you foresee any problems in functionality?

The sample questionnaire in Table 1 includes an exhaustive list of risks that might

be encountered during the progress of a project.

The answers to the questions in the risk identification questionnaire enable the

project manager to estimate the impact of risks.

In the sample questionnaire Table 1, the risks are categorized under product

engineering, product-design, and reusability.

From this table, you obtain a list of risks that are relevant to each category. You

compare the information obtained from this table with past results and estimate

the criticality of risk.

Risk identification is a systematic attempt to specify threats to the project plan

(estimates, schedule, resource loading, etc.).

By identifying known and predictable risks, the project manager takes a first step

toward avoiding them when possible and controlling them when necessary.

There are two distinct types of risks for each of the categories that have been

presented in Section 6.2: generic risks and product-specific risks. Generic risks

are a potential threat to every software project. Product-specific risks can be

Software Project Management (CS615)

342

© Copyright Virtual University of Pakistan

identified only by those with a clear understanding of the technology, the people,

and the environment that is specific to the project at hand. To identify product -

specific risks, the project plan and the software statement of scope are examined

and an answer to the following question is developed: What special characteristics

of this product may threaten our project plan?

Risk Identification involves identifying risks that may occur on a particular

project and determining which risks might affect the project and documenting

their characteristics.

ii. Risk Analysis

After identifying the risks, the project manager needs to analyze the risks.

Uncertainty and loss are the two characteristics of risk.

The uncertainty factor in risk means that the unknown event mayor may not

happen. While analyzing risks, the project manager needs to quantify the level of

uncertainty and the degree of loss.

Based on this, the project manager plans schedules and costs. During analysis,

information on risk is converted into information on decision-making. Analysis

provides the basis for the project manager to work on the “right” risks.

Table 2: Risk Analysis Table

Risk

Description

Probability of

Occurrence

(0 – 1)

Impact on

Project

(1 – 10)

Risk Factor

(Probability x

Impact)

Table 2 displays a risk analysis format. There are various tasks involved in risk

analysis.

First, the WBS elements are identified. One of the tasks in the risk analysis phase

is to describe the risk. The risk can be product-related, process-related,

organization-related, client-related, or infrastructure-related.

Second, the WBS elements are evaluated to determine the risk events.

Then the project manager quantifies the probability of occurrence of risk. The

project manager can assign probability values between 0 and 1. For example, a

risk with a low probability of occurrence is marked 0.2 while that with a high

Software Project Management (CS615)

343

© Copyright Virtual University of Pakistan

probability of occurrence is marked 0.8. The reason why a particular risk has a

high or low probability depends on the actual circumstance of the project.

Third, the risks are rated depending on their probability of occurrence. Based on

the probability of risk, the project manager identifies the impact of the risk. The

impact of risk on cost, schedule, and quantity needs to be calculated and graded.

The impact of risk can be graded on a scale of 1 to 10, 1 being the lowest, and 10

being the highest.

Then the risk factor is calculated by multiplying the probability of risk and the

impact of risk. Finally, each risk is prioritized relative to other risks. The risk

factor is used to prioritize the identified risks. For example, the risk with a

probability value 0.1 and an impact value 2 will have minimal impact. While risks

close to probability value 0.8 and with an impact value 9 will have greater impact.

Therefore, the project manager can prioritize risks based on the probability and

the impact of risks. A risk that has a high impact and low probability will not

absorb a significant amount of the project manager's time. However, high-impact

risks with moderate to high probability will catch the attention of the project

manager.

iii. Risk Mitigation

Risk mitigation is the best possible approach adopted by the project manager to

avoid risks from occurring. The probability of the risk occurring and the potential

impact of the risk can be mitigated by dealing with the problem early in the

project.

Essentially, risk mitigation involves three possibilities and the project manager

needs to adopt a risk mitigation strategy aimed at them. The three possibilities

include:

1. Risk avoidance

2. Risk monitoring

3. Contingency planning

1. Risk Avoidance

To avoid risks from occurring, the project team prepares the risk plan before the

commencement of the project. The project team identifies the potential risks and

prioritizes them based on their probability of occurrence and impact. Then, the

team prepares a plan for managing risks. In most software projects, this plan is

popularly called the risk management plan. Table 3 displays the format of a risk

management plan.

Table 3: Risk Management Plan

Risk

Description

Probability

of

Occurrence

(0 – 1)

Impact

on

Project

(1 –

10)

Risk

Factor

(Probability

x Impact)

Mitigation

Steps Responsibility Start

Date

End

Date

Software Project Management (CS615)

344

© Copyright Virtual University of Pakistan

To prepare the risk management plan, the project team first identifies and assesses

the risks associated with the project.

Then, the probability of occurrence of each risk is estimated and the possible

impact is calculated.

In the plan, the probable cost and damage is also quantified.

The project team also identifies the contingency plans for all the identified risks.

The contingency plan for each risk is based on the project's defined operational

software process. The plan is modified throughout the software development life

cycle of the project based on the changes taking place.

The contingency plan also includes the cost, in terms of effort, in carrying out the

plan. The software risks identified are tracked, reassessed, and re-planned at the

end of each phase.

The project manager revisits the plan if significant changes are introduced in the

software project.

2. Risk Monitoring

As the project proceeds, risk-monitoring activities commence. It is not possible to

monitor closely all the risks that are identified for the project. For example, if 100

risks are identified for a project, only top 20 risks are monitored.

There are re-planning checkpoints where the information obtained from

monitoring the risks is used to refine the risk assessments and management plan.

The project manager monitors the top 20 percent of the factors that may indicate

the status of the risks in the project.

In the case of large teams, the project manager also needs to monitor the attitude

of the team members and their problems. This helps the project manager monitor

any possible team-related risks.

Besides monitoring the top 20 percent of the risks, the project manager needs to

monitor the mitigation steps also.

Software Project Management (CS615)

345

© Copyright Virtual University of Pakistan

Consider an example. To ensure that particular software is browser- independent,

the software is created on the lowest compatible browser. Such software will

work on any browser thus making it browser-independent.

Therefore, mitigating a project risk involves working hard at reducing the

possibility that the risk will ever occur.

Mitigation includes nearly all actions that a project team takes to overcome risks.

For example, choosing a more expensive but proven technology over, a newer,

less expensive technology is a step toward mitigating project risks.

3. Contingency Planning

The possibility of contingency planning arises when mitigation efforts fail and

risk becomes a reality.

Contingency planning is used to monitor risks and invoke a predetermined

response. According to the plan, a trigger is set up. If the trigger is reached, the

contingency plan is put into effect.

Contingency planning involves maintaining an alternative plan if the original plan

fails. A simple example could be the savings people make for a rainy day.

Contingency plans are a must for the top 20 percent of the risks identified. These

plans are put to use after the risks become a reality.

The importance of contingency planning can be realized from this example.

Despite the massive attack on WTC, the stock markets in the US resumed

functioning within a few days. This was possible because the finance companies

had backed up their data and information on computers elsewhere. The

contingency planning of finance companies prevented the risk of huge data loss

for the stock market.

iv. Managing Risks: An Example

Consider a scenario. Your organization is a vendor of software solutions. A bus

transport company the US wants you to develop a Schedule Adherence system.

The team that will develop this software is new and the platform selected for

development is also new to your organization. The project team needs to be

trained intensively for this.

During this project, the team is expected to manage a large volume of data. The

team has never had any experience in managing such a large volume of data. The

system also needs to use this data to generate various MIS reports related to

delays or adherence of bus services.

The performance requirement is less than fifteen seconds for all popular browsers.

Your organization is anticipating numerous requirement changes during the

Software Project Management (CS615)

346

© Copyright Virtual University of Pakistan

development process. The system needs to be implemented across several states

in the country. The data related to the system is highly confidential because it can

provide an edge to the competitors.

Now, as a project manager, you need to prepare a risk management plan for this

project. The project starts on May 15 and should be completed on November 15.

First, you need to identify the potential risks involved in the project. The potential

risks to the project are described in Table 4.

Table 4: Potential Risks to a Project

Risk Description

Inexperienced staff

Performance risk due to high volume of data to be processed

Cross-browser compatibility

Involvement of new technology

Design changes during development

After identifying the risks, you need to estimate the probability of their

occurrence and their impact on product development. Based on this, you calculate

the risk factor and plan the mitigation steps. Your risk management plan is

displayed in Table 5.

Table 5: The Risk Management Plan for Building a Schedule Adherence System

Risk

Description

Probability

of

Occurrence

(0 – 1)

Impact

on

Project

(1 –

10)

Risk

Factor

(Probability

x Impact)

Mitigation

Steps Responsibility Start

Date

End

Date

Inexperience

Staff 0.8 3 2.4 Project

Manager

Conducting

training

sessions before

the need

commencement

of project

May

15

July

15

Performance

risk due to

high volume

of data to be

processed

0.6 7 4.2 Architect

Massive tuning

of architecture

during the

design phase

and conducting

May

15

Till

the

end of

the

project

Software Project Management (CS615)

347

© Copyright Virtual University of Pakistan

a proof of

concepts for

the design

Crossbrowser

compatibility

0.6 5 3.0 Developer

Using the

lowest

compatible

browser for

development

May

15

Till

the

end of

the

project

Involvement

of new

technology

0.5 5 2.5 Project

Manager

Ensuring all

details

pertaining to

the technology

is available and

keeping in

close touch

with the

technology

vendor

May

Till

the

end of

the

project

Design

changes

during

development

0.6 8 4.8 Architect

Designing a

flexible

architecture

that can

accommodate

future changes

and

enhancement

May

15

Till

the

end of

the

project

In Table 5, the risk factors with high values are the high priority risks. Here, the

high priority risks are design changes during development, performance risk due

to high volume of data to be processed, and cross-browser compatibility.

The high priority risks need to be monitored closely and continuously. The rest of

the risks can be monitored periodically.

Certain risks need contingency planning despite being low in the priority list. For

example, the risk due to involvement of new technology is a low priority risk.

However, the probability of occurrence of this risk is 0.5, which is fairly high.

This calls for contingency planning because you may not be aware of all the

details of the new technology. Suppose the system fails to respond if the number

of users exceeds a certain number. In such a situation, you need to have a

contingency plan ready. You need to discuss with the vendor regarding a

workaround for such a situation. The workaround should be ready in the case of

failure of the system.

9.5 Risk Components and Drivers

Software Project Management (CS615)

348

© Copyright Virtual University of Pakistan

The U.S. Air Force [AFC88j has written a pamphlet that contains excellent

guidelines (or software risk 1dentification and abatement. The Air Force approach

requires that the project manager identify the risk drivers that affect software risk

components- Performance, cost, support, and schedule. In the context of this

discussion, the risk components are defined in the following manner:

a) Performance risk - the degree of uncertainty that the product will meet its

requirements and be fit for its intended use.

b) Cost risk - the degree of uncertainty that the project budget will be

maintained.

c) Support risk - the degree of uncertainty that the resultant software will be

easy to correct, adapt, and enhance.

d) Schedule risk - the degree of uncertainty that the project schedule will be

maintained and that the product will be delivered on time.

The impact of each risk driver on the risk component is divided into one of four

impacts categories-negligible, marginal, critical, or catastrophic.

Referring to Figure 2, a characterization of the potential consequences of errors

(rows labeled 1); or a failure to achieve a desired outcome (rows labeled 2) are

described. The impact category is chosen based on the characterization that best

fits the description in the table.

Figure 2: Impact assessment

Components/Category Performance Support Cost Schedule

1 Failure to meet the

requirement would result in

mission failure

Failure results in increased

costs and schedule delays

with expected values of

$500 K

Catastrophic

2 Significant

degradation to

non

achievement

of technical

performance

Non

responsive or

unsupportable

software

Significant

financial

shortages,

budget

overrun

likely

Unavoidable

IOC

Critical 1 Failure to meet the

requirement would degrade

system performance to a point

where mission success is

questionable

Failure results in operational

delays and/or increased costs

with expected $100 K to $

500 K

Software Project Management (CS615)

349

© Copyright Virtual University of Pakistan

2 Some

reduction in

technical

performance

Minor delays

in software

modification

Some

shortage of

financial

resources,

possible

overruns

Possible

slippage in

IOC

1 Failure to meet the

requirement would result in

degradation of secondary

mission

Costs, impacts and / or

recoverable schedule slips

with expected value of $ 1 K

to $ 100 K

Marginal

2 Minimal to

small

reduction in

technical

performance

Responsive

software

support

Sufficient

financial

resources

Realistic

achievable

schedule

1 Failure to meet the

requirement would create

inconvenience or non

operational impact

Error results in minor cost

and / or schedule impact

with expected value of less

than $ 1 K

Negligible

2 No reduction

in technical

performance

Easily

supportable

software

Possible

budget

under run

Early

achievable IOC

Note:

(3) The potential consequence of undetected software errors or faults.

(4) The potential consequence if the desired outcome is not achieved.

9.6 Developing a Risk Table

A risk table provides a project manager with a simple technique for risk

projection. A sample risk table is illustrated below.

Sample risk table prior to sorting

Risks Category Probability Impact RMMM

Size estimate may be significantly low

Larger number of users than planned

Less reuse than planned

End-users resist system

Delivery deadline will be lightened

Funding will be lost

Customer will change requirements

Technology will not meet expectations

Lack of training on tools

Staff inexperienced

Staff turnover will be high

PS

PS

PS

BU

BU

CU

PS

TE

DE

ST

ST

60%

30%

70%

40%

50%

40%

80%

30%

80%

80%

60%

2

3

2

3

2

1

2

1

3

2

2

Software Project Management (CS615)

350

© Copyright Virtual University of Pakistan

Impact values:

l- Catastrophic

2- Critical

3- marginal

4- Negligible

A project team begins by listing all risks (no matter how remote) in the first

column of the table. This can be accomplished with the help of the risk item

check-lists given earlier.

Each risk is categorized in the second column (e.g., PS implies a project size risk,

BU implies a business risk). The probability of occurrence of each risk is entered

in the next column of the table. The probability value for each risk can be

estimated by team members individually. Individual team members are polled in

round-robin fashion until their assessment of risk probability begins to converge.

Next, the impact of each risk is assessed. Each risk component is assessed using

the characterization presented in the sample risk table, and an impact category is

determined. The categories for each of the four risk components - performance,

support, cost, and schedule - are averaged to determine an overall impact value.

Figure 2: Risk and management concern

Once the first four columns of the risk table have been completed, the table is

sorted by probability and by impact. High-probability, high-impact risks percolate

to the top of the table, and low-probability risks drop to the bottom. This

accomplishes first order risk prioritization. The project manager studies the

Disregard

risk factor

1.0

Very

high

High

Management

concern

Impact

Probability

Of

occurrence

Very low

0

Software Project Management (CS615)

351

© Copyright Virtual University of Pakistan

resultant sorted table and defines a cutoff line. The cutoff line (drawn horizontally

at some point in the table) implies that only risks that lie above the line will be

given further attention. Risks that fall below the line are re-evaluated to

accomplish second-order prioritization.

Referring to Figure 2, risk impact and probability have a distinct influence on

management concern. A risk factor that has a high impact but a very low

probability of occurrence should not absorb a significant amount of management

time. However, high-impact risks with moderate to high probability and lowimpact

risks with high probability should be carried forward into the risk analysis

steps that follow.

All risks that lie above the cutoff line must be managed. The column labeled

RMMM contains a pointer into Risk Mitigation, Monitoring and Management

Plan or alternatively, a collection of risk information sheets developed for all risks

that lie above the cutoff.

9.7 Reactive VS. Proactive Risk Strategies

Reactive strategies have been laughingly called the “Indiana Jones School of risk

management” [THO92]. In the movies that carried his name, Indiana Jones, when

faced with overwhelming difficulty, would invariably say, “Don’t worry, I’ll

think of something!” Never worrying about problems until they happened, Indy

would react in some heroic way.

Sadly, the average software project manager is not Indiana Jones and the

members of the software project team are not his trusty sidekicks. Yet, the

majority of software teams rely solely on reactive risk strategies. At best, a

reactive strategy monitors the project for likely risks. Resources are set aside to

deal with them, should they become actual problems. More commonly, the

software team does nothing about risks until something goes wrong. Then, the

team flies into action in an attempt to correct the problem rapidly. This is often

called a fire fighting mode. When this fails, “Crisis Management” [CHA92] takes

over, and the project is in real jeopardy.

A considerably more intelligent strategy for risk management is to be proactive. A

proactive strategy begins long before technical work is initiated. Potential risks

are identified, their probability and impact are assessed and they are ranked by

importance. Then, the software team establishes a plan for managing risk. The

primary objective is to avoid risk, but because not all risks can be avoided, the

team works to develop a contingency plan that will enable it to respond in a

controlled and effective manner.

9.8 Risk Mitigation, Monitoring, and Management

Software Project Management (CS615)

352

© Copyright Virtual University of Pakistan

All of the risk analysis activities presented to this point have a single goal to assist

the project team in developing a strategy for dealing with risk. An effective

strategy must consider three issues:

• risk avoidance

• risk monitoring

• risk management and contingency planning

If a software team adopts a proactive approach to risk, avoidance is always the

best strategy. This is achieved by developing a plan for risk mitigation. For

example, assume that high staff turnover is noted as a project risk, rl Based on

past history and management intuition, the likelihood, ll of high turnover is

estimated to be 0.70 (70 per cent, rather high) and the impact, xl is projected at

level 2. That is, high turnover will have a critical impact on project cost and

schedule.

To mitigate this risk, project management must develop a strategy for reducing

turnover. Among the possible steps to be taken are

• Meet with current staff to determine causes for turnover (e.g., poor working

conditions, low pay, and competitive job market).

• Mitigate those causes that are under our control before the project starts.

• Once the project commences, assume turnover will occur and develop

techniques to ensure continuity when people leave.

• Organize project teams so that information about each development activity is

widely dispersed.

• Define documentation standards and establish mechanisms to be sure that

documents are developed in a timely manner.

• Conduct peer reviews of all work (so that more than one person is “up to

speed").

• Assign a backup staff member for every critical technologist.

As the project proceeds, risk monitoring activities commence. The project

manager monitors factors that may provide an indication of whether the risk is

becoming more or less likely. In the case of high staff turnover, the following

factors can be monitored:

• General attitude of team members based on project pressures.

• The degree to which the team has jelled.

• Interpersonal relationships among team members.

• Potential problems with compensation and benefits.

• The availability of jobs within the company and outside it.

In addition to monitoring these factors, the project manager should monitor the

effectiveness of risk mitigation steps. This is one mechanism for ensuring

continuity, should a critical individual leave the project. The project manager

Software Project Management (CS615)

353

© Copyright Virtual University of Pakistan

should monitor documents carefully to ensure that each can stand on its own and

that each imparts information that would be necessary if a newcomer were forced

to join the software team somewhere in the middle of the project.

Risk management and contingency planning assumes that mitigation efforts have

failed and that the risk has become a reality. Continuing the example, the project

is well underway and a number of people announce that they will be leaving. If

the mitigation strategy has been followed, backup is available, information is

documented, and knowledge has been dispersed across the team. In addition, the

project manager may temporarily refocus resources (and readjust the project

schedule) to those functions that are fully staffed, enabling newcomers who must

be added to the team to "get up to speed." Those individuals who are leaving are

asked to stop all work and spend their last weeks in "knowledge transfer mode.

This might include video-based knowledge capture, the development of

"commentary documents," and/or meeting with other team members who will

remain on the project.

It is important to note that RMMM steps incur additional project cost. For

example, spending the time to "backup" every critical technologist costs money.

Part of risk management, therefore, is to evaluate when the benefits accrued by

the RMMM steps are outweighed by the costs associated with implementing

them. In essence, the project planner performs a classic cost/benefit analysis. If

risk aversion steps for high turnover, it will increase both project cost and

duration by an estimated 15 percent, but the predominant cost factor is "backup,"

management may decide not to implement this step. On the other hand, if the risk

aversion steps are projected to' increase costs by 5 percent and duration by only 3

percent management will likely put all into place.

For a large project, 30 or 40 risks may be identified. If between three and seven

risk management steps are identified for each, risk management may become a

project in itself! For this reason, we adapt the Pareto 80-20 rule to software risk.

Experience indicates that 80 percent of the overall project risk (i.e., 80 percent of

the potential for project failure) can be accounted for by only 20 percent of the

identified risks. The work performed during earlier risk analysis steps will help

the planner to determine which of the risks reside in that 20 percent (e.g., risks

that lead to the highest risk exposure. For this reason, some of the risks identified,

assessed, and projected may not make it into the RMMM plan - they don't fall

into the critical 20 percent (the risks with highest project priority).

9.9 SAFETY RISKS AND HAZARDS

Risk is not limited to the software project itself. Risks can occur after the software

has been successfully developed and delivered to the customer. These risks are

typically associated with the consequences of software failure in the field.

Software Project Management (CS615)

354

© Copyright Virtual University of Pakistan

In the early days of computing, there was reluctance to use computers (and software)

to control safety critical processes such as nuclear reactors, aircraft flight

control, weapons systems, and large-scale industrial processes. Although the

probability .of failure of a well-engineered system was small, an undetected fault

in a computer- based control or monitoring system could result in enormous

economic damage or, worse, significant human injury or loss of life. But the cost

and functional benefits of Computer-based control and monitoring far outweigh

the risk. Today, computer hardware and software are used regularly to control

safety critical systems.

When software is used as part of a control system, complexity can increase by an

order of magnitude or more. Subtle design faults induced by human error-something

that can be uncovered and eliminated in hardware-based conventional

control-become much more difficult to uncover when software is used.

Software safety and hazard analysis [LEV95] are software quality assurance

activities that focus on the identification and assessment of potential hazards that

may affect software negatively and cause an entire system to fail. If hazards can

be identified early in the software engineering process, software design features

can be specified that will either eliminate or control potential hazards.

9.10 THE RMMM PLAN

A risk management strategy can be included in the software project plan or the

risk management steps can be organized into a separate Risk Mitigation,

Monitoring and Management Plan. The RMMM plan documents all work

performed as part of risk analysis and are used by the project manager as part of

the overall project plan.

Some software teams do not develop a formal RMMM document. Rather, each

risk is documented individually using a risk information sheet (RIS) [WIL97]. In

most cases, the RIS is maintained using a database system, so that creation and

information entry, priority ordering, searches, and other analysis may be

accomplished easily. The format of the RIS is illustrated in Figure 6.5.

Once RMMM has been documented and the project has begun, risk mitigation

and monitoring steps commence. As we have already discussed, risk mitigation is

a problem avoidance activity. Risk monitoring is a project tracking activity with

three primary objectives:

1. To assess whether predicted risks do, in fact, occur.

2. To ensure that risk aversion steps defined for the risk are being properly

applied.

3. To collect information that can be used for future risk analysis.

Software Project Management (CS615)

355

© Copyright Virtual University of Pakistan

In many cases, the problems that occur during a project can be traced to more than

one risk. Another job of risk monitoring is to attempt to allocate origin (what

risk(s) caused which problems throughout. the project).

Software Project Management (CS615)

356

© Copyright Virtual University of Pakistan

LECTURE # 42

10. Quality

10.1 Quality Concept

What is it? It's not enough to talk the talk by saying that soft ware quality is

important, you have to (1) explicitly define what is meant when you say 'software

quality, (2) create a set of activities that will help ensure that every software

engineering Work product exhibits high quality, (3) perform quality assurance

activities on every software project, (4) use metrics to develop strategies to

improving your software process and as a consequence the quality of. the end

product.

Who does it? Everyone involved in the software engineering process is

responsible for quality.

Why is it important? You can do it right, or you can do it over again. If a

software team stresses quality in all software engineering activities, it reduces the

amount of rework that it must do that results in lower costs, and more importantly,

improved time-to-market.

What are the steps? Before software quality assurance activities can be initiated,

it is important to define 'software quality' at a number of different levels of

abstraction, Once you understand what quality is, a software team must identify a

set of SQA activities that will filter errors out of work products before they are

passed on.

What is the work product? A Software Quality Assurance Plan is created to

define a software team's SQA strategy. During analysis, design, and code

generation, the primary SQA work product is the formal technical review

summary report. During testing, test plans and procedures are produced. Other

work products associated with process improvement may also be generated.

How do I ensure that I've done it right? Find errors before they become

defects! That is, work to improve your defect removal efficiency, thereby

reducing the amount of rework that your software team has to perform.

SQA encompasses:

(1) A quality management approach

(2) Effective software engineering technology (methods and tools)

(3) Formal technical reviews that are applied throughout the software process

(4) A multi-tiered testing strategy

Software Project Management (CS615)

357

© Copyright Virtual University of Pakistan

(5) Control of software documentation and the changes made to it

(6) A procedure to ensure compliance with software development standards

(when applicable)

(7) Measurement and reporting mechanisms.

Software quality is defined as conformance to explicitly stated functional and

performance requirements, documents, and standards. The factors that affect

software quality are a complex combination of conditions that can be measured

based on data, such as audit-ability, completeness, consistency, error tolerance,

and expandability.1n addition, this data includes hardware independence,

software system independence, modularity, security, and simplicity.

Software quality assurance is a planned and systematic approach necessary to

ensure the quality of a software product. Software reviews filter the product of all

errors. Software reviews can be conducted at all stages in the DLC of a software

product, such as analysis, design, and coding.

Testing is an important element of SQA activity. There are various testing tools to

automate testing process. The SQA plan is used as the template for all SQA

activities planned for a software project and includes details of the SQA activities

to be performed during project execution.

SCM is used to establish and maintain integrity of software items and ensure that

they can be traced easily. SCM helps define a library structure for storage and

retrieval of software items. SCM helps assess the impact of a recommended

change and make decisions depending on the costs and benefits. SCM needs to be

performed at all phases in the DLC of a software project.

The various SCM activities are identifying changes, controlling changes,

controlling versions, implementing changes, and communicating changes. These

activities are independent of the supervision of the project or the product

manager. This is to ensure objectivity in SCM. The scope of SCM is not limited

by code and includes requirements, design, database structures, test plans, and

documentation. SCM procedures vary with the project.

10.2 Producing quality software

As we have seen, one of the main problems in producing quality software is the

difficulty in determining the degree of quality within the software. As there is no

single widely accepted definition for quality, and because different people

perceive quality in different ways, both the developer and the customer must

reach agreement on metrics for quality' (this is discussed in more detail later). The

method of measuring quality may differ for different projects.

Software Project Management (CS615)

358

© Copyright Virtual University of Pakistan

This problem is discussed in a paper by Wesselius and Ververs (1990), in which

they conclude that complete objectivity in quality assessment cannot be achieved.

They identify three distinct components of quality:

􀂃 An objectively assessable component

􀂃 A subjectively assessable component

􀂃 A non-assessable component

The quality of a product is objectively assessable when the characteristics of the

product, as stated in the requirements specification, can be identified.

The quality of a product is subjectively assessable when the characteristics of the

product comply with the customer's expectations.

The quality of a product is non-assessable when it behaves according to our

expectations in situations that have not been foreseen.

Wesselius and Ververs suggest that, for the quality of a software product to be

assessable, as many characteristics as possible should be moved from the

subjective and non-assessable components to the assessable component.

Essentially, this means that the requirements specification must describe as many

measurable characteristics of the product as possible.

Experience supports Wesselius and Ververs' conclusions. Badly defined

requirements are always a source of dispute between developer and customer.

Well-defined, detailed and measurable requirements minimize disputes and

disagreements when the development of the product is complete.

However, many development methods have a prolonged interval between the

specification of requirements and the delivery of the product (refer to Chapter 4

for a discussion of the software development cycle). The determination of quality

should not be postponed until development is complete. Effective software quality

control requires frequent assessments throughout the development cycle. Thus,

effective quality control coupled with a good requirements specification will

clearly increase the quality of the final product.

10.3 Quality Control

Variation control may be equated to quality control. But how do we achieve

quality control? Quality control involves the series of inspections, reviews, and

tests used throughout the software process to ensure each work product meets the

requirements placed upon it.

Quality control includes a feedback loop to the process that created the work

product. The combination of measurement and feedback allows us to tune the

Software Project Management (CS615)

359

© Copyright Virtual University of Pakistan

process when the work products created fail to meet their specifications. This

approach views quality control as part of the manufacturing process.

Quality control activities may be fully automated, entirely manual, or a

combination of automated tools and human interaction. A key concept of quality

control is that all work products have defined; measurable specifications to which

we may compare the output of each process. The feedback loop is essential to

minimize the defects produced.

10.4 Quality Control Myths

The establishment of effective quality control frequently encounters various

misconceptions and myths, the most common of which is related to the cost

effectiveness of quality control. Cobb and Mills (1990) list several of these myths,

and suggest methods of combating them. Two of the more prevalent myths

identified by Cobb and Mills are described below.

Myth: Quality costs money. This is one of the most common myths (not only in

software development). In fact, quality in software usually saves money. Poor

quality breeds failure. There is a positive correlation between failures and cost in

that it is more expensive to remove execution failures designed into software than

to design software to exclude execution failures.

Myth: Software failures are unavoidable. This is one of the worst myths

because the statement is partly true, and is therefore often used as an excuse to

justify poor quality software. The claim that ‘there is always another bug' should

never be a parameter in the design or implementation of software.

As these myths lose ground in modern approaches to software development, the

demand for suitable quality control standards and procedures increases. The IEEE

issued their first standard for software quality assurance plans in 1984 (IEEE

.1984), followed by a detailed guide to support the standard, issued in 1986. The

US Department of Defense issued a separate standard 2168 for defense systems

software quality programs (DOD 1988b), which forms a companion to the famous

US DOD standard 2167A (DOD 1988a) for defense systems software

development. The European ISO standard 9000-3, of 1990 (ISO 1990) gives a

broader meaning to the term quality assurance and covers configuration control

too.

10.5 Resources for quality control

When the SQA mandate includes configuration control activities, the required

resources will also include those required for configuration control. Merging SQA

and configuration control is not uncommon, and can eliminate some duplication

of assignments and activities. Two alternative organizational charts are shown in

Software Project Management (CS615)

360

© Copyright Virtual University of Pakistan

Fig. 8.5. Note that for small projects, merging the two groups may mean simply

assigning both responsibilities to the same person.

Though many tools are common to quality control and configuration control, few

tools are specifically designed for quality control. The following are some of the

general support tools that can be useful in supporting SQA activities:

• Documentation utilities

• Software design tools

• Debugging aids

• Structured preprocessors

• File comparators

• Structure analyzers

• Standards auditors

• Simulators

• Execution analyzers

• Performance monitors

• Statistical analysis packages

• Integrated CASE tools

• Test drivers

• Test case generators

These tools support quality control in all phases of software development.

Documentation aids can provide partially automatic document writers, spelling

checkers and thesauruses etc. Structured preprocessors (such as the UNIX utility

lint) are useful both to standardize code listings. And to provide additional

compile-time warnings that compilers often overlook. Early warnings regarding

possible execution time problems can be provided by simulators, execution time

analyzers and performance monitors. Substantial software system testing can

often be performed automatically by test suite generators and automatic test

executors.

All SQA tools to be used during software development should be identified and

described in the SQA plan. This plan includes a description of all required quality

assurance resources and details of how they will be applied. Thus, at the start of

the project SQA resources can be budgeted and procured as part of the required

project development resources.

Software Project Management (CS615)

361

© Copyright Virtual University of Pakistan

(a)

(b)

10.6 Quality Assurance

Quality assurance consists of the auditing and reporting functions of

management. The goal of quality assurance is to provide management with the

data necessary to I be informed about product quality, thereby gaining insight and

confidence that product quality is meeting its goals. Of course, if the data

provided through quality assurance identify problems, it is management's

responsibility to address the problems, and apply the necessary resources to

resolve quality issues.

Software Quality Assurance

Even the most jaded software developers will agree that high-quality software is

an important goal. But how do we define quality? A wag once said, 'Every

program does something right, it just may not be the thing that we want it to do.'

Project manager

Configuration

control

CC manage

Software quality

control

OC manager

Project manager

Software quality

assurance SQA

Configuration

control

Software quality

control

Software Project Management (CS615)

362

© Copyright Virtual University of Pakistan

Many definitions of software quality have been proposed in the literature. For our

purposes, software quality is defined as:

Conformance to explicitly stated functional and performance requirements,

explicitly documented development standards, and implicit characteristics that

are expected of all professionally developed software.

There is little question that this definition could be modified or extended. In fact,

a definitive definition of software quality could be debated endlessly. For the

purposes of this book, the definition serves to emphasize three important points:

1. Software requirements are the foundation from which quality is measured.

Lack of conformance to requirements is lack of quality.

2. Specified standards define a set of development criteria that guide the manner

in which software is engineered. If the criteria are not followed, lack of

quality will almost surely result.

3. A set of implicit requirements often goes unmentioned (e.g., the desire for

ease of use and good maintainability). If software conforms to its explicit

requirements but fails to meet implicit requirements, software quality is

suspect.

Background Issues

Quality assurance is an essential activity for any business that produces products

to be used by others. Prior to the twentieth century, quality assurance was the sole

responsibility of the craftsperson who built a product. The first formal quality

assurance and control function was introduced at Bell Labs in 1916 and spread

rapidly throughout the manufacturing world. During the 1940s, more formal

approaches to quality control were suggested. These relied on measurement and

continuous process improvement as key elements of quality management.

Today, every company has mechanisms to ensure quality in its products. In fact,

explicit statements of a company's concern for quality have become a marketing

ploy during the past few decades.

The history of quality assurance in software development parallels the history of

quality in hardware manufacturing. During the early days of computing (1950s

and 1960s), quality was the sole responsibility of the programmer. Standards for

quality assurance for software were introduced in military contract software

development during the 1970s and have spread rapidly into software development

in the commercial world [IEE94].

Software Project Management (CS615)

363

© Copyright Virtual University of Pakistan

Extending the definition presented earlier, software quality assurance is a planned

and systematic pattern of actions [SCH98] that are required to ensure high quality

in software.

The scope of quality assurance responsibility might best be characterized by

paraphrasing a once-popular automobile commercial:

Quality is Job # 1'. The implication for software is that many different

constituencies have software quality assurance responsibility-software engineers,

project managers, customers, salespeople, and the individuals who serve within an

SQA group.

The SQA group serves as the customer's in-house representative. That is, the

people who perform SQA must look at the software from the customer's point of

view. Has software development been conducted according to pre-established

standards? Have the technical disciplines properly performed their roles as part of

the SQA activity? The SQA group attempts to answer these and other questions to

ensure that software quality is maintained.

SQA Activities

Software quality assurance is composed of a variety of tasks associated with two

different constituencies-the software engineers who do technical work and an

SQA group that has responsibility for quality assurance planning, oversight,

record keeping, analysis, and reporting. 'If Software engineers address quality and

perform quality assurance and quality control activities by applying solid

technical methods and measures, conducting formal technical reviews, and

performing well-planned software testing.

The charter of the SQA group is to assist the software team in achieving a highquality

end product. The Software Engineering Institute [PAU93] recommends a

set of SQA activities that address quality assurance planning, oversight, record

keeping, analysis, and reporting.

These activities are performed (or facilitated) by an independent SQA group that:

1. Prepares SQA plan for a project

The plan is developed during project planning and is reviewed by all

interested parties. Quality assurance activities performed by the software

engineering team and the SQA group are governed by the plan. The plan

identifies

• evaluations to be performed

• audits and reviews to be performed

• standards that are applicable to the project

Software Project Management (CS615)

364

© Copyright Virtual University of Pakistan

• procedures for error reporting and tracking

• documents to be produced by the SQA group

• amount of feedback provided to the software project team

2. Participates in the development of the project's software process

description

The software team selects a process for the work to be performed. The SQA

group reviews the process description for compliance with organizational

policy, internal software standards, externally imposed standards (e.g., ISO-

900 I), and other parts of the software project plan.

3. Reviews software engineering activities to verify compliance with the

defined software process. The SQA group identifies, documents, and tracks

deviations from the process and verifies that corrections have been made.

4. Audits designated software work products to verify compliance with

those defined as part of the software process. The SQA group reviews

selected work products; identifies, documents, and tracks deviations; verifies

that corrections have been made; and periodically reports the results of its

work to the project manager.

5. Ensures that deviations in software work and work products are

documented and handled according to a documented procedure.

Deviations may be encountered in the project plan, process description, -

applicable standards, or technical work products.

6. Records any noncompliance and reports to senior management.

Noncompliance items are tracked until they are resolved.

In addition to these activities, the SQA group coordinates the control and

management of change and helps to collect and analyze software metrics.

10.7 SQA Plan

The SQA plan serves as the template for SQA activities planned for each software

project. The SQA group and the project team develop the SQA plan. The initial

two sections of the plan describe the purpose and references of the SQA plan. The

next section records details of the roles and responsibilities for maintaining

software product quality.

The Documentation section of the SQA plan describes each of the work products

produced during the software process. This section defines the minimum set of

work products that are acceptable to achieve high quality. The Documentation

section consists of:

Software Project Management (CS615)

365

© Copyright Virtual University of Pakistan

– Project document such as project plan, requirements document, test cases, test

reports, user manual, and administrative manuals

– Models such as ERDs, class hierarchies

– Technical document such as specifications, test plans

– User document such as help files

All applicable standards to be used in the project are listed in the Standards and

Guidelines section of the SQA plan. The standards and practices applied are the

document standards, coding standards, and review guidelines.

Example of the contents of a software quality assurance plan

1. Software quality assurance organization and resources

Organization structure.

Personnel skill level and qualifications

Resources

2. SQA standards, procedures, policies and guidelines

3. SQA documentation requirements

List of all documentation subject to quality control

Description of method of evaluation and approval

4. SQA software requirements

Evaluation and approval of software

Description of method of evaluation

Evaluation of the software development process

Evaluation of reused software

Evaluation of non-deliverable software

5. Evaluation of storage, handling and delivery

Project documents

Software

Data files

6. Reviews and audits

7. Software configuration management (when not addressed in

a separate document)

8. Problem reporting and corrective action

9. Evaluation of test procedures

10. Tools techniques and methodologies

11. Quality control of subcontractors, vendors and suppliers

12. Additional control

Miscellaneous control procedures

Project specific control

13. SQA reporting, records and documentation.

Status reporting procedures

Maintenance

Software Project Management (CS615)

366

© Copyright Virtual University of Pakistan

Storage and security

Retention period

10.8 Software quality metrics

Much attention has been devoted to questions associated with the measurement of

quality. How do we determine the extent to which a software product contains this

vague attribute called quality? When is the quality of a software product high and

when is it low?

One of the more recent developments in quality assurance (not only for software)

is the realization that quality is not a binary attribute that either exists or does not

exist. Kaposi and Myers (1990), in a paper on measurement-based quality

assurance, have stated their belief that 'the quality assurance of products and

processes of software engineering must be based on measurement 7. The earlier

the measurement of quality begins, the earlier problems will be located. Cohen et

al. (1986), in addressing the cost of removing errors during the early phases of

software development, proclaim the existence of the famous exponential law8.

Software Project Management (CS615)

367

© Copyright Virtual University of Pakistan

The quality of two products can be compared, and it is perfectly acceptable to

claim that the quality of one product is greater than the quality of another. It is

also acceptable to measure quality and deduce the extent of expected faults based

on the measured result.

The set of measurable values associated with the quality of a product is referred to

as the product's quality metrics. Software quality metrics can be used to determine

the extent to which a software product meets its requirements. The use of quality

metrics increases the objectivity of the evaluation of product quality. Human

evaluation of quality is subjective, and is therefore a possible source of

disagreement, particularly between customer and developer.

A number of methods for establishing software quality metrics are currently being

developed, though no generally accepted standard has yet emerged. For example,

an initial draft of IEEE Std-1061 (1990) includes a detailed discussion of software

quality metrics in general, including a suggested methodology for applying

metrics, and many examples and guidelines. Quality metrics, once defined, do

indeed increase objectivity, but the definition itself is not necessarily objective

and greatly depends upon the needs of the organization that produces the

definition.

The basic approach for applying software quality metrics requires:

• The identification of all required software quality attributes. This is usually

derived from the software requirements specification.

• Determinations of measurable values to be associated with each quality

attribute. A description of the method by which each measurable value will be

measured.

• A procedure for documenting the results of measuring the quality of the

software product.

A set of many values can be used to determine the overall quality of a software

product. However, a single measure can be created to represent the overall quality

of the software product. This requires:

• A weighted method for combining the measured quality attributes into a

single measure of quality for the product.

Some examples of software metrics are:

Reliability: The percentage of time that the system is successfully operational

(e.g. 23 out of 24 hours produces: 100 x (23/24) percent)

Recoverability: The amount of time it takes for the system to recover after failure

(e.g. 1hour to reload from backups and 30 minutes to reinitialize the system)

Software Project Management (CS615)

368

© Copyright Virtual University of Pakistan

User-friendliness: The amount of training time needed for a new user

The measurement of software quality should not be performed only at the end of a

project. The degree of quality should be measured at regular intervals during

development. Thus, any major reduction in the overall measure of quality should

act as a warning for the project manager that collective action is required. High

quality at the end of the project is achieved by assuring high quality throughout

the development of the project.

10.9 Some general guidelines

The basic software quality assurance activities cover the review and approval of

the development methodology, the software and documentation, and the

supervision and approval of testing. Other SQA activities, such as the supervision

of reviews, the selection and approval of development tools, or the administration

of configuration control, depend on the way SQA is adapted to a specific project.

The size of the project is usually the determining factor. The following guidelines

discuss some of the parameters to be considered for different types of project

when planning SQA.

• In small projects, many SQA activities can be performed by the project

manager. This includes the organization and supervision of reviews and

audits, the evaluation and selection of development tools, and the selection

and application of standards.

• Test procedures and testing are always best when conducted by a separate

independent team (discussed later). The decision on whether supervision of

testing activities can be assigned to SQA depends on many factors, including

the independence of the SQA team, the size of the project and the 'complexity

of the project.

• When testing is performed by an independent test team, SQAS involvement

will be minimal. In most other cases it will be the responsibility of the SQA

team to plan and supervise the testing of the system.

• As a general guideline, it is usually undesirable for SQA to be performed by a

member of the development team. However, small projects often cannot

justify the cost of a dedicated SQA engineer. This problem can be solved by

having a single SQA engineer responsible for two or three small projects (with

each project funding its share of the SQA services).

One additional guideline is based on the conclusions of Wesselius and Ververs

(1990) for the application of effective quality control:

Software Project Management (CS615)

369

© Copyright Virtual University of Pakistan

• The ability to control software quality is directly linked to the quality of the

software requirements specification. Quality control requires the unambiguous

specification of as many of the required characteristics of the software product

as possible.

Software Project Management (CS615)

370

© Copyright Virtual University of Pakistan

Lecture # 43

11. Application Tools

11.1 Managing Tasks in Microsoft Project 2000

Project management is a highly specia1ized and professional task. The chances

that a project can go haywire are very high because project management includes

numerous activities, such as planning, resource allocation, risk management, and

estimation. You can automate all these activities using a tool, Microsoft Project

2000. Activities such as project planning, resource and cost allocation, and project

tracking can be done easily using the various user-friendly features of Microsoft

Project 2000.

Microsoft Project 2000 is a popular project management tool that also enables you

to schedule and track your project plan. In Microsoft Project, every unit of work,

which consumes effort, time, and money, is called a task. You use Microsoft

Project to specify tasks and the expected duration of each task. Using the taskrelated

information, Microsoft Project prepares a project schedule. The schedule

displays a plan consisting of the start and end dates of each task.

In addition, it plots a pictorial Gantt chart. The Gantt chart view depicts the

extension of tasks across days along with the corresponding resources.

11.2 Creating Tasks

To manage a project efficiently, it is important to treat the project as a

decomposable entity that can be analyzed and resolved. A problem first needs to

be broken into units and then analyzed for solutions because it is always easier to

focus on micro level units. Microsoft Project enables you to perform these tasks.

It assumes that you have performed the WBS exercise for the project. The WBS

exercise helps you to come up with indivisible units called tasks. Therefore, a task

is an activity that has a defined start and end dates.

For example, XYZ Inc. has to develop an ERP project. They plan to complete the

project in five phases: analysis, design, development, testing, and implementation.

During the analysis phase, the WBS exercise is performed and a list of tasks is

defined for each of the subsequent phases. Using Microsoft Project, you can

create tasks for each phase, specify their duration, and assign resources to them.

You can also set relationships between tasks to identify the successor and

predecessor tasks.

11.3 Types of Tasks

Software Project Management (CS615)

371

© Copyright Virtual University of Pakistan

Microsoft Project enables you to create three types of tasks:

• General

• Milestone

• Recurring

General Tasks

General tasks are the usual tasks that are independent and have no special

characteristics related to their duration or time. For example, Analysis is a general

task that XYZ Inc. plans to conduct. To create the Analysis task, you can use the

Project menu on the Microsoft Project worksheet. The steps to create the Analysis

task are as follows.

1. Click the Project menu.

This displays the Project menu that contains all the task-related commands. Figure

11.1 displays the Project menu.

Figure 11.1: Project Menu

Software Project Management (CS615)

372

© Copyright Virtual University of Pakistan

2. Click the Task information command on the Project menu.

This displays the Task Information dialog box where you specify the

details of the task being created.

As shown in Figure 11.2, the Task Information dialog box contains five

tabs: General, Predecessors, Resources, Advanced, and Notes. You use

the General tab of the Task Information dialog box because you need to

create a general task. The other tabs have specific purposes for each task.

For example, you can specify the details for a task by using the Advanced

tab. For the same task, you can use the Notes tab to add notes.

Figure 11.2: Different Tabs in the Task Information Box

Tip: In addition to the access key I, you can display the Task Information dialog

box by using the Shift and F2 shortcut key combination.

3. Type Analysis in the Name text box.

4. Specify the duration of the Analysis task as 5d in the Duration text box.

The duration of a task signifies the period for which the task lasts in a project

schedule. The start date is preset as the current date unless you enter a specific

date. The finish date for the task is displayed as five days after the current date

in the Gantt chart view. Duration can be specified in minutes, hours, days,

weeks, months, or years.

Software Project Management (CS615)

373

© Copyright Virtual University of Pakistan

If you are not sure of a confirmed duration, you can specify an estimated

duration of a task.

Figure 11.3 displays the Task Information dialog box where task details

are specified.

Figure 11.3: Task Information Dialog Box

Tip: To specify an estimated duration for a particular task, you can precede or

succeed the duration with a question mark. Alternately, you can select the

Estimated check box next to the Duration text box.

5. Click OK to confirm the details provided by you.

After a task is created, you; can specify the subtasks below it. For example,

Project scope determination is a subtask of the Analysis task. To specify the

subtask, you first create the Project scope determination subtask by using the

Task information dialog box. Next, you specify a summary designation for the

Analysis task. A summary designation indicates that the task represents a

parent task for a group of related tasks below it. The start date of a summary

task is the start date of the first subtask. Similarly, the finish date of the

summary task is the finish date of the last subtask under the summary task.

To designate Analysis as the summary task, perform the following steps:

Software Project Management (CS615)

374

© Copyright Virtual University of Pakistan

1. Create a task named Project scope determination using the Project

menu.

You need to create this task below the Analysis task.

2. Select the Project scope determination task.

3. Click the Indent icon on the Formatting toolbar.

The Indent icon is the green arrow pointing towards right. Clicking this icon

indents the selected task to the right. Notice in Figure 11.4 that Microsoft

Project formats the summary task in bold. Alternatively, you can use the left

indent icon to make the Analysis task as a summary task.

Figure 11.4: Creating Summary Tasks

Similarly, you create the rest of the tasks listed in the project plan of XYZ Inc.

and specify subtasks below them. You store the list of tasks and their details in a

file with an extension .mpp in Microsoft Project.

Milestone Tasks

Milestone tasks are the second type of tasks that you can create using Microsoft

Project. These tasks have no duration. They serve as markers or reference nodes

for significant accomplishments in a project. Examples of a milestone task are

project startup, project end, pilot implemented, and SRS document sign off.

Creating a milestone task is similar to creating any other task. The only difference

is that after the task is created, you select an additional option named Mark task as

milestone in the Task Information dialog box.

Software Project Management (CS615)

375

© Copyright Virtual University of Pakistan

For example, in the analysis phase, XYZ Inc. has a milestone task named

Analysis Complete. To indicate that Analysis Complete is a milestone task,

perform the following steps.

1. Click the Advanced tab in the Task information dialog box.

This tabbed page contains specialized options that enable you to create

milestone tasks. It also contains options to specify constraints and deadlines.

2. Type Analysis Complete in the Name text box.

3. Select the Mark task as milestone check box.

You do this to specify a task as a milestone task.

4. Click OK to close the Task Information dialog box.

Figure 11.5 displays the Mark task as milestone check box selected.

Figure 9.5: Creating Milestone Tasks

A milestone task is displayed as a task with no duration next to it in the Gantt

chart view. Similarly, you create other milestone tasks in the Project file.

Recurring Tasks

Recurring tasks, as the name suggests, occur repeatedly at regular intervals. For

example, a weekly project meeting with all the team members is a recurring task.

You can schedule a recurring task in a project plan cycle as daily, weekly

monthly, or yearly. You make this selection after deciding the seriousness of the

Software Project Management (CS615)

376

© Copyright Virtual University of Pakistan

nature of the task. The seriousness of the nature of the task determines how often

the task needs to recur.

For example, if it is a simple meeting to take stock of the situation, you can select

the weekly option. Similarly, you can annually schedule a high level meeting of

the board of directors. However, if an ongoing project is faltering due to frequent

slippages, you need to closely monitor the activities of the project. To monitor the

project activities effectively, you can convene a meeting every day.

You can also schedule the start and end dates of a recurring task. For example, for

XYZ Ltd. you need to create the recurring task Project Meeting under the

Analysis task. The Project Meeting task recurs every Friday until March 14,

which is the project end date. You can create this task by using the Insert menu,

and then specify the details in the Recurring Task Information dialog box. To

create the recurring task you perform the following steps.

1. Select the task row where you want the task to appear.

2. Click the Insert menu.

3. Click the Recurring Task command to display the Recurring Task Information

dialog box.

4. Type Project meeting in the Name text box.

5. Select the Friday check box in the Recurrence pattern group box. This step

specifies that the task should recur every Friday. Note that the Weekly option

button is selected by default.

6. Click the End by option button.

This ensures that the weekly task should continue only until February 14. Figure

11.6 displays this step.

Software Project Management (CS615)

377

© Copyright Virtual University of Pakistan

Figure 9.6: Creating Recurring Tasks

7. Select February 14 from the calendar.

8. Click OK to close the Recurring Task Information dialog box.

A recurring task appears with a special circular arrow symbol in the indicator

field. In the Gantt chart view, it appears at intervals on all the days it is scheduled

until the last date specified.

11.4 Adding Constraints to Tasks

Constraints are defined as1illitations that negatively affect the schedule and

quality of a project. Some of the typical project constraints are mentioned below:

􀂃 Duration of a project

􀂃 Resources of a Project

􀂃 Performance goals of a project

A constraint also affects other constraints. For example, you may need more

resources if you reduce the project duration. You may also have to forgo some of

the goals and features of the project if you decide to reduce the project duration.

Therefore, it is important that you decide the tradeoff judiciously.

In Microsoft Project, you can specify constraints as limitations that are enforced

on a task. For example, you can specify that a task must start on a particular date

or not finish later than a particular date. Therefore, schedule-related constraints

are available in Microsoft Project.

• As soon as possible (ASAP)

• As late as possible (ALAP)

• Start no later than (SNLT)

• Finish on later than (FNLT)

• Start no earlier than (SNET)

• Finish no earlier than (FNET)

• Must start on (MSO)

• Must finish on (MFO)

ASAP

When you use this constraint, Microsoft Project schedules a specific task as early

as possible. For this reason you do not mention a specific date for such a task.

Microsoft Project automatically assigns this constraint when you schedule a new

task from the start date of a project. To change this constraint to a specific

constraint, you can assign a specific start date to it.

ALAP

When you use this constraint, Microsoft Project schedules a specific task as late

as possible. This is the reason why no specific date is mentioned for such a task.

Software Project Management (CS615)

378

© Copyright Virtual University of Pakistan

Microsoft Project automatically assigns this constraint when you schedule a new

task from the finish date of a project. To change this constraint to a specific

constraint, you can assign a specific finish date to it.

SNLT

You select this constraint to specify the latest possible start date of a task. For

example, you want to conduct a training program on quality standards for the

development team. You want to conduct the training program before the

development phase begins so that you have enough time on hand. Therefore, you

select the SNLT constraint and specify the start date that is before the start of the

development phase. This means the training begins on or before the specified

date. You also keep in mind the duration of the training. Suppose it is a two-day

training program and the project development start date is February 15. Therefore,

after selecting the SNLT constraint, you will enter the start date of the training as

February 13.

FNLT

You select this constraint to specify the latest possible date by which a task can be

completed. For example, you want the project proposal task to be completed on or

before the analysis phase, which is scheduled to start from February 20.

Consequently, by enforcing this constraint on the project proposal task, you

ensure that the finish date for this task is the same as the start date for the analysis

phase.

SNET

This constraint enables you to schedule the start date of a task as early as possible.

This is different from the ASAP constraint because the ASAP is a vague

constraint with no specific start dates for a task. However, by choosing the SNET

constraint, you can specify an early start date for a task. For example, the task to

create test cases is dependent upon the construction and the unit testing phases.

Therefore, the task to create test cases cannot begin unless the earlier two tasks

are over. In this case, you would enforce the SNET constraint on the creation of

test cases and specify a start date. This start date cannot be before the end date of

the preceding tasks. Consequently, you can create test cases any time on or after

this start date but not before.

FNET

You select this constraint when you do not want a task to be complete before a

scheduled finish date. For example, during the unit-testing task you discover there

were many bugs that were addressed by the developers. This makes you skeptical

about the quality of the product. Therefore, you want to extend the finish date of

unit testing and enforce the constraint FNET on it. Consequently, you will not be

able to finish the unit-testing task before the specified date.

Software Project Management (CS615)

379

© Copyright Virtual University of Pakistan

MSO

This constraint indicates that you must begin a task only on the specified start date

and not later or before that. This is an inflexible constraint. It is usually enforced

during a short cycle duration project when you are unsure whether each task

mayor may not start on time. This may disturb the planned schedule of the entire

project. You can enforce the MSO constraint for critical projects depending upon

client requirements.

MFO

If you use the MSO constraint, it is most likely that you would use the MFO

constraint also. Using the MFO constraint enables you to focus on completing a

particular task. It is useless if you enforce a strict start date with no strict finish

date for completing a task. You can again enforce this constraint for critical

projects depending upon client requirements.

You enforce or use a constraint on a task by specifying the details in the advanced

page of the Task Information dialog box. In that dialog box, you can also specify

the start and the end dates of a constraint depending upon the type of constraint

that you choose.

For example, for XYZ Inc. you need to add a constraint to the Develop test plans

task. This task is a subtask of the Testing task. After creating both the tasks, you

specify the duration of the Develop test plans task. You want that the task should

not carry on for more than two days. You also need to impose a constraint that the

task should not finish later than August 10. However, the management would

appreciate if the task finishes before that.

To add the constraint to the Develop test plans task, you use the constraints

feature in the Task Information dialog box. To access the constraints feature, you

perform the following steps:

1. Click the Advanced tab in the Task Information dialog box.

2. Type Develop test plans in the Name text box of the Advanced tabbed page.

3. Type 2 in the Duration text box

This specifies the maximum time allotted to complete the task. 4. Click the

Constraint type box.

4. Click the Constraint type box.

5. Select the Finish No Later Than option in the displayed list.

6. Click the Constraint date list.

7. Select August l0 as the finish date from the calendar that is displayed.

Figure 9.7 displays this step.

Software Project Management (CS615)

380

© Copyright Virtual University of Pakistan

Figure 9.7: Adding Constraints

8. Click OK to close the Task Information dialog box.

The Develop test plans task is displayed with an icon for Finish No Later Than

constraint in the Task sheet of the Gantt chart view.

Tip:

After specifying a constraint type and its date, it is a good idea to specify the

details of choosing a particular constraint type and its date. Subsequently, you

may want to share this information with your colleagues in meetings. This can be

done by clicking the Notes tab in the Task Information dialog box and entering

your comments.

11.5 Adding Deadlines to Tasks

Deadlines are strict finish dates for a particular task. Microsoft Project considers a

deadline to be a target date to complete a task. You add a deadline to a specific

task if you track the progress of that task. Setting realistic deadlines to tasks also

enables you to schedule the subsequent tasks.

Deadlines are important because they depict the finish date of a task. Therefore,

you can track whether a task has exceeded the planned time or is completed

before time. If the task is taking longer than expected, you can take remedial

measures such as adding resources. Adding deadlines does not affect project

schedule nor does it enforce a date constraint. However, it marks a task that has

crossed its deadline with an indication mark next to it.

Software Project Management (CS615)

381

© Copyright Virtual University of Pakistan

In the .mpp file that you are creating for XYZ Inc., you need to set July 15 as the

deadline for the task Assign development staff; which is a subtask of the

Development task. To set the deadline, you perform the following steps:

1. Create the task Assign development staff by using the Project menu.

2. Select the Assign development staff task.

This is the task for which you need to set a deadline.

3. Click the Advanced tab in the Task Information dialog box.

4. Click the Deadline list box in the Advanced page.

This is done to specify the deadline for the Assign development staff task.

5. Select July 15 in the calendar to specify the deadline date.

6. Click OK to close the Task Information dialog box.

Similarly, you can add deadlines for the other tasks for the XYZ Inc. project.

11.6 Setting Dependencies between Tasks

There is dependency between tasks when a particular task cannot begin until its

preceding task is completed. For example, the creation of the high-level design of

a project cannot start until the client signs off the SRS document. The SRS

document serves as a prerequisite for the immediate subsequent phase.

In Microsoft Project, you can specify four types of dependencies:

• Finish-to-Start (FS)

• Start-to-Start (SS)

• Finish-to-Finish (FF)

• Start-to-Finish (SF)

FS

In dependency relationships of tasks, the name of the relationship consists of the

start or finish dates of the predecessor task and the start or finish date of the

successor task. For example, the relationship between the task to finish the SRS

document and the task to begin the high level design is FS. This is because you

link the finish status of the predecessor task to the start status of the successor

task. FS is the default relationship when you link any two tasks.

SS

In addition to FS, you can also begin two tasks at the same time. For example,

you can begin the task to do functional testing and integration testing of the

testing phase simultaneously. The dependency in a SS relationship occurs when

both the predecessor and the successor tasks start at the same time. This is

because these tasks do not share any common component nor are they dependent

on each other. Therefore, the link between them is SS.

Software Project Management (CS615)

382

© Copyright Virtual University of Pakistan

FF

You can also begin two tasks that finish simultaneously. In such a case, the

dependency relationship between the two tasks is called an FF relationship. For

example, the task to prepare a checklist for implementing a software product

cannot end unless implementation testing for that software product is complete.

SF

Finally, you can have a SF relationship between tasks. This relationship indicates

that a task cannot end until its preceding task starts. This relationship usually

takes place when a project is scheduled from the project finish date. This

relationship helps to minimize the risk of delay of a predecessor task if the

successor task is dependent on the start of the predecessor task. For example, the

testing phase can only start after the coding phase is complete.

11.7 Lag and Lead Time between Tasks

While adding dependencies to tasks, you can also specify lag and lead times for

any two interdependent tasks. Lag time is defined as the excess time that is

allowed to lapse between predecessor and the successor tasks. This results in a

delay in the start of the successor task. For example, you may use this option if

you feel that the tasks of the analysis phase are taking more than the planned time

to complete. Consequently, you might not want to start the high--level design task

as planned but postpone it. In this case, you would calculate the maximum lag

time for the high-level design to start.

You specify the lag time for a task as a positive value in the Lag field cell of the

Predecessors page. This page exists in the Task Information dialog box.

Lead time is defined as the overlap that exists between two dependent tasks. For

example, you could decide to start testing units when developers have partially

completed creating the applications for a project. Therefore, you move ahead of

the schedule of a successor task before time.

You specify the lead time for a task as a negative value in the same Lag field cell

of the Predecessors page. This page exists in the Task Information dialog box.

Consider an example to link two tasks, procuring resources and drafting a project

plan. According to the plan, securing resources is a predecessor task while drifting

a project plan is a successor task. You need to link the two tasks using the start-tofinish

relationship because it is anticipated that the task to draft a plan cannot start

before the resources are procured and incorporated in the project plan. During the

course of the project, you feel that the successor task cannot begin as planned

because procuring resources is too time-consuming. You analyze and deduce that

the project plan can only be drafted four days after resources are procured.

You link the two tasks by using the Edit menu. After linking the two tasks, you

set the type of relationship as start-to finish. Assume that for the XYZ Inc:

Software Project Management (CS615)

383

© Copyright Virtual University of Pakistan

project, you need to link the Develop code and Developer primary testing tasks.

You have created the Development summary task before. Now, you create these

two tasks under the Development summary task. Then, you set a relationship

between the tasks. Finally, you set a four-day lag time between the two tasks. To

link tasks and set the lag time between them, perform the following steps:

1. Create a task named Develop code by using the Project menu.

2. Create a task named Developer primary testing below the Develop code task

by using the Project menu.

3. Select Develop code.

4. Select Developer primary testing with the Ctrl key pressed.

5. Click the Edit menu.

6. Click the Link Tasks command.

The two tasks are displayed as linked to each other in the Gantt chart view as you

see in Figure 11.8.

Figure 11.8: Linking Tasks

Software Project Management (CS615)

384

© Copyright Virtual University of Pakistan

7. To estab1ish the start-to-finish, relationship between the two tasks, select

the Developer primary testing task and click the Project menu.

8. Click the Task Information command.

This information displays the Task Information dialog box wherein you can

establish a defined relationship between the two tasks by using the

Predecessors tab.

9. Click the Predecessors tab in the Task Information dialog box.

10. Select the Start-to-Finish (SF) relationship in the Type field cell.

This defines a start-to-finish relationship for the tasks.

11. Type 4d in the Lag field cell to specify four days lag time between the

two tasks. This step is displayed in Figure 11.9.

Figure 11.9: Specifying Value for the Lag Field

12. Click OK to close the dialog box.

The tasks Develop code and Developer primary testing appear linked to each

other with the symbol of Start-to-Finish relationship in the Gantt chart view.

11.8 Splitting Tasks

Software Project Management (CS615)

385

© Copyright Virtual University of Pakistan

A split in a task is defined as an abrupt and sudden interruption in the planned

schedule. The need to split tasks arises because practically no task can be

completed without a break. Due to resource crunch, a planned task is normally

halted for some time.

For example, at XYZ Inc., both the tasks to train developers and to test a software

module require a Windows 2000 Server. However, depending upon the criticality

of the tasks, you can split one of the non critical tasks. In this case, you decide to

stop testing the software module and continue training the developers. To specify

the task using Microsoft Project, you first create a Testing task as the summary

task. After creating the Testing task, you create the Unit testing task under the

Testing task. Next, you split the Unit testing task.

To split the Unit testing task, you perform the following steps:

1. Create a task named Unit testing below the Testing summary task.

2. Select the Unit testing task.

3. Click the Edit menu.

The Edit menu contains the command that enables you to split a task.

4. Click the Split Task command on the Edit menu.

Upon clicking the Split Task command, the shape of the cursor changes. In

addition, a small yellow box with a tool tip suggesting how to split a task

hovers on the task view of the Microsoft Project window.

5. Drag the changed mouse cursor over the task in the Gantt chart view.

Software Project Management (CS615)

386

© Copyright Virtual University of Pakistan

Figure 11.10: Splitting Tasks

In Figure 11.10, you can see the task being split into the required number of days.

To split a task for a specified number of days, you drag the mouse pointer to a

particular date. For example, a task is scheduled to start from May 5. You want a

part of the task to start again from May 15. Therefore, there is a gap between May

5 and May 15. To start the task again from May 15, you drag the last end of the

task and release the mouse pointer on May 15 in the Gant Chart view.

11.9 Assigning Resources and Resource Costs to Tasks

Resources are means that help convert input to a task into output for the task.

Resources are assigned to tasks for the following reasons:

• To track the costs of each resource

• To track the work completed and the material resources used in a project

There are two types of resources, work and material. Work resources refer, to the

people and equipment. At the end of a project, these resources are not consumed.

Unlike work resources, material resources are used completely by the end of the

project. For example, to complete the task of writing the code for a module, you

need human and material resources. You need material resources such as

hardware, software, and electricity.

Software Project Management (CS615)

387

© Copyright Virtual University of Pakistan

Assigning resources to a task is a two-step process. First, you add the available

resources to a project. You can do this by adding resources by using the View

menu and then clicking the Resource Sheet command on the View menu. When

you click the Resource Sheet command, Microsoft Project changes the default

Gantt chart view to the Resource Sheet view. Figure 11.11 displays the Resource

Sheet view.

Figure 11.11: Resource Sheet View

Suppose for the XYZ Inc. project, you want to add a hardware resource in the

Develop prototype task. The steps to add the resource are as follows:

1. Create a task named Develop prototype below the Analysis summary task.

2. Select the Develop prototype task.

3. Click the Tools menu.

4. The Tools menu contains the command to add a resource.

5. Point to the Resources command.

6. When you point to the Resources command, the Assign Resources command

of the Resources command of the Resources submenu is displayed.

7. Click the Assign Resources command. Figure 11.12 displays the Assign

Resources dialog box.

Software Project Management (CS615)

388

© Copyright Virtual University of Pakistan

Figure 11.12: Assigning Resources to Tasks

The Assign Resources dialog box contains two fields, Name and Units. The Name

field indicates the name of the available resources in the resource pool or a

project. The Units field indicates the number of resources that can be used for a

particular resource.

You can use the Assign Resources dialog box to assign units for both work and

material resources. The unit for work resources is specified in terms of

percentage. However, the unit for material is specified as a numeric value.

For example, you may select three computers or five workstations for the

development team of a project. These values are not more than the predetermined

value set for a resource in the Max.Units field of every resource in the Resource

Sheet view.

Select the hardware resource for the Develop prototype task. You close the

Assign Resources dialog box by clicking the Close button. The hardware resource

is added next to the Develop prototype task.

11.10 Assigning Costs to Tasks

Software Project Management (CS615)

389

© Copyright Virtual University of Pakistan

Cost is an important aspect of project scheduling. Controlling costs ensures the

optimal use of resources. For example, to complete a specific task in a project

plan, you can assign more resources to that task. Alternatively, you can increase

the duration of that task depending on the cost of the resources that are used by

that task.

You can assign two rates for any type of a resource. The rate for work resources

are calculated on an hourly basis. However, the rate at which the materia1

resources are calculated can be:

• Standard rate: The normal rate at which a resource is procured

• Overtime rate: The rate that you pay if you overuse a work resource

For example, for the XYZ Inc. project, you need to specify the standard and the

overtime rates for a work resource named Tester. To do this, you first assign the

work resource Tester to the Unit Testing task that you created earlier. After

assigning the resource to the Unit Testing task, perform the following steps to

assign rates to the resource:

1. Click the Resource Sheet view of Microsoft Project

The Resource Sheet view is used to display all resources and their respective

costs.

2. Type Tester in the first cell of the Resource Name column

3. Select Tester.

You do this because that is the work resource for which you need to specify

the standard and overtime rates.

4. Click the Project menu to display the Resource Information command.

5. Click the Resource Information command on the Project menu.

6. Click the Cost tab in the dialog box.

The costs tab provides information about the standard and overtime rates and

the cost per unit of a particular resource.

7. Type $30.00/h in the first cell of the Standard Rate column as shown in

Figure 9.13.

8. Type $10.00/h in the first cell of the Overtime Rate column.

The rates can also be entered as negative values to denote the decrease in rate as

compared, to previous rates or as positive values to denote a comparative increase

in rate, such as +20% or -20%.

9. Click OK to close the Resource Information dialog box.

Software Project Management (CS615)

390

© Copyright Virtual University of Pakistan

While calculating costs for work resources; Microsoft Project calculates the resource cost

by the hourly rates that you specify and the time required for completing a task.

However, when you assign a material resource to a task, Microsoft Project automatically

calculates the total cost of the resource by using the material resource rate specified by

you and the quantity of material required for completing the task.

Figure 11.13: Assigning Costs to Resources

11.11 Tracking a Project Plan

Project management is a multiple-phase undertaking. The first phase is the project

initiation or the project planning phase. This phase is followed by the projecttracking

phase. Finally, you wrap up a project with the-project-end phase. Project

tracking is an extremely in important activity in an organization. Unless a project

is tracked effectively, it might never come close to termination. Project tracking

also ensures strict adherence to project plans, requirements, and schedules.

Progress Lines

To track a project plan, you first view the progress of a project. You can view the

progress of a project by applying progress lines to the tasks in the project. You

can display progress lines in three ways,

Software Project Management (CS615)

391

© Copyright Virtual University of Pakistan

You can choose to display progress lines always at the current status of a project.

To do this, you need to select the Always display current progress lines check box

in the Progress Lines dialog box. Selecting this option displays progress lines

every time based on the current status of a project.

The second way to display project lines is to display them on selected dates of a

project plan. For example, you use this option when you need to know the

progress status of a project on the jay development is completed. In this case, you

select the Display selected progress lines check box to display progress lines on

that day. Similarly, you can use this option to display progress lines on the day

when testing is completed or the project-end date.

Finally, you can display progress lines at regular intervals such as daily, weekly,

or monthly.1f you choose daily, you can further define its preciseness by choosing

everyday, every second, or every third day, and so on. Alternatively, if you

choose monthly, you can refine your choice by selecting the month and day when

a progress line is displayed. To display progress lines for all the tasks listed in the

Sample-Project.mpp file every third day, you perform the following steps:

1. Click the Tools menu

2. Point to the Tracking command to view different options for creating progress

lines

3. On the Tracking submenu, click the Progress Lines command

4. The Progress Lines dialog box is displayed. In the dialog box, select the Display

progress lines at recurring intervals check box.

5. After selecting the Display progress lines at recurring intervals check box,

select the Daily option button.

6. To specify that the progress lines must be displayed every third day, click the:

every box and select the every 3rd option in the list.

7. You can further choose to display the progress lines every third day of a week on

a workday. This is shown in Figure 11.14

8. To confirm the specifications and close the Progress Lines dialog box, click OK.

Figure 11.14: Setting Options for Progress Lines

Software Project Management (CS615)

392

© Copyright Virtual University of Pakistan

Figure 11.15: Progress Lines in the Gantt Chart View

Project Baselines

Project baselines are another way of depicting the progress of a project. Baselines

are indicators that help you compare the actual start date with the planned start

date of a project. They also help compare the actual cost incurred with the

planned cost for a project. After preparing a project plan for tasks, you can save

the plan as a baseline. This serves as an ideal plan for you to compare the actual

performance of the project with the baseline that you save.

To save a project plan as a baseline, perform the following steps:

1. Click the Tools menu, and point to the Tracking command.

2. Select the Save Baseline command on the Tracking submenu.

3. In the Save Baseline dialog box, select the Save baseline and Entire project

option buttons to save a baseline of the entire project.

4. Click OK to close the Save Baseline dialog box. You can also save a part of

the project plan by saving a few tasks as baselines by clicking the Selected

tasks option button.

To view the deviation from a baseline performance to the actual performance

of a project, perform the following step:

Software Project Management (CS615)

393

© Copyright Virtual University of Pakistan

5. In the Project Information dialog box, click the Statistics button to view the

project statistics for the Sample-Project.mpp dialog box. This dialog box is

displayed in Fig 11.16.

Figure 11.16: Displaying Project Baseline Information

The dialog box displays critical and summarized information about the variance

values of the start and finish dates of a project, work completed in hours, cost, and

duration in days. Higher the variance of a column, higher is the degree to which a

project does not conform to the baseline plan. The actual values are displayed in

the dialog box.

You can compare the baseline values for all these factors with the actual values of

a task to conduct project plan analysis.

11.12 Recording and Updating Tasks

One way of tracking a project schedule is by determining the actual work done by

a resource. After doing that, you compare it against the total work to be done

initially. Using these factors, you can calculate the remaining work that needs to

be done in the rest of the project cycle.

Software Project Management (CS615)

394

© Copyright Virtual University of Pakistan

For example, you need to check the status of the Test component modules task in

the XYZ Inc. project .This task exists under the Testing summary task. You use

the Task Sheet view to record the actual work done by a resource and calculate

the work that remains to be done. To do that, perform the following steps:

1. Select the task Unit testing for which you want to view the task completion status.

This task exists under the Testing summary task.

2. Click the View menu.

3. Click the Table Entry command.

4. Click the Work command on the Table Entry submenu

After doing this, four fields appear: Work, Baseline, Actual, and Remaining.

You update the Actual field value with the current amount of work done.

Microsoft Project automatically updates the Remaining value after comparing the

Actual value with the value in the Work field. Alternatively, you can update the

value of the remaining field to a number that you feel is correct. Consequently,

Microsoft Project updates the Tota1figure in the Work field. It also displays the

difference in the previous Work and the current Work, values in the Variance

field.

For example, the Work field in Figure 17 displays the value 20. You update the

Actual field with the value 13. Consequently, the remaining field would

automatically show 7. However, you can modify the Remaining field to display

the value 10 if seven days are not adequate. Notice that the Work field displays

the value 27, and the value in the Variance field is 3.

Software Project Management (CS615)

395

© Copyright Virtual University of Pakistan

Figure 11.17: Updating the Status of Tasks

Note:

You can also update the percentage of work completed by specifying the

value in the Percent complete spin box. The Percent complete spin box is

present in the General tab of the Task Information dialog box.

Consequently, Microsoft Project updates the actual and remaining work in

the work sheet of tasks.

11.13 Rescheduling Tasks

Using Microsoft Project, you can reschedule the tasks of a project. Rescheduling

involves modifying the start or finish dates of a task. For example, you need to

reschedule the start date of the Create user manuals task. This task exists below

the Development summary task. To reschedule an incomplete task, perform the

following steps:

1. Create a task named Create user manuals under the Development task.

2. Make the Development task a summary task by using the left indent Icon.

3. Select the Create user manuals task.

4. Click the Tracking command on the Tools menu.

5. Click the Update Project command on the Tracking submenu, to display the

Update Project dialog box. Figure 11.18 displays this dialog box.

Software Project Management (CS615)

396

© Copyright Virtual University of Pakistan

Figure 11.18: Rescheduling Tasks

6. In the Update Project dialog box, select the Reschedule uncompleted work to start

after option. This option is used to reschedule an incomplete task.

7. Specify a new start date for the Create user manuals task.

8. Select the Selected tasks option to reschedule a task. If you need to reschedule

entire project, choose the Entire project option.

9. Click OK.

11.14 Modifying the Duration of a Project Plan

During the course of a project, schedule, cost, and effort slippages are quite

common. Therefore, you sometimes need to modify the project start and end

dates. Normally the start date is modified for short cycle projects that need an

early head start. Finish date is modified when you are unable to meet the project

end date due to slippages. Assume that the project starts on February 15 and you

change its finish date from June 10 to June 15. To do this, perform the following

steps:

1. Click the Project menu

2. On the Project menu, click the Project Information command. This displays the

Project Information dialog box.

3. In the Project Information dialog box, click the Schedule from list box.

4. Select the Project Finish Date option from the Schedule from list.

Software Project Management (CS615)

397

© Copyright Virtual University of Pakistan

5. Click the Finish date box, and select June 15 from the calendar of the month

June. This step is shown in Figure 11.19.

6. Click OK.

Figure 11.19: Modifying the Plan Duration

You have modified the project finish date from June 10 to June 15. You can view the

change in the Gantt chart view of the project.

11.15 Displaying Project Information Using Reports

You create reports to display project-related information in a tabular format,

which is easily comprehensible. Project reports provide a picture of the status of a

project. The status of a project helps measure the progress of it. Reports can be

prepared for a specific phase or for all the phases at one time.

Creating Standard Reports

Using Microsoft Project 2000, you can create two types of standard reports:

• Standard resource report: You create standard resource reports to display

resource allocation and the costs incurred on them

Software Project Management (CS615)

398

© Copyright Virtual University of Pakistan

• Standard task report: You create standard task reports to display information

regarding tasks and the duration to complete each task in a project.

To create a report on the resources listed in the Sample-Project.mpp file, perform

the fo1lowing steps:

5. Display the Resource Sheet view of Microsoft Project

6. Click the View menu.

7. Click the Reports command.

This command displays the Reports dialog box. This contains the various

report formats.

8. Select the Custom icon to create a new resource

Figure 11.20 displays the Custom icon.

Figure 11.20: Displaying the Custom Icon in the Reports Dialog Box

5. Click the Select button.

This displays the Custom Report dialog box.

6. Click the New button.

This way, you create a new type of a resource report that is not part of the list of

reports displayed. The Define New Report dialog box is displayed as shown in

Fig 11.21.

Software Project Management (CS615)

399

© Copyright Virtual University of Pakistan

Figure119.21: Defining New Reports

7. In the Report type box, select the Resource option.

You do this to create a report displaying the various resources used in a

project.

8. Click OK to confirm your selection.

The Resource Report dialog box is displayed as shown in Figure 11.22. In this

dialog box, you specify the name of the report. In the same dialog box, you

can sort the information to be displayed in the report.

Software Project Management (CS615)

400

© Copyright Virtual University of Pakistan

Figure 11.22: Resource Report Dialog Box

9. Click OK to confirm your specifications.

After the Resource Report dialog box is closed, the Custom Reports dialog

box is displayed.

10. Click the Preview button to view the report.

The report is shown in Figure 11.23. To be able to view the report, you

configure a printer to the computer that has Microsoft Project.

Figure 11.23: Report on the Resources Listed in the Project1.mpp File

Similarly, you can also view a report on tasks. To view the report on tasks, repeat

the procedure for creating a report on resources in the Gantt chart view of

Microsoft Project.

Modifying and Printing a Standard Report

You might need to modify a report to display more information or to display the

existing information in a different format. To modify the ways in which a task is

displayed, you Use the Task report dialog box.

Software Project Management (CS615)

401

© Copyright Virtual University of Pakistan

You can modify an existing standard task or a resource report by clicking the Edit

button on the Custom Reports dialog box. This displays the relevant reports

dialog box.

For example, to modify an existing report to display only summary tasks and add

gridlines to each task for the XYZ Inc. project, perform the following steps:

1. Click the Definition tab in the Task Report dialog box. The Task Report dialog

box is displayed in Figure 11.24.

Figure11.24: Modifying Reports

2. Click the Show summary tasks check box.

This check box is used to display only the summary tasks in a project. For

example, in the current project file, selecting this check box would display only

the broad-level tasks, Analysis, Design, Development, Testing, and

Implementation and not the subtasks below each one of them.

3. Click the Details tab.

4. On the Details page, select the Gridlines between details check box.

The Gridlines between details check box is shown selected in Figure 25.

Software Project Management (CS615)

402

© Copyright Virtual University of Pakistan

Figure 9.25: Selecting Gridlines between details Check Box.

5. Click OK to close the Task Report dialog box.

In Task Report dialog box, you can display specific fields in the Definition tab. In

addition, you call also use the Details tab to display a summary of tasks in

gridlines and resources.

You can also sort a report on different fields displayed on a report.

Printing a Standard Report

Printing a standard report is really simple. In the Define New Report dialog box,

you click the Print button to print a report.

Figure 1126 displays the Define New Report dialog box. Clicking the Print button

in the Custom Reports dialog box, displays the Print dialog box.

Software Project Management (CS615)

403

© Copyright Virtual University of Pakistan

Figure 11.26: Printing a Report

Software Project Management (CS615)

404

© Copyright Virtual University of Pakistan

Finally, you can see the Sample-Project.mpp file that you are creating for XYZ

Inc. complete with all the components that you have added.

12 Commissioning & Migration

12.1 Software Implementation

After the software product is developed, the challenge lies in seeing the system

work successfully at the user-end. Product implementation is the crucial activity

of actually handing over the product to the users. The product moves from the

theoretical environment of the development team to the practical environment of

the user. Implementation begins with the preparatory activities of planning,

training the user staff, and testing the system. After the preparatory activities are

complete, the new system is installed and configured at the user end.

Implementation marks the end of product development. After this, the product is

handed over to the maintenance team.

Implementation Prerequisites

The purpose of implementation is to organize and implement the new or updated

system. Most of the time, implementation is a contract-based activity. The

contract provides details of the implementation activity. Implementation

procedure includes details such as the scope, method, and duration of

implementation. There are some prerequisites of implementation. They are

finalizing the number of licenses, procedures for error logging, scheduling system

changeover, and procedure for maintaining data backups. However, the primary

task is to organize a team to monitor implementation.

An implementation coordination committee is set up to monitor implementation

committee. Other committee members include line managers of other departments

and members of the development team.

IThe committee performs various activities. It identifies various requirements of

implementation process, such as arranging for software licenses, project software,

and other standby facilities. The committee looks into the implications of the

system environment, staff allocation for implementation tasks, and internal

communication. The committee also devises alternative methods facilitating

system changeover.

Key Implementation Plans

The various activities performed during implementation are preparing an

implementation plan, a raining plan, an acceptance plan, and a system support

plan.

a. Implementation Plan

Software Project Management (CS615)

405

© Copyright Virtual University of Pakistan

The first task of implementation is the creation of the implementation plan.

The implementation plan contains details of the methods of system transfer

and the timescale for implementation. Details of hardware and software

needed for implementation are also mentioned in the plan. The plan contains

details of date, location, and timescale for implementation. The plan also

mentions the prerequisites of implementation, such as the existing network

environment and the availability of related software. You can look at an

implementation plan in Table 12.1.

Table 12.1: Implementation Plan

Implementation Plan

1) Implementation Schedule

Serial No. Location Start Date End Date Days Resources

2) Resource List

Serial No. Resource

Name

Contact

Name

Pager or

Mobile No. E-mail ID Key Resource

(Y/N)

3) Software Components for Installation

3.1) Server

Serial No. Software

Name Version Space

Required Location

3.2) Client

Serial No. Software

Name Version Space

Required Location

4) Data Migration

Serial No. Data to be

Migrated

Location of

Server

Data

Migration

Mode of

Migration Batch or Script

Software Project Management (CS615)

406

© Copyright Virtual University of Pakistan

In the implementation plan, Implementation Schedule section records .details

such as location and duration of implementation. The Resource List section

has a list of the resources and their contact numbers. The plan has details of

the server and clients in the Components of Installation section. Finally, the

plan also contains data migration details.

b. Training Plan

Preparing a training plan is one of the tasks of implementation. The training

plan contains details of the participants to be trained. It also mentions the

focus area arid .the audience for die training session. Training schedule

containing the training venue, training name, start date and end date is a part

of the training plan. The plan conveys budgetary details and the roles and

responsibilities of participants as well as the faculty. A training plan is

displayed in Table 12.2. The plan has details of the focus areas of training,

courses identified for training, and training schedules. Roles and

responsibilities of trainer are also included in the training plan.

Table 12.2: Training Plan

Training Plan

1) Focus Areas for Training

Serial No. Focus Area

2) Training Courses

Serial No. Course

Title Duration Category Faculty Details Number of

participants

3) Training Schedule

Serial No. Course

Title Code Start Date End Date Venue

4) Roles and Responsibilities

Member Role Back-up Responsibilities

Software Project Management (CS615)

407

© Copyright Virtual University of Pakistan

c. Acceptance Plan

The purpose of an acceptance plan is to determine the details of acceptance

testing. The plan contains details such as the order of testing of functions,

location, date, and duration of testing. Details of participating members,

coordinators, and users are also mentioned in the plan. The acceptance plan

lists the procedure for bug fixing, version control, and verification and

validation details. Procedure for the creation of acceptance test cases and

setting up software and hardware environment is also mentioned in the plan.

The acceptance plan in Table 12.3 contains details of the acceptance schedule,

acceptance criteria, list of resources, and a bug report form.

Table12. 3: Acceptance Plan

Acceptance Plan

1) Schedule

Serial

No. Module From

Date To Date Days Resource

Name Documentation

2) Acceptance Criteria

Serial

No.

Item

Name Acceptance Criterion

3) Resource List

Serial

No.

Resource

Name E-mail Telephone/Pager Key Resource (Y/N)

4) Bug Reporting Procedure

Serial

No. Module Bug Reported

by

Report

Date

Closure

Date

Assigned

To Fixed On

d. System Support Plan

The implementation team prepares the system support plan either during or

before product installation. The system support plan contains details of how

the system will be supported after it is implemented. Typically, the support

plan has a warranty clause. The warranty clause usually lasts for a year. The

warranty covers details of people in the support activities, details of

agreement, the response time, and support details.

Implementation Activities

After the prerequisites are in place, implementation activities begin in right

earnest. Now, all the plans created for implementation are put into practice.

Implementation activities include acceptance testing, user and operator training,

Software Project Management (CS615)

408

© Copyright Virtual University of Pakistan

data migration, installation and configuration, product sign-off, product wind-up,

post mortem, and product delivery.

i. User Acceptance Testing

You must have heard the proverb, "the proof of the pudding lies in the eating.

This applies for software product also. The success of the software product

depends on how the user responds to the product. One of the important

implementation activities is user acceptance. This aims at ensuring that the

system is working according to the user requirements. UAT is done to ensure

that the desired product design matches the actual product design.

UAT is the final testing performed by the end user after using the product over

a limited period me. As part of the implementation process, the project

manager prepares the User Acceptance Test plan. The UAT plan is the last

stage of the testing process where the user tests the product. The user tests the

product and identifies whether it is acceptable or not.

Ideally, UAT is conducted in the same environment as the one in which the

product is designed. UAT plan consists of the activities to be conducted,

functions to be tested, the time, and environment in which software will be

tested. Often test cases are attached with the plan. The user validates the

software based on the test cases.

The executable product is installed in the test environment and configured for

use. Then the user executes the test supplied. r the user tests the software

product, the implementation team takes care of the bugs or items identified by

the user. The bug fixing and closing of issues continue iteratively until all

problems are solved. The software product is then ready for use. The user

representative uses a signoff on the prescribed format to indicate satisfaction

with the product. This marks end of the development activity. The final bugfree

version is delivered to the user.

ii. Training

To familiarize the users with the new system, you need to train them. Apart

from the users, there are the operators who also need to be trained to handle

the system. Training for both the users and operators has separate goals.

Training sessions aim at providing the participants with specific skills

required in handling the new system. Training aids used are documents, icons,

on1ine helps, and demonstrations or classroom sessions. The user training

focuses on major m functions and the users' need to gain access to them. Some

of the activities that a user might need to perform are simulating activities,

analyzing data, drawing graphs, and searching for information. The user is

trained on navigation skills, information searching skills, and security

functions. The users are trained on the differences between the old and new

activities to familiarize them with the differences.

Software Project Management (CS615)

409

© Copyright Virtual University of Pakistan

The operator training focuses on the support functions of the system. The

support functions include granting user access, granting file access, recovering

damaged files, installing new devices and software, and making backups.

Therefore, the operators' training focuses on two function areas. First, the

operators learn to run the system, and second they learn to support the users.

Another important approach to training is documentation. Documentation can

be in the form of user manuals and guides. The use of documentation in

training will depend on the target audience. Therefore, you need to ensure that

your development team does not neglect training and documentation. This

should be planned and tracked from the project start as soon as the

requirements analysis is complete. You also need to ensure that training and

documentation for users and operators is updated periodically.

iii. Data Migration

At times, the user might want to transfer data from the old system to the new

system during implementation. The implementation team migrates data from

the old system to the new system. This task can be automated by using scripts

and tools. Data migration is an important activity. As a project manager, you

need to ensure that all data is successfully migrated. At times, data migration

involves a large amount of data from heterogeneous sources. This entails lot

of work, which might be beyond the handling capacity of the implementation

team. Typically, in such situations, data migration activity is subcontracted to

an external agency. If the data is in the form of documents, data entry

operators could also be hired. Although the activity is subcontracted, as a

project manager, you need to plan and monitor its progress continuously.

iv. Installation and Configuration

To make the system available to end users, the implementation team needs to

install and configure the system. This involves making the system run and

prepare it for actual work. The implementation team does this by deploying

the system on user machines. During installation, the files, components, and

executables are copied to the user machine.

Configuration is the act of making necessary changes in the system

parameters that are specific for target users. This activity is performed along

with installation. Installation and configuration activity can be automated by

using many tools. You can perform installation and configuration at multiple

locations by using tools. These tools create installable disks that can be used

to install and configure. This enhances the productivity of the implementation

team to a great extent.

At times, the project manager might need to outsource the installation activity.

Then great care needs to be taken to ensure that correct versions are installed.

At times, Web-based automatic installation facilities are used to simplify the

process further. At times, the implementation team might need to install the

Software Project Management (CS615)

410

© Copyright Virtual University of Pakistan

system at multiple locations simultaneously. The team prepares separate plans

for each location. The implementation team also configures the installed

system.

v. Product Sign-Off

At the end of acceptance testing, the user-representative gives the sign-off in

the form of an acceptance letter. This marks the formal end of the

implementation phase. This means that all issues raised during the acceptance

testing are solved and closed. As a project manager, you need to ensure that

the contractual obligations with the user are fulfilled. You need to verify that

the client accepts all documents and deliverables as mentioned in the contract.

You also ensure that the sign-off is according to defined guidelines and is in

the form of an acceptance letter.

vi. Project Wind-Up

Project wind-up marks the formal closure of the development phase. This

activity begins after obtaining a sign-off from the user. The key activities

performed during project wind-up are analyzing what went wrong and what

could have been better. Major learning from the project is summarized at the

end of the project. Certain completion criteria are formalized at the project

start. These criteria prevent the project from dragging on endlessly. Certain

activities are performed to ensure that the project ends on time.

• Monitoring deliverables

• Monitoring progress

• Controlling change requests

• Monitoring work yet to be done

Usually a senior project manager supervises the project-wind up activities.

During project wind-up, you need to gather feedback both internally as well as

from the client. The various wind-up activities performed during project end

include obtaining client feedback of the project. You also need to update and

close the project plan. Another activity is updating project-related statistics at

the end for resource estimation. You can determine the level of success of the

project based on the quality of the delivered system and the level of

satisfaction of all concerned.

During project wind up, the project manager also plans for the allocation of

the project staff. The deliverables list is checked to ensure that all

requirements are met. The project manager also verifies the financial

completion of the project. A contract is also drawn to deal with the problems

later for a defined period under a warranty. The project is evaluated for

adherence to schedule, budget, technical goals, and client and project team

satisfaction.

Software Project Management (CS615)

411

© Copyright Virtual University of Pakistan

Another important project-end activity is data collection. Data accumulated

during the project is collected and organized after completion. This data helps

in resource estimation and quality assurance of future projects. The data

collected regarding the actual cost per task, cost overrun and under-run per

task, unplanned tasks, and planned task that were not required are estimated.

Data about software change requests and bug statistics is also noted.

The performance of the project team is also evaluated at the end of the project.

The team members are evaluated in terms of their ability to accomplish

project tasks. The time taken, the quality achieved, and the adherence to cost

and schedule is also noted. The team members are also evaluated based on

their innovative approach to accomplishing a task. The ability of the team

member to work as a team, communicate, and support each other is also

judged. The team members are also asked to evaluate themselves in terms of

their strengths and weaknesses.

vii. Post Mortem

The post mortem activities involve collecting valuable information at the end

of the project. The knowledge gained from the project is documented for use

by other projects. Similarly, the recommendations for enhancements are also

documented. You also need to submit project- related items, hard copies, and

files to the project library. Usually, post mortem activities are conducted

among the team members. The team members exchange feedback about each

other regarding interpersonal communication and work processes within the

team.

Finally, the project manager prepares a project closedown report. This report

contains suggestions on what should be done to improve software quality in

the next project. This report contains details of what the team has failed to

deliver and the lessons learned from the project. This report will help detect

and eliminate long-term problems. The project closedown report contains the

following details:

• Description of the project

• Success assessment

• Schedule, budget, and technical details

• Problems while implementing solutions

• Data updates regarding cost estimation

viii. Product Delivery

Product delivery marks the last leg of implementation. In this phase, the

packaged software, documentation, and other items mentioned in the contract

are passed on to the maintenance team. As a project manager, you need to

ensure the smooth transfer of knowledge from the development team to the

maintenance team. The maintenance activities are discussed in detail in the

next section.

Software Project Management (CS615)

412

© Copyright Virtual University of Pakistan

12.2 Software Maintenance

According to surveys, changeability is one of the most important attributes of

complex, multifunction software systems. This calls for continuous adjustments

of the software to suit the changing environment. While changes are inevitable, it

is not always possible to create products foreseeing the changes. Therefore, the

product needs to be changed according to the changing scenario. You might need

to upgrade the software product based on new system requirements or remove

redundant functionality. The need for a change brings software maintenance into

the picture. Maintenance activities can either be in-house or outsourced.. In the

case of in-house maintenance, the development team performs the maintenance

activities. On the other hand, an independent maintenance team performs

outsourced maintenance activities.

Software maintenance deals with the sustenance of a piece of software after it is

released. Maintenance activity is needed when errors are detected after the

software product is released. Changing requirements of the software product also

require maintenance activity to cater to the changes.

Maintenance activity assumes greater importance for a project manager. This is

because managing software maintenance is more challenging than managing

software development. Consider an example. You are maintaining a banking

operation. A small Program change is introduced as part of the maintenance

activity. Suppose this change results in an incorrect interest calculation. You can

well imagine the kind of confusion this error will create, not to mention the loss of

client faith and goodwill in the bank. Therefore, as a project manager, you need to

be extra cautious while managing a maintenance project.

Types of Maintenance Activities

Maintenance is an important phase in SDLC: The need for maintenance activities

has increased with the increase in software packages. Maintenance activities

include correction and prevention of defects, enhancements to incorporate

changing needs, and porting of applications and adaptability. The changing

hardware and software scenarios have increased the demand for software

maintenance. Today, in the entire SDLC of a software application, the

maintenance effort is about 80 percent and the development effort is only 20

percent.

There are four types of maintenance activities:

• Corrective

• Adaptive

• Perfective

• Preventive

Software Project Management (CS615)

413

© Copyright Virtual University of Pakistan

Corrective maintenance is about fixing bugs. This takes approximately 17

percent of the maintenance time. During corrective maintenance, the existing code

is used to correct the fault that causes the code to deviate from its documented

requirements. Here, the focus is on fixing defects.

During adaptive maintenance, the existing code is changed to adapt the new

features and functionality. These new features are usually part of a new release of

a code. This change normally takes 18 percent of the maintenance time.

Perfective maintenance improves the maintainability of the code. During this

activity, the code is restructured to make it easily understood and to remove

ambiguities. The enhancement of code occupies 60 percent of the maintenance

time.

Preventive maintenance is undertaken to protect the code against failure. Here,

the focus is on adhering to coding standards and reduce the chances of code

failure. Preventive maintenance .activity takes around 5 percent of the

maintenance time.

In the above list of maintenance activities, you can see that out of total

maintenance effort, only 20 percent is spent on corrective maintenance and 80

percent on the rest. This refutes the popular belief that maintenance activities is all

about fixing mistakes.

Maintenance Activities

To perform maintenance activities, the maintenance team needs to acquire the

business and technical knowledge of the client systems. The maintenance process

is usually divided into three phases.

• Initiation Phase

• Preparation Phase

• Execution Phase

Initiation Phase

The initiation phase starts with the commencement of maintenance activities. It is

primarily a knowledge acquisition phase. During this phase, the maintenance team

takes over the system from the development team. The maintenance team

familiarizes itself with the ways and functioning of the system. This is essentially

a phase of knowledge transfer from the development team to the maintenance

team. The major activities of the initiation phase are baseline assessment and

operating procedures. During baseline assessment, the interfacing and

communication methods between the development and maintenance teams are

defined. The user-coordinator from the user side and the information technology

help from the maintenance team are identified. During this phase, the plan for

acquiring the systems knowledge is also finalized.

During the operating procedures activities, the maintenance team understands the

application and the functionality involved in the maintenance task. The

Software Project Management (CS615)

414

© Copyright Virtual University of Pakistan

maintenance team reviews the current operating procedures of the system. The

team also obtains details about the environment set up, deployment of software,

the resource allocation process, and priority settings. Other' activities such as root

cause analysis, work assignment to the development teams, and updating of

documentation procedures is also done. The maintenance team refers to the

problem management procedures, on-call or escalation procedures; and

operational process for handling: faults. It also makes decisions based on the

severity of the faults, application criticality, and infrastructure issues.

The maintenance team finalizes procedures for transferring support work from the

development team. The maintenance team members are initiated to hands-on

exposure of the systems. The maintenance team finalizes the quality systems and

standards and guidelines to be followed.

Preparation Phase

The preparation phase begins after the initiation phase. During this phase, the

maintenance team sets up the administrative and support procedures needed for

maintenance activities. In this phase, the environment is set up and hardware,

software, and network are made ready for operation. All the procedures decided

and finalized during the initiation phase are put into practice in this phase.

According to the documentation procedures finalized in the initiation phase, the

latest documentation is kept in the library. During this phase, bug reporting,

problem solving, and other support methodologies are established. The security

measures are also put in place and practiced during this phase.

Execution Phase

The execution phase follows the preparation phase. In this phase, the maintenance

team starts executing the maintenance activities after the preparation in the earlier

phase. During this phase, the maintenance team is in close touch with the

development team for a small period of time. Such communication is

recommended to ensure better coordination.

Maintenance Curve

Maintenance activity begins after product implementation. The effort spent on

maintenance varies over a period of time. Normally, maintenance effort is very

high immediately after implementation. The system faces numerous changes

during this time. The changes could be in the form of bugs, changes in network

environment, or problems caused by user mishandling. During this time, the effort

spent on maintenance activities is very high. With time, the system stabilizes and

maintenance activities also slowdown. During this period, the users are more or

less satisfied with the system. The system also runs smoothly without requiring

any major changes. Therefore, maintenance activity is at its lowest during this

phase.

Software Project Management (CS615)

415

© Copyright Virtual University of Pakistan

However, over a period of time, business processes change and the system also

depreciates. During this period, major changes start coming in. The changes are in

the form of enhancements and additions of new systems or modules.

These changes take place continuously to keep the system up-to-date with the

changing needs and requirements. Maintenance activities are also at a maximum

during this phase.

However, soon the system becomes obsolete and is phased out. Along with the

system phase- out, maintenance activities also come to an end.

Figure 12.1 shows the variation of maintenance activity with time. In the curve,

maintenance effort is very high during the initial phase. Then the maintenance

effort stabilize during the maturity phase. Finally, the maintenance effort

increases sharply just before system phase out. The system is phased out to pave

the way for new systems.

Figure 12.1: Maintenance Curve

Maintenance Process

There are certain prerequisites that you need to follow before beginning with the

maintenance process. All documentation needs to be complete and up-to-date. All

existing items need to be configured, and the latest copy of the code should be

available. The hardware, software, and network environment for testing and

maintenance should be made available. Before beginning with the maintenance

process, the maintenance team is identified. The user representative from the user

side is identified and the maintenance team is constituted. The maintenance team

Software Project Management (CS615)

416

© Copyright Virtual University of Pakistan

consists of the head of IT, the project coordinator, and team members. The

maintenance project 1anager is the single point contact between the user

representative and the maintenance team. The project manager categorizes the

type of maintenance activity to be performed based on specifications. The project

manager ensures proper communication between all the entities 1volved in

maintenance activity. To ensure that the maintenance process runs smoothly, there

is a thorough checking of all deliverables. Maintenance activity is the most

critical because the system is running and already in place. Therefore, the project

manager needs to ensure that no error arises during the maintenance process.

The common approach followed in the maintenance process is as follows. After

the user makes a request for change, the maintenance team performs an impact

analysis. Then the team plans for the system release. The system goes through

design changes, coding, and testing. Finally, the system is released. The

maintenance activities undertaken are corrective maintenance, adaptive

maintenance, perfective maintenance, and preventive maintenance.

Corrective Maintenance Process

The corrective maintenance process begins with the user representative reporting

bugs to the project coordinator by using the problem report form. The project

coordinator analyzes the problem and assigns the problem to one of the team

members for corrective action. If the bug fixing leads to any changes in the

system, the change is carried out based on the change request process. The team

member requests the SCM team to check out the item to be modified. Then the

bugs are fixed and tested in the test environment. After this, the user acceptance is

carried out for the successful completion of the corrective maintenance process.

Finally, the SCM team releases the modified item. All related documents are

modified to reflect the changes and the project coordinator closes the problem

report.

Adaptive Maintenance Process

In the adaptive maintenance process, changes are made to the system to

accommodate changes in its external environment. Adaptive maintenance

includes work related to enhancing software functionality. During this process,

certain system changes, additions, insertions, deletions, and modifications are

included to meet the evolving needs of the user and the environment. At times, the

original environment of the software product might change. For example, there

might be changes in operating system, business rules, and external product

characteristics. Adaptive maintenance refers to modifications that adapt to these

changes. The project coordinator plans the changes to be made. The detail plan

and the quality goals are defined for the changes. The team is formed based on the

quantum of work. The change request procedure is followed to carry out the

changes. Finally, the changes are deployed based on a deployment strategy.

Perfective Maintenance Process

Software Project Management (CS615)

417

© Copyright Virtual University of Pakistan

Perfective maintenance refers to enhancements that make the product better,

faster, smaller, better documented, better structured with more functions and

reports. It includes all efforts to improve the quality of software. Perfective

maintenance extends the software beyond its original functional requirements.

During perfective maintenance, the user or the system personnel initiates the

changes to the system. The initiator raises the change request to the project

coordinator. The changes could be a result of enhancements of new functionality

in the existing system.

After tracking-the changes, an impact analysis is done and a detail plan is made to

carry out the changes. Based on the amount of changes, a dedicated member or a

team works on the changes. The testing is done in the testing environment- and

changes are implemented in the system based on the deployment strategy.

Preventive Maintenance Process

Preventive maintenance activities make changes to software programs so that they

can be more easily corrected, adapted, and enhanced. During the preventive

maintenance process, the project coordinator identifies the potential risks.

Recommendations are made to the management for approval of the maintenance

actions. The project coordinator prepares the project detail plan for carrying out

the changes. The preventive maintenance team is formed based on the quantum of

work. The team implements the change based on the request procedure. Finally,

deployment happens based on the deployment strategy.

The maintenance process begins when the user initiates a request for a change.

The process ends when the system changes are tested and the change is released

for operation. In between, there are many activities that are coordinated and

planned using change management.

Reengineering

Reengineering is a process of abstraction of a new system from an old system.

Reengineering is the modification and evolution of software product to meet the

constantly changing business requirements. Failure to reengineer can prevent an

organization from remaining competitive and persistent. This is because every

system faces the risk of being phased out sooner than they were earlier. Therefore,

you need to develop systems that support multiple platforms and are open to

modifications and changes. Here, the role of reengineering comes into play.

Reengineering comprises reverse engineering and forward engineering.

Reverse Engineering

Reverse engineering is a process of recovering the design of the running system

from the source code. Reverse engineering involves analyzing a software system

to achieve two objectives. First, reverse engineering helps to identify the system

components and their Interactions. Second, it helps make representations of the

system on a different, higher level of abstraction.

Software Project Management (CS615)

418

© Copyright Virtual University of Pakistan

Suppose, you want to retrieve the design or a product whose design document is

not available. You can recover the design by working backwards on the product

from the source code to the design requirements. At times, you might need to

reengineer programs developed many years back. The specifications of such

programs are either unclear or was not developed at all. In such a situation, you

use reverse engineering to analyze the program at a higher level of abstraction.

Therefore, you perform reverse engineering to add a significant functionality to

the old program. You can also use it to make the system cost-effective and to

adopt new technologies.

Certain prerequisites are necessary for reverse engineering. The existing system

should be in a running condition. The latest source code should be available.

During reverse engineering, the reverse engineering team gathers information

about the source code and the design and specifications documents. They also

obtain information about the knowledge and experience of the developer. Then

the team studies the existing code and the existing documents. Then they create a

draft document from the existing code. The team discusses with the users and

modifies the draft document based on the discussions.

To perform requirement reengineering, the team first prepares a prototype. After

this, it provides the demo of the prototype to the users. Then the system

requirement specification document is modified based on the discussions. The

team obtains approval from the users on the requirements.

During design reengineering, the team studies the existing data model and the

new requirements. Then they map the requirements with the existing data model

and conduct gap analysis. After this, they modify the data model based on the gap

analysis. The team studies the behavior of the existing programs and prepares

program specifications based on the behavior and the existing code. Then the

unwanted functionality is removed from the program specifications. The program

is then modified based on the new requirements.

During construction reengineering, the team comments on the unwanted code

from the programs. Then they add remarks in the filtered code, and modify the

programs based on the new functionality. Finally, the team tests the reengineering

process. Testing involves preparing the unit level test cases, the test code, and

fixing the defects. Then the code for integration testing is released. The various

testing methodologies followed are conducting integration testing, functional

testing, independent testing, user acceptance testing, and releasing the code for

deployment.

Reverse engineering helps understand the processing of the system, understand

data, and eliminate dead code, bad coupling, and no documentation. It also

reduces the maintenance efforts. The tools used for reverse engineering are Rigi

and Refine Language Tools, static analyzer, and test editor.

Software Project Management (CS615)

419

© Copyright Virtual University of Pakistan

Reverse Engineer Forward Engineer

Existing System Proposed System

Abstraction

Forward Engineering

Forward engineering is the process of building a new program from the

requirements and design specifications of an old program. During forward

engineering, old design information is recovered from existing software and is

used to reconstitute the existing system. In the process, the quality of the existing

system is enhanced and new functions are added. Therefore, forward engineering

moves from a high-level abstraction and design to a low-level implementation.

Forward engineering is used to improve the overall performance of the system.

Figure 12.2 displays the reengineering process.

Figure 12.2: Reengineering Process

Maintenance: Best Practices

In addition to the maintenance process, there are some maintenance best practices. A

maintenance process is successful if the testing and production environment are the same.

Version control is strictly implemented using version control tools, such as VSS and

PVCS. You need to check that the deployment strategy is clearly defined and tested and

the documentation is kept up-to-date.

The members of the maintenance team management should be rotated in different

business areas to enhance efficiency. It is very essential to identify backups of the key

personnel. There should be a balance between the new development and problem fixing.

Ensure proper training, and use the latest technology. Knowledge sharing sessions also

help in improving communication within the team. There should be an online help

facility for the maintenance team, and helpdesk tools should be available to track the

problems. Periodic causal analysis of the nature of problems and corrective action need to

be conducted. To ensure successful maintenance process, you need to conduct periodic

quality reviews and monitor the quality goals of the team.

- CS615 Midterm Paper of Software Project Management year 2006

Time Allowed: 90 Minutes

www.vuzs.net

Question No. 1 Marks : 2

The first activity in risk analysis is risk management.

True

False

Question No. 2 Marks : 16

If you are given a Software Project to manage, what steps you will consider for planning of the project.

Question No. 3 Marks : 2

During the Implementation phase the software modules are coded and initial unit tests are performed.

True

False

Question No. 4 Marks : 14

a) Giving reasons for your answer based on the type of system being developed, suggest the most appropriate software process model which might be used as a basis for managing the development of the following system: (9)

- Certified Carriers is a courier company that has decided to automate its billing, customer service, and inventory systems due to an increase in their sales volume and customer strength.

- The company has no experience in automation because this is for the first time that they are planning for automating their basic services.

- The client too has no idea about the size, cost, and the duration of the project.

- They have assigned the automation project to Technology Systems.

- Technology Systems needs to analyze the systems of Certified Carriers and present a prospective: working model of the software product.

- Only after the working model is approved and signed-off by Certified Carrier, will the team draw up a specific project plan and create a development team.

- However, an analysis team is formed to create the working model, arrange meetings with the client, accept feedback, and implement all practicable feedback to the working model.

- The team at Technology Systems intends to reuse the technology and the working model to further develop and complete the creation of the software product.

b) Explain why the waterfall model of the software process is not an accurate reflection of the detailed software processes in most organizations. Why is a spiral model more realistic? (5)

www.vuzs.net

Question No. 5 Marks: 2

Both the software engineer and customer take an active role in software requirements engineering-a set of activities that is often referred to as Requirement

Managing

Recognition

Analysis

Modeling

Question No. 6 Marks : 2

The Efficiency with which a program runs on different platforms or operating systems is called:

Portability

Reusability

Configurability

Interoperability

- CS615 Midterm Paper - SOFTWARE PROJECT MANAGEMENT

FALL 2006 (Session - 3 )

www.vuzs.net

Marks: 35

Time: 60min

Question No: 1 ( Marks: 12 )

Write an outline of Software Requirements Specification document. In detail.

Question No: 2 ( Marks: 15 )

Write descriptive note on the followings: (15)

a) Waterfall model and its disadvantage if any. (5)

b) Four dimensions of a software project. (5)

c) In your opinion what are the essential Project Manager skills to execute a Software project timely and in cost-effective way meeting the specifications and quality standards. Briefly discuss two of them. (5)

Question No: 3 ( Marks: 2 )

Efficiency with which a program runs on different platforms or operating systems is Reusability

True

False

Question No: 4 ( Marks: 2 )

During the Implementation phase the software modules are coded and initial unit tests are performed

True

False

www.vuzs.net

Question No: 5 ( Marks: 2 )

-------------------is a software engineering task that bridges the gap between system level requirements engineering and software design.

Cost Analysis

Design analysis

Risk analysis

Requirements analysis

Question No: 6 ( Marks: 2 )

---------- is path finding,----------- is path following

Leadership, Management

Leader, Leadership

Management, Leadership

Manager, Management

Solution is provided by vuZs Solution Team.

You are free to distribute and use it. In case you wanted to host or re-distribute it. Please don’t remove the links of group and website.

List down the tasks of Initializing process (2)

Requirement gathering:

Scope determination:

Resource allocation

Creating an initial project plan

What is prototype (2)

A prototype is a model of a product which is used for testing before a manufacturing run is ordered

When a software engineer is provided incorrect, incomplete requirements, which areas are affected most (3)

Name any six planning process tasks (3)

Planning Process Tasks

1. Scope Planning

2. Scope Definition

3. Activity Definition

4. Activity Sequencing

5. Activity Duration Estimating

6. Resource Planning

7. Cost Estimating

8. Cost Budgeting Risk Planning

9. Schedule Development

10. Quality Planning

11. Communications Planning

12. Organization Planning

13. Staff Acquisition

14. Procurement Planning

15. Project Plan Development

Describe Formal change process in detail (5)
Discuss technology related problems in a software project (5)

Overestimated savings from reusable components and new tools and

methods:

You can reuse software components in a software project to save time, effort, and cost of creating the component again. It is important that you assess the savings that the use of such a software component provides to a software project. This expectation of both the customer and the management might not be met, if you overestimate the savings from reusing software

components.

• Switching tools in mid way: The current technology environment offers new tools and technologies for software development at a fast rate. All these tools and technologies offer the benefits of a shorter development cycle, lower costs, and under better functionality than earlier tools. You should identify and commit to the tool and technology for the software project before the project commences. Switching the tool or technology used during the software development stage causes the developers to relearn a new tool. In addition, there is a chance that it might not be possible to integrate the software already developed with the new tool.

• Integrating different software products in cross-platform implementation:

The modem software environment requires that all software should integrate with each other. However, many software projects do not plan for integration with existing software in the same or different domain. This limits the applicationofsu9h software and reduces the shelf life drastically. They key to the success of a software product is interoperability. The software project manager needs to determine the scope for the software product such that is can be integrated easily with existing software.

Elaborate the prblem in project money fuzzy users which is product related (2)

Fuzzy users: it is product related problem You also need to clarify the background characteristics of the users of the final software product at the beginning of the software project. If the description of the users is fuzzy, then the software analysis, design, and development stages may reflect the ambiguity with regard to the functions and performance of the final software product.

2) list the inputs of initiating process (2)

Initiating Process

⇒ Inputs

• Product Description

• Strategic Plan

• Selection Criteria

• Historical Information

3) what are the people related problem on software project management

• Low motivation

• Problem employees

• Unproductive work environment

• Inefficient project management style

• Lack of stakeholder interest

• Ineffective project sponsorship by management

Explain the process of controlling versions (3)

Controlling Versions

Version control combines procedures and tools to manage different versions of configuration objects that are created during software product development. To control versions, you can use Version Control Register. In Version Control Register, you enter the details of components, such as component identification numbers, their versions, and dates of validity. It is advisable to release a baseline after a version is released. Baseline is a specification or a product that is formally reviewed and agreed upon. This serves as the basis for further development. Baseline can be changed only through formal change control procedures. A baseline consists of a set of SCIs that are logically related to each other. Baselines are established when subsequent changes to the SCIs need to be controlled. Version control is essential so that everybody uses only the latest version. Any kind of version mismatch might result in rework.

Differentiate between the bibliography and appendix (5)

– The bibliography contains references to all documents that relate to the software. These include other software engineering documentation, technical references, vendor literature, and; standards.

– The appendix contains information that supplements the specifications. Tabular data, detailed description of algorithms, charts, graphs and other material, are presented as appendixes.

Elaborate the concept of product operation factors and explain all product operation factors? (5)

1. Product Operation Factors

The product operation factors determine the quality of software when a program is executed. Good quality software is not only correct and reliable but also delivers correct performance in all circumstances. Some of the factors of product operation are correctness, reliability, efficiency, integrity, and usability. You can look at the factor description in Table 1.

Table 1: Product Operation Factors

Correctness Accuracy of the program and the extent to which it fulfills design specifications

Reliability Extent to which the program is secure and its ability to recover quickly from failure.

Efficiency Performance of the program and its ability to perform tasks within a time frame

Integrity Ability of the program to take care of security and the extent to which it can prevent

unauthorized.

Usability Ease with which a user can learn, operates, and uses the program.

- CS615 Solved Paper - Midterm 2009

- From Software Project Management Midterm Papers

Spring 2009  Session 3

www.vuzs.net

Time: 60 min

M a r k s: 40

Question No: 1    ( M a r k s: 1 )

________ identifying which quality standards are relevant to the project and determining how to satisfy them.

► Quality Planning

► Communications Planning

► Organization Planning

► Staff Acquisition

Question No: 2    ( M a r k s: 1 )

These all are outputs of Initiating Process except

► Project Manager Assignments

► Constraints

► Selection Criteria

► Assumptions

Question No: 3    ( M a r k s: 1 )

Project management processes can be organized into _____________ groups

► Four

► Fiveqq

► Six

► Seven

Project management processes can be organized into five groups of one or more

processes each:

1. Initiating processes—authorizing the project or phase

2. Planning processes—defining and refining objectives and selecting the best

of the alternative courses of action to attain the objectives that the project

was undertaken to address

3. Executing processes—coordinating people and other resources to carry out

the plan

4. Controlling processes—ensuring that project objectives are met by

monitoring and measuring progress regularly to identify variances from plan

so that corrective action can be taken when necessary

5. Closing processes—formalizing acceptance of the project or phase and

bringing it to an orderly end

Question No: 4    ( M a r k s: 1 )

Product quality depends on its conformance to ______

► Software requirements

► Development standards

► Implicit requirements

► All of given

Product quality depends on its conformance to software requirements, development standards, and implicit requirements

www.vuzs.net/

http://groups.google.com/group/vuZs

Question No: 5    ( M a r k s: 1 )

_______is the technical kernel of software engineering

► Design

► Implementation

► Requirements analysis

► Testing

Design is the technical kernel of software engineering. During design, progressive refinements of data structure, architecture, interfaces, and procedural detail of software components are developed, reviewed, and documented.

Question No: 6    ( M a r k s: 1 )

Mode of specification has a great impact on quality of solution. Forcing SWE to work with incomplete, inconsistence, or misleading specifications result in frustration and confusion affecting:

► Quality

► Timeliness and

► Completeness of SW product

► All of given

Mode of specification has a great impact on quality of solution. Forcing SWE to work with incomplete, inconsistence, or misleading specifications result in frustration and confusion affecting:

– Quality

– Timeliness and

– Completeness of SW product

Question No: 7    ( M a r k s: 1 )

Finally, the specification includes a ________

► Bibliography

► Appendix

► Both Bibliography and Appendix

► Reference

Question No: 8    ( M a r k s: 1 )

Cognitive model describes a system as perceived by its _________

► User community

► Developer

► Top level management

► Manager

Question No: 9    ( M a r k s: 1 )

A review of the Software Requirements Specification is conducted by ________

► Software developer

► Customer

► Both the software developer and the customer

► Top level management

www.vuzs.net/

http://groups.google.com/group/vuZs

Question No: 10    ( M a r k s: 1 )

A meeting is conducted at a _________ and attended by both software engineers and customers.

► Software engineer site

► Neutral site

► Customer site

► Company site

Question No: 11    ( M a r k s: 1 )

The model serves as the basis for the creation of ________ for the Software.

► Design

► Maintenance

► Testing

► Specifications

The model serves as a foundation for software design and as the basis for the creation of specifications for the Software.

Question No: 12    ( M a r k s: 1 )

Throughout evaluation and solution synthesis, the analyst's primary focus is on

► "What, not "how."

► Model

► Evaluation and Synthesis

► Specification

Question No: 13    ( M a r k s: 1 )

In problem evaluation area of effort, once problems have been identified, the ___________determines what information is to be produced by the new system and what data will be provided to the system.

► Analyst

► Designer

► Coder

► Manager

Question No: 14    ( M a r k s: 1 )

Requirements are refined and analyzed to assess their clarity, completeness, and_______

► Correctness

► Consistency

► Concurrency

► None of given

Question No: 15    ( M a r k s: 1 )

A software project that meets all the stated objectives is a success of _________

► Project quality

► Project fundamental purpose

► Project management myth

► Project requirement

Question No: 16    ( M a r k s: 1 )

All of the following describe the activity list except:

► It’s an extension of the WBS

► It include all activities of the project

► It describe the WBS update

► It include a description of project activities

Not all activities of the project are indicated in the activity list. Only the controlled and planned ones

Question No: 17    ( M a r k s: 1 )

Software project are carried out sequentially and that each phase is completed before the next is taken up.

► The Prototyping Model

► The Incremental Model

► The Waterfall model

► The Spiral model

The Waterfall model: This is the traditional life cycle model. It assumes that all phases in a software project are carried out sequentially and that each phase is completed before the next is taken up.

Question No: 18    ( M a r k s: 1 )

Project management is a _________of constant communication and negotiation.

► Process

► Concept

► Practice

► None of given

project management is a process of constant communication and negotiation (google book)

Question No: 19    ( M a r k s: 1 )

These all are design phase activities except

► Output Design

► Input Design

► The software test plan

► Software Selection

Its part of requirment phase

Question No: 20    ( M a r k s: 1 )

Which organization has set the de facto standards for project management techniques?

► PMBOK

► PMI

► PMA

► PMO

The Project Management Institute (PMI) is the industry-recognized standard for project management practices

Question No: 21    ( M a r k s: 2 )

Give the name of configuration control tools?

- Automatic version control and

- Change control tools

- Monitoring, auditing and registration support utilities

- Storage facilities; a safe repository for all approved configuration items,including:

– On-site storage for the day to day development process

– Off-site storage for catastrophe recovery

Question No: 22    ( M a r k s: 3 )

Software requirements analysis a bridge between system engineering and software design, show it by diagram.

Automatic version control and

Question No: 23    ( M a r k s: 5 )

Write down the software process player’s names and their roles in projects. vuzs.net

Question No: 24    ( M a r k s: 10 )

Explain the following terms regarding project characteristics and project dimensions.

·     Temporary,

·     Unique,

·     Aims,

·     People,

·     Process

Temporary

Temporary means that every project has a definite beginning and a definite end. The end is reached when the project’s objectives have been achieved, or it becomes clear that the project objectives will not or cannot be met, or the need for  the project no longer exists and the project is terminated. Temporary does not necessarily mean short in duration; many projects last for several years. In every case, however, the duration of a project is finite; projects are not ongoing efforts

unique:

Operations and projects differ primarily in that operations are ongoing and repetitive while projects are temporary and unique. A project can thus be defined in terms of its distinctive characteristics—a project is a temporary endeavor undertaken to create a unique product or service. Temporary means that every project has a definite beginning and a definite end. Unique means that the product or service is different in some distinguishing way from all other products or services. For many organizations, projects are a means to respond to those requests that

Aims/Tasks/Purpose

The projects are designed to achieve specific targets defined in terms of aims, tasks or a purpose. The nature and size of the project depends upon complexity of the task, realization of the aims and scope of the purpose any organization wants to achieve. In short project has to be aimed for achieving certain tasks in a given time frame.

Process:

A software process provides the framework from which a comprehensive plan for software development can be established.

- Virtual University Old & Current Question Papers

- CS615 Solved Paper of Software Project Management - Midterm 2009

Published on Saturday, 28 August 2010 01:49

Written by Farhat Qudsia

- CS615 Solved Paper - Midterm 2009

- From Software Project Management Midterm Papers

Spring 2009  Session 3

www.vuzs.net

Time: 60 min

M a r k s: 40

Question No: 1    ( M a r k s: 1 )

________ identifying which quality standards are relevant to the project and determining how to satisfy them.

► Quality Planning

► Communications Planning

► Organization Planning

► Staff Acquisition

Question No: 2    ( M a r k s: 1 )

These all are outputs of Initiating Process except

► Project Manager Assignments

► Constraints

► Selection Criteria

► Assumptions

Question No: 3    ( M a r k s: 1 )

Project management processes can be organized into _____________ groups

► Four

► Five

► Six

► Seven

Project management processes can be organized into five groups of one or more

processes each:

1. Initiating processes—authorizing the project or phase

2. Planning processes—defining and refining objectives and selecting the best

of the alternative courses of action to attain the objectives that the project

was undertaken to address

3. Executing processes—coordinating people and other resources to carry out

the plan

4. Controlling processes—ensuring that project objectives are met by

monitoring and measuring progress regularly to identify variances from plan

so that corrective action can be taken when necessary

5. Closing processes—formalizing acceptance of the project or phase and

bringing it to an orderly end

Question No: 4    ( M a r k s: 1 )

Product quality depends on its conformance to ______

► Software requirements

► Development standards

► Implicit requirements

► All of given

Product quality depends on its conformance to software requirements, development standards, and implicit requirements

www.vuzs.net/

http://groups.google.com/group/vuZs

Question No: 5    ( M a r k s: 1 )

_______is the technical kernel of software engineering

► Design

► Implementation

► Requirements analysis

► Testing

Design is the technical kernel of software engineering. During design, progressive refinements of data structure, architecture, interfaces, and procedural detail of software components are developed, reviewed, and documented.

Question No: 6    ( M a r k s: 1 )

Mode of specification has a great impact on quality of solution. Forcing SWE to work with incomplete, inconsistence, or misleading specifications result in frustration and confusion affecting:

► Quality

► Timeliness and

► Completeness of SW product

► All of given

Mode of specification has a great impact on quality of solution. Forcing SWE to work with incomplete, inconsistence, or misleading specifications result in frustration and confusion affecting:

– Quality

– Timeliness and

– Completeness of SW product

Question No: 7    ( M a r k s: 1 )

Finally, the specification includes a ________

► Bibliography

► Appendix

► Both Bibliography and Appendix

► Reference

Question No: 8    ( M a r k s: 1 )

Cognitive model describes a system as perceived by its _________

► User community

► Developer

► Top level management

► Manager

Question No: 9    ( M a r k s: 1 )

A review of the Software Requirements Specification is conducted by ________

► Software developer

► Customer

► Both the software developer and the customer

► Top level management

www.vuzs.net/

http://groups.google.com/group/vuZs

Question No: 10    ( M a r k s: 1 )

A meeting is conducted at a _________ and attended by both software engineers and customers.

► Software engineer site

► Neutral site

► Customer site

► Company site

Question No: 11    ( M a r k s: 1 )

The model serves as the basis for the creation of ________ for the Software.

► Design

► Maintenance

► Testing

► Specifications

The model serves as a foundation for software design and as the basis for the creation of specifications for the Software.

Question No: 12    ( M a r k s: 1 )

Throughout evaluation and solution synthesis, the analyst's primary focus is on

► "What, not "how."

► Model

► Evaluation and Synthesis

► Specification

Question No: 13    ( M a r k s: 1 )

In problem evaluation area of effort, once problems have been identified, the ___________determines what information is to be produced by the new system and what data will be provided to the system.

► Analyst

► Designer

► Coder

► Manager

Question No: 14    ( M a r k s: 1 )

Requirements are refined and analyzed to assess their clarity, completeness, and_______

► Correctness

► Consistency

► Concurrency

► None of given

Question No: 15    ( M a r k s: 1 )

A software project that meets all the stated objectives is a success of _________

► Project quality

► Project fundamental purpose

► Project management myth

► Project requirement

Question No: 16    ( M a r k s: 1 )

All of the following describe the activity list except:

► It’s an extension of the WBS

► It include all activities of the project

► It describe the WBS update

► It include a description of project activities

Not all activities of the project are indicated in the activity list. Only the controlled and planned ones

Question No: 17    ( M a r k s: 1 )

Software project are carried out sequentially and that each phase is completed before the next is taken up.

► The Prototyping Model

► The Incremental Model

► The Waterfall model

► The Spiral model

The Waterfall model: This is the traditional life cycle model. It assumes that all phases in a software project are carried out sequentially and that each phase is completed before the next is taken up.

Question No: 18    ( M a r k s: 1 )

Project management is a _________of constant communication and negotiation.

► Process

► Concept

► Practice

► None of given

project management is a process of constant communication and negotiation (google book)

Question No: 19    ( M a r k s: 1 )

These all are design phase activities except

► Output Design

► Input Design

► The software test plan

► Software Selection

Its part of requirment phase

Question No: 20    ( M a r k s: 1 )

Which organization has set the de facto standards for project management techniques?

► PMBOK

► PMI

► PMA

► PMO

The Project Management Institute (PMI) is the industry-recognized standard for project management practices

Question No: 21    ( M a r k s: 2 )

Give the name of configuration control tools?

- Automatic version control and

- Change control tools

- Monitoring, auditing and registration support utilities

- Storage facilities; a safe repository for all approved configuration items,including:

– On-site storage for the day to day development process

– Off-site storage for catastrophe recovery

Question No: 22    ( M a r k s: 3 )

Software requirements analysis a bridge between system engineering and software design, show it by diagram.

Automatic version control and

Question No: 23    ( M a r k s: 5 )

Write down the software process player’s names and their roles in projects. vuzs.net

Question No: 24    ( M a r k s: 10 )

Explain the following terms regarding project characteristics and project dimensions.

·     Temporary,

·     Unique,

·     Aims,

·     People,

·     Process

Temporary

Temporary means that every project has a definite beginning and a definite end. The end is reached when the project’s objectives have been achieved, or it becomes clear that the project objectives will not or cannot be met, or the need for  the project no longer exists and the project is terminated. Temporary does not necessarily mean short in duration; many projects last for several years. In every case, however, the duration of a project is finite; projects are not ongoing efforts

unique:

Operations and projects differ primarily in that operations are ongoing and repetitive while projects are temporary and unique. A project can thus be defined in terms of its distinctive characteristics—a project is a temporary endeavor undertaken to create a unique product or service. Temporary means that every project has a definite beginning and a definite end. Unique means that the product or service is different in some distinguishing way from all other products or services. For many organizations, projects are a means to respond to those requests that

Aims/Tasks/Purpose

The projects are designed to achieve specific targets defined in terms of aims, tasks or a purpose. The nature and size of the project depends upon complexity of the task, realization of the aims and scope of the purpose any organization wants to achieve. In short project has to be aimed for achieving certain tasks in a given time frame.

Process:

A software process provides the framework from which a comprehensive plan for software development can be established.

List down the tasks of Initializing process (2)

Requirement gathering:

Scope determination:

Resource allocation

Creating an initial project plan

What is prototype (2)

A prototype is a model of a product which is used for testing before a manufacturing run is ordered

When a software engineer is provided incorrect, incomplete requirements, which areas are affected most (3)

Name any six planning process tasks (3)

Planning Process Tasks

1. Scope Planning

2. Scope Definition

3. Activity Definition

4. Activity Sequencing

5. Activity Duration Estimating

6. Resource Planning

7. Cost Estimating

8. Cost Budgeting Risk Planning

9. Schedule Development

10. Quality Planning

11. Communications Planning

12. Organization Planning

13. Staff Acquisition

14. Procurement Planning

15. Project Plan Development

Describe Formal change process in detail (5)
Discuss technology related problems in a software project (5)

Overestimated savings from reusable components and new tools and

methods:

You can reuse software components in a software project to save time, effort, and cost of creating the component again. It is important that you assess the savings that the use of such a software component provides to a software project. This expectation of both the customer and the management might not be met, if you overestimate the savings from reusing software

components.

• Switching tools in mid way: The current technology environment offers new tools and technologies for software development at a fast rate. All these tools and technologies offer the benefits of a shorter development cycle, lower costs, and under better functionality than earlier tools. You should identify and commit to the tool and technology for the software project before the project commences. Switching the tool or technology used during the software development stage causes the developers to relearn a new tool. In addition, there is a chance that it might not be possible to integrate the software already developed with the new tool.

• Integrating different software products in cross-platform implementation:

The modem software environment requires that all software should integrate with each other. However, many software projects do not plan for integration with existing software in the same or different domain. This limits the applicationofsu9h software and reduces the shelf life drastically. They key to the success of a software product is interoperability. The software project manager needs to determine the scope for the software product such that is can be integrated easily with existing software.

Elaborate the prblem in project money fuzzy users which is product related (2)

Fuzzy users: it is product related problem You also need to clarify the background characteristics of the users of the final software product at the beginning of the software project. If the description of the users is fuzzy, then the software analysis, design, and development stages may reflect the ambiguity with regard to the functions and performance of the final software product.

2) list the inputs of initiating process (2)

Initiating Process

⇒ Inputs

• Product Description

• Strategic Plan

• Selection Criteria

• Historical Information

3) what are the people related problem on software project management

• Low motivation

• Problem employees

• Unproductive work environment

• Inefficient project management style

• Lack of stakeholder interest

• Ineffective project sponsorship by management

Explain the process of controlling versions (3)

Controlling Versions

Version control combines procedures and tools to manage different versions of configuration objects that are created during software product development. To control versions, you can use Version Control Register. In Version Control Register, you enter the details of components, such as component identification numbers, their versions, and dates of validity. It is advisable to release a baseline after a version is released. Baseline is a specification or a product that is formally reviewed and agreed upon. This serves as the basis for further development. Baseline can be changed only through formal change control procedures. A baseline consists of a set of SCIs that are logically related to each other. Baselines are established when subsequent changes to the SCIs need to be controlled. Version control is essential so that everybody uses only the latest version. Any kind of version mismatch might result in rework.

Differentiate between the bibliography and appendix (5)

– The bibliography contains references to all documents that relate to the software. These include other software engineering documentation, technical references, vendor literature, and; standards.

– The appendix contains information that supplements the specifications. Tabular data, detailed description of algorithms, charts, graphs and other material, are presented as appendixes.

Elaborate the concept of product operation factors and explain all product operation factors? (5)

1. Product Operation Factors

The product operation factors determine the quality of software when a program is executed. Good quality software is not only correct and reliable but also delivers correct performance in all circumstances. Some of the factors of product operation are correctness, reliability, efficiency, integrity, and usability. You can look at the factor description in Table 1.

Table 1: Product Operation Factors

Correctness Accuracy of the program and the extent to which it fulfills design specifications

Reliability Extent to which the program is secure and its ability to recover quickly from failure.

Efficiency Performance of the program and its ability to perform tasks within a time frame

Integrity Ability of the program to take care of security and the extent to which it can prevent

unauthorized.

Usability Ease with which a user can learn, operates, and uses the program.

CS615 Software Project Management  Solved Quiz 
shared by Gulshan Ali

Like all engineering disciplines, requirements engineering is not conducted in a
Sporadic random
Otherwise haphazard fashion
But instead is the systematic use of proven approaches?
All of given

_____________ includes consideration such as the post-implementation support activities provided to the customer.

Training plan creation
User acceptance plan
Implementation plan creation
Support plan creation

Requirements are refined and analyzed to assess their clarity, completeness, and_______ 
Correctness
Consistency
Concurrency
None of given
__________ defines the duration of implementation and the hard and software perquisites for implementing the software product. 
Training plan creation
User acceptance plan
Implementation plan creation
Support plan creation

Implementation of software quality often associated with
Project Manager - unconfirmed
Software developer
Customer
User

A software project that meets all the stated objectives is a success of _________
Project quality
Project fundamental purpose 
Project management myth
Project requirement

- CS615 - Software Project Management  Solved MCQs from Quiz # 2

Muhammad Qaisar Rafique  

The overall role of Software in a larger system is identified during 
Requirements engineering 
Process engineering 
System engineering 
All of given

The British Standards Institution (1986) has stated the quality as 
The ability of a software product to satisfy its specified requirements 
"An inherent or distinguishing characteristic or a property" 
“Quality is in the eye of the beholder, a matter, of the client's judgment.” 
All of the given
www.vuzs.net
McCall (MCC77) and his colleagues proposed some software quality factors based on _______ most important aspects of a software product:
4 
3 
6 
5

Inefficient project management style is a
Product-related problems 
Technology-related problems 
Process-related problems 
People-related problems

Upon evaluating current problems and desired information (input and output), the analyst begins to ______ 
Synthesize solutions 
Model 
Specification 
All of given

These all are Product Revision Factors except
Usability 
Maintainability 
Flexibility 
Testability

We can classify the problems that affect software projects into _______ categories 
3 
4 
5 
6

The check-in and checkout facilities provide_________ 
Best control 
Component control 
SCI control 
Synchronization control

The code generation step performs the task
Translated specification into a machine-readable form 
Translated design into a machine-readable form 
Translated requirements into a machine-readable form 
Translated user data into a machine-readable form

Research-oriented software development is a
Technology-related problems 
Process-related problems 
People-related problems 
Product-related problems

A meeting is conducted at a _______ and attended by both software engineers and customers.
Software engineer site
Neutral site
Customer site
Company site

Reviews conducted at each of this phase/s_____
Analysis
Design
Coding
All of given


All given below are the problems that affect software projects except:

Product-related problems
Technology-related problems
Procedure-related problems
People-related problems

_______is the technical kernel of software engineering

Design
Implementation
Testing
Requirement Analysis

Both the software engineer and customer take an active role in software requirements engineering-a set of activities that is often referred to as
Analysis
Design
Specification
System acceptance

The model serves as the basis for the creation of ______ for the Software.
Design
Maintenance
Testing
Specifications

Before requirements can be analyzed, modeled, or specified they must be gathered through a/an _______
Elicitation process
Interviewing
Meeting
None of given

Technology-related problems include _____
Overestimated savings from reusable components and new tools and methods
Switching tools in mid way
Integrating different software products in cross-platform implementation
All of given

Insufficient identification is a
Technology-related problems
Process-related problems
People-related problems
Product-related problems

Throughout evaluation and solution synthesis, the analyst's primary focus is on ______
“Not what, not "how"
"What, also "how"
"What, not "how"
None of given

The overall role of Software in a larger system is identified during
Requirements engineering 
Process engineering 
System engineering 
All of given


In problem evaluation area of effort, once problems have been identified, the ___________determines what information is to be produced by the new system and what data will be provided to the system.
Analyst 
Designer 
Coder 
Manager

A ‘facilitator’ controls the meeting can be ________

Customer 
A developer 
An outsider 
All of given

Version control combines ______ to manage different versions of configuration objects that are created during software product development.
Procedure 
Tools 
Procedure and Tools 
None of given

Many software projects digress from the original scope because of the nature of the software product or technology used, it’s happen in ________
Product scope changed toward the end of the project life cycle 
Research-oriented software development 
Defined scope 
Fuzzy users


When you build a product or system, it's important to go through a series of predictable steps – a road map that helps you create a timely, high-quality result, The road map that you follow is called a ________
Software design 
Software process 
Software schedule 
Framework

Before requirements can be analyzed, modeled, or specified they must be gathered through a/an _______
Elicitation process 
Interviewing 
Meeting 
None of given

Defined scope is a
Technology-related problems 
Product-related problems 
Process-related problems 
People-related problems

- CS615 - Software Project Management MCQs from Quiz # 3

__________ is based on soft skills and relies more on human factors, such as collecting information during group discussions
Select correct option:
Source lines of Code (SLOC)
Function Point (FP)
Constructive Cost Model (COCOMO)
Delphi technique

In __________ the planner develops estimates of the information domain.
Select correct option:
Function point sizing
Standard component sizing
Change sizing
All of given

www.vuzs.net

Describe where the work must be performed. Specify the location of hardware and software and where the people must perform the work is called __________
Select correct option:
Scope of work
Location of Work
Period of Performance
Deliverables Schedule

A _________ is defined as "the work breakdown that covers the acquisition of a specific defense material item and is related to contractual effort."
Select correct option:
Program WBS
Contract WBS
Contract Program WBS
None of given

A __________ extends the Program WBS to a lower level in order to provide management and cost information to the Government
Select correct option:
Program WBS
Contract WBS
Contract Program WBS
None of given

Effective project managers_________
Lead by example
Are visionary
Are good motivators, communicators, supports team members and stand up to upper management where necessary?
All of given

There are ________ types of Work Breakdown Structures.
None of given
Two
Three
Four

Cost, effort, risks, and resources are the factors included in-------- ►; Estimation. ►; Testing. ►; Development. ►; Maintenance..

Question No: 6 ( M a r k s: 2 ) - Please choose one

The nature of software applications can be characterized by their information ►; complexity. ►; content. ►; determinacy. ►; content and determinacy..

Question No: 7 ( M a r k s: 2 ) - Please choose one

The software quality assurance activity which is performed to check errors in logic, function, or implementation for any representation of the software is called : ►; Inspection. ►; Formal technical review(s). ►; Walkthrough. ►; Auditing..

Question No: 8 ( M a r k s: 2 ) - Please choose one

Which of the items listed below is not one of the software engineering layers? ►; Process. ►; Manufacturing. ►; Methods. ►; Tools..

Question No: 9 ( M a r k s: 2 ) - Please choose one

The first step in project planning is to -------------------- ►; Determine the budget. ►; Select a team organizational model. ►; Determine the project constraints. ►; Establish the objectives and scope..

Question No: 10 ( M a r k s: 2 ) - Please choose one

The requirements phase precedes the design phase ►; True. ►; False..

Question No: 11 ( M a r k s: 2 ) - Please choose one

Software engineers do not need to consider hardware when designing a computer-based system ►; True. ►; False..

CS615 – Software Project Management Online Quiz # 2

Total Questions: 8

Question # 1 of 8 ( Start time: 07:32:00 PM )  Total M a r k s: 1

…………. theory when the deliverables of a project are more important than its phases. This normally happens when the deliverables are decided before the project begins.

Select correct option:

Project life-cycle-based

Scheduled

None of given

Deliverable-based (handouts pdf file, page 277)

Question # 2 of 8

Predecessor activities need to ------------ before the next can begin. After a predecessor activity is completed, the successor activity becomes the predecessor for another activity.

Select correct option:

Both start and end

End (handouts, page 297)

Start

None of given

Question # 3 of 8

Each …………. can be subdivided into sub tasks.

Select correct option:

None of given

Program

Task (handouts, page 275)

Project

Question # 4 of 8

Using PERT and CPM, -----------------------, helps you complete a project on time. By using these techniques, you can determine the latest time by when an activity should start to be completed on time.

Select correct option:

Individually

Combination

Individual and Combine (handouts, page 296)

None of given

Question # 5 of 8 ( Start time: 07:34:55 PM )  Total M a r k s: 1

Over the course of the project, a comparison of the due date and the date delivered provides a metric for how well deliverable dates are ………………. by the project team.

Select correct option:

Met (handouts, page 274)

Scheduled

None of given

Changed

Question # 6 of 8

Risk analysis and management are a series of steps that help a software team to understand and manage ------------------------.

Select correct option:

Uncertainty (handouts, page 305)

Crises

None of given

Problem

Question # 7 of 8 ( Start time: 07:36:07 PM )  Total M a r k s: 1

A node on a network schedule is that point in time at which an activity ----------------.

Select correct option:

Begins

Begins or Ends (handouts, page 297)

Ends

None of given

Question # 8 of 8

To ------------------- risks from occurring, the project team prepares the risk plan before the commencement of the project.

Select correct option:

Avoid (handouts, page 312)

Deal

None of given

Manage

1. Which organization has set the de facto standards for project management techniques?

A. PMBOK

B. PMO

C. PMI

D. PMA

Answer: C

The Project Management Institute (PMI) is the industry-recognized standard for project management practices.

2. The VP of marketing approaches you and requests that you change the visitor logon screen on the company's website to include a username with at least six characters. This is considered:

A. Project initiation

B. Ongoing operations

C. A project

D. Project execution

Answer: B

Projects exist to create a unique product or service. The logon screen in this question is not a unique product. A minor change has been requested, indicating this is an ongoing operation function. Some of the criteria for projects are that they are unique, temporary with definitive start and end dates, and considered complete when the project goals are achieved.

3. Your company manufactures small kitchen appliances. They are introducing a new product line of appliances in designer colors with distinctive features for kitchens in small spaces. These new products will be offered indefinitely starting with the spring catalog release. Which of the following is true?

A. This is a project because this new product line has never been manufactured and sold by this company before.

B. This is an ongoing operation because the company is in the business of manufacturing kitchen appliances. Introducing designer colors and features is simply a new twist on an existing process.

C. This is an ongoing operation because the new product line will be sold indefinitely. It's not temporary.

D. This is not a project or an ongoing operation. This is a new product introduction not affecting ongoing operations.

Answer: A

This is a project. The product line is new, which implies this is a unique product-it hasn't been done before. We can discern a definite start and end date by the fact that the new appliances must be ready by the spring catalog release.

4. Your company manufactures small kitchen appliances. They are introducing a new product line of appliances in designer colors with distinctive features for kitchens in small spaces. These new products will be offered indefinitely starting with the spring catalog release. In order to determine the characteristics and features of the new product line, you will have to perform which of the following?

A. Fast tracking

B. Consulting with the stakeholders

C. Planning the project life cycle

D. Progressive elaboration

Answer: D

Progressive elaboration is the process of determining the characteristics and features of the product of the project. Progressive elaboration is carried out in steps in detailed fashion.

5. A project is considered successful when:

A. The product of the project has been manufactured.

B. The project sponsor announces the completion of the project.

C. The product of the project is turned over to the operations area to handle the ongoing aspects of the project.

D. The project meets or exceeds the expectations of the stakeholders.

Answer: D

A project is considered successful when stakeholder needs and expectations are met or exceeded.

6. The VP of customer service has expressed concern over a project you're involved in. His specific concern is that if the project is implemented as planned, he'll have to purchase additional equipment to staff his customer service center. The cost is substantial and was not taken into consideration in the project budget. The project sponsor insists that the project must go forward as originally planned or the customer will suffer. Which of the following is true?

A. The VP of customer service is correct. Since the cost was not taken into account at the beginning of the project, the project should not go forward as planned. Project initiation should be revisited to examine the project plan and determine how changes can be made to accommodate customer service.

B. The conflict should be resolved in favor of the customer.

C. The conflict should be resolved in favor of the project sponsor.

D. The conflict should be resolved in favor of the VP of customer

service.

Answer: B

Conflicts between stakeholders should always be resolved in favor of the customer. This question emphasizes the importance of identifying your stakeholders and their needs as early as possible in the project. We'll discuss this more in later chapters.

7. Which of the following brings together a set of tools and techniques used to describe, organize, and monitor the work of project activities?

A. Project managers

B. Guide to the PMBOK

C. Project management

D. Stakeholders

Answer: C

Project management brings together a set of tools and techniques to organize project activities. Project managers are the ones responsible for managing the project processes.

8. What are the triple constraints?

A. Time, schedules, and quality

B. Time, availability, and quality

C. Time, money, and schedules

D. Time, money, and quality

Answer: D

The triple constraints that drive all projects are time, money, and quality.

9. You are the project manager for a large construction project. The project objective is to construct a set of outbuildings to house the Olympic support team that will be arriving in your city 18 months from the project start date. You've been given a budget of $12 million to complete this project. Resources are easily attained. Which of the triple constraints is the primary constraint for this project?

A. Time, because the date cannot be moved

B. Money, because the budget is set at $12 million

C. Resources, because they're not fixed

D. Quality, because the buildings have to be functional and safe

Answer: A

The primary constraint on this project is time because the date absolutely cannot move. The Olympics are scheduled to begin on a certain date, and this can't be changed. The budget is also a constraint because it's set at $12 million, but in this example, it would be a secondary constraint. It's important that the project manager understands the priority of the constraints and manages to them.

10. You are the project manager for a large construction project. The project objective is to construct a set of outbuildings to house the Olympic support team that will be arriving in your city 18 months from the project start date. Resources are not readily available as they are currently assigned to other projects. Jack, an expert crane operator, is needed for this project two months from today. Which of the following skills will you use to get Jack assigned to your project?

A. Negotiation and influencing skills

B. Communication and organizational skills

C. Communication skills

D. Problem-solving skills

Answer: A

Negotiation and influencing skills are needed to convince Jack's boss and come to agreement concerning his assignment.

11. You are a project manager with technical expertise in the pharmaceutical industry. You've decided to try your hand at project management in the entertainment industry. Which of the following is true?

A. You will likely be successful because communication skills are your strong suit. You anticipate having technical experts on your project team to address industry specifics that you're not familiar with.

B. You will likely be successful because your organizational skills are excellent. You anticipate having technical experts on your project team to address industry specifics that you're not familiar with.

C. You will probably be successful because you have a friend in the entertainment industry that has briefed you on all the important aspects of this project that you'll need to know. You anticipate having technical experts on your project team to address industry specifics that you're not familiar with.

D. You will probably not be successful because you have little knowledge of the entertainment industry even though you anticipate having technical experts on your project team to address industry specifics that you're not familiar with.

Answer: A

Project management processes span industries. A project manager can take these skills across industries and apply them successfully. Technical experience in the industry doesn't hurt, but it's not required. The most important skill any project manager can have is communication skills. Poor communication skills might lead to an unsuccessful conclusion no matter how strong the project manager's other skills are.

12. You are managing a project to install a new postage software system that will automatically print labels and administer postage for certified mailings, overnight packages, and other special mailing needs. You've attempted to gain the cooperation of the business analyst working on this project and need some answers. She is elusive and tells you that this project is not her top priority. To avoid situations like this in the future, you should:

A. Establish the business analyst's duties well ahead of due dates and tell her you'll be reporting on her performance to her functional manager.

B. Establish the business analyst's duties well ahead of due dates and tell her you are expecting her to meet these expectations because the customer is counting on the project meeting due dates to save significant costs on their annual mailings.

C. Negotiate with the business analyst's functional manager during the planning process to establish expectations and request to participate in the business analyst's annual performance review.

D. Negotiate with the business analyst's functional manager during the planning process to establish expectations and inform the functional manager of the requirements of the project. Agreement from the functional manager will assure the cooperation of the business analyst.

Answer: C

Negotiate with the functional manager to participate in the business analyst's annual performance review.

13. The amount of authority a project manager possesses can be related to:

A. The project manager's communication skills

B. The organizational structure

C. The amount of authority the manager of the project manager

possesses

D. The project manager's influencing skills

Answer: B

The level of authority the project manager has is determined by the organizational structure. For instance, in a functional organization, the project manager has little to no authority, but in a projectized structure, the project manager has full authority.

14. What is one of the advantages of a functional structure?

A. All employees report to one manager and have a clear chain of command.

B. All employees report to two or more managers, but project team members show loyalty to functional managers.

C. The organization is focused on projects and project work.

D. Teams are collocated.

Answer: A

An advantage for employees in a functional organization is that they have only one supervisor and a clear chain of command exists.

15. You have been assigned to a project in which the objectives are to direct customer calls to an Interactive Voice Response system before being connected to a live agent. You are in charge of the media communications for this project. You report to the project manager in charge of this project and the VP of marketing, who share responsibility for this project. Which organizational structure do you work in?

A. Functional organization

B. Weak matrix organization

C. Projectized organization

D. Balanced matrix organization

Answer: D

Employees in a balanced matrix often report to two or more managers. Functional managers and project managers share authority and responsibility for projects. There is a balance of power between the functional managers and project managers.

16. You have been assigned to a project in which the objectives are to expand three miles of the north-south highway through your city by two lanes in each direction. You are in charge of the demolition phase of this project, and you report to the project manager in charge of this project. You have been hired on contract and will be released at the completion of the demolition phase. What type of organizational structure does this represent?

A. Functional organization

B. Weak matrix organization

C. Projectized organization

D. Balanced matrix organization

Answer: C

Projectized organizations are focused on the project itself. One issue with this type of structure is determining what to do with project team members when they are not actively involved on the project. One alternative is to release them when they are no longer needed.

17. What are the five project management process groups, in order?

A. Initiation, Executing, Planning, Controlling, and Closing

B. Initiation, Controlling, Planning, Executing, and Closing

C. Initiation, Planning, Controlling, Executing, and Closing

D. Initiation, Planning, Executing, Controlling, and Closing

Answer: D

Remember the acronym that sounds like syrup of ipecac: IPECC.

18. You have been assigned to a project in which the objectives are to expand three miles of the north-south highway through your city by two lanes in each direction. You are interested in implementing a new project process called design-build in order to speed up the project schedule. The idea is that the construction team will work on the first mile of the highway reconstruction at the same time the design team is coming up with plans for the third mile of the reconstruction rather than completing all design before any construction begins. This is an example of:

A. Managing the projects as a program

B. Fast tracking

C. Progressive elaboration

D. Collocation

Answer: B

Fast tracking is starting a new phase before the phase you're working on is completed. This compresses the project schedule, and the project is completed sooner as a result.

19. During which project management process are risk and stakeholder's ability to influence project outcomes the highest at the beginning of the process?

A. Planning

B. Executing

C. Initiation

D. Controlling

Answer: C

The Initiation process is where stakeholders have the greatest ability to influence outcomes of the project. Risk is highest during this stage because of the high degree of unknown factors.

20. You are a project manager working on gathering requirements and establishing estimates for the project. Which process group are you in?

A. Planning

B. Executing

C. Initiation

D. Controlling

Answer: A

The Planning process is where requirements are fleshed out, stakeholders are identified, and estimates on project costs and time are made.

Assignment

Instructions: Please make bold the correct option only

1. Basit is the project manager working on the Resource Planning process. He should consider all of the following when developing the resource requirements output except:

- WBS

- Supply purchase policies

- Resource rates

- Special knowledge and talents

2. All of the following are true regarding the tools and techniques of activity sequencing except:

- GERT uses analogous methods

- GERT allows for loops

- GERT is a conditional diagramming method

- GERT allows for conditional branches

3. Pervaiz Elahi is a project manager for Changing Tides Video games. He has produced a project network diagram and has updated the activity list. Which process have he just finished?

- The Activity Sequencing process, which identifies all the specific activities of the project

- The Activity Sequencing process, which identifies all the activities dependences

- The activity duration Estimating process, which diagram project network time estimates

- The activity duration Estimating process, which identifies all the dependent activities of the project

4. Pervaiz Elahi is a project manager for Changing Tides Video games. He has gathered the inputs of for the Activity Duration Estimation process. He will employ which tools and techniques to produce the outputs for this process?

        Activity list, analogous estimating, quality based durations, and alternatives identification

        Activity list, analogous estimating, expert judgment, and quality based durations

        Expert judgment, analogous estimating, quality based durations, and reserve time

        Expert judgment, alternative identification, quality based durations, and reserve time

5. As a project manager, you know that all of the following are true concerning analogous estimating techniques except:

- It’s a qualitatively based estimating technique

- It’s a Top-down estimating technique

- It’s a tool and technique of Activity Duration Estimating  and  Cost Estimating

- It’s a form of expert judgment

6. All of the following are true regarding parametric modeling except:

- It’s a form of Top-down estimating

- It’s a mathematical model

- It’s a tool used to estimate project costs

- It’s a tool used to estimate project time

7. Which logical relationship does the PDM use most often?

- Start to finish

- Start to start

- Finish to finish

- Finish to start

8. One of the most powerful leadership tools a project manager is has his/her_______

- Own knowledge

- Own experience

- Own behavior

- Own reference

9. The organization structure that provides the project manager with the most authority over the project team is:

- Functional

- Balanced matrix

- Strong matrix

- Projectized

10. Using an EFFORT RATIO for each type of change in________

- Fuzzy logic sizing

- Function point sizing

- Changing sizing

- Standard component sizing

11. What is one of the problems with project management software?

- The project manager manages the software instead of the project

- Project duration calculations are sometimes approximate

- You cannot override the project management software decisions regarding schedule

- It’s expensive and difficult to use

12. Which of the following is displayed as an S-curve?

- Gantt

- Cost baseline

- Critical path

- PERT

13. If you know expected value is 500 and the standard deviation is 12, you can ay with approximately a 95 percent confidence rating which of the following?

- The activity will take between 488 and 512 days

- The activity will take between 464 and 536 days

- The activity will take between 494 and 506 days

- The activity will take between 476 and 524 days

14. If your expected value is 110 and the standard deviation is 12, which of the following is true?

- There is approximately a 99 percent chance of completing this activity between 86 and 134 days

- There is approximately a 68 percent chance of completing this activity between 98 and 122 days

- There is approximately a 95 percent chance of completing this activity between 98 and 122 days

- There is approximately a 75 percent chance of completing this activity between 86 and 134 days

15. Which of the following tools and techniques shows the impacts of one decision over another as well as the probability and cost of each risk along a logical path?

- Simulation

- Decision tree

- Probability / impact risk matrix

- Sensitivity analysis

16. All of the following strategies are tools and techniques of Risk Response Planning used to reduce or control risk except?

- Mitigation

- Simulation

- Avoidance

- Acceptance

17. Object points are measurable code sections in an object-oriented programming language, such as________

- C++

- Ada

- Java

- All of the given

18. __________ involves determining what qualities are to be used to perform project activities.

- Resource planning

- Cost estimating

- Cost budgeting

- Cost control

19. The resources assigned to them will significantly influences the duration of most activities.

- True

- False

20. Using the intermediate COCOMO technique effort is calculated in___________

- Two-step process

- Three-step process

- Four-step process

- Five-step Process

Objectives

This assignment has been designed so that you would be able to understand the Planning and WBS.

Assignment

Instructions: Please make bold the correct option only

1. Which of the following is true regarding NPV?

- NPV assumes reinvestment at the cost of capital

- NPV decisions should be made based on the highest value for all of the selections

- NPV assumes reinvestment at the prevailing rate

- NPV assumes reinvestment at the NPV rate

2. Hasnain is a project manager for VU International. Since he doesn’t sleep much, he get a lot of project work done. He is considering recommending a project that cost s Rs. 575’000, and expected inflows are Rs. 25000 per quarter for the first 2 years, then Rs. 75000 per quarter thereafter.   What is the pay back period?

- 40 months

- 38 months

- 39 months

- 41 months

3. Mathematical models using linear, dynamic, integer, or algorithm models are considered:

- Project selection criteria

- A form of expert judgment

- Project selection methods

- A form of historical information

4. WBS Is Not:

- The WBS should contains 100% of the work defined by the scope or contract

- Development of WBS should involve the entire project team

- A listing of tasks or activities

- Should captures all deliverables (Internal, External, Interim) in terms of work to be completed

5. COMSAT project selection committee used a weighted scoring model and found that project BAT, with a score of 54, should be chosen over the other competing projects. Which of the following is true?

- Weighted scoring models are a benefit measurement method, which is tool and technique in the Initiation process

- Weighted scoring models are constraint optimization method, which is output of  the  Initiation process

- Weighted scoring models are constraint optimization method, which is tool and technique in the Initiation process

- Weighted scoring models are a benefit measurement method, which is output of  the  Initiation process

6. Obtaining forma project plan approval and sign-off is important for all of the following reason except:

- Stakeholders are aware of the specific details regarding project schedule, budgets, and risk

- Stakeholders will be more likely to cooperate

- Stakeholders are aware of the project details, which makes them more likely to participate in future project decisions

- Stakeholders are able to recommend a project  planning methodology to follow throughout the remaining process group

7. All of the following are true regarding the project plan except:

- Some of its input and outputs from other planning processes

- It’s used to guide the project Executing and Controlling processes and it is the baseline used to measure project performance

- It consists of one document that should be formally approved and signed by stakeholder

- It contains things like the WBS, project schedule , and resource assignment

8. An activities list is typically shown in this ways.

- It can be shown as an outline

- It can be shown as an outline or it can be graphically presented

- It can be graphically presented

- None of the given

9. Always remember that projects are in dynamic working environments, so try to maintain flexibility in the work breakdown structure.

- Always true

- Always false

- Sometimes true sometimes false

- Depends on condition

10. To create a schedule, you can use project management tools;

- Gantt charts

- Network-scheduling techniques

- PERT

- All of given

11.  Usman is project manager for a new website for a local zoo. He needs to perform Quantitative Risk Analysis. He will use all of the following tools and techniques to accomplish this except:

- Overall risk ranking for the project

- List of prioritized risk

- Inputs to other processes

- List of risks for additional analysis and management

12. Which of the following describes the cost of quality associated with scrapping, rework, and downtime?

- Internal failure

- External failure

- Prevention cost

- Appraisal cost

13. Choudhary & Brothers hardware vendor left you voicemail saying that a snowstorm in the Midwest will prevent your equipment from arriving on time. You identified a risk response for this risk and have arranged for a local company to lease you the needed equipment until yours arrives. This is an example of which risk response strategy?

- Transference

- Acceptance

- Mitigation

- Avoidance

14. What document outlines the action steps to be taken if an identified risk event should occur?

- Project plan

- Corrective action Plan

- Contingency Plan

- Risk response plan

15. Tools and techniques for risk identification include all but:

- Checklist

- Risk assessment

- Interviewing

- Assumption analysis

16. Tools and techniques for Performance reporting are:

- Performance review

- Variance analysis

- Trend analysis

- All of the given

17. Analogous estimating is a form of _________

- Expert Judgment

- Bottom up estimating

- Delphi method

- Computerized estimating

18. ____________ is another term for top down estimating.

- Life cycle costing

- Parametric modeling

- Analogous estimating

- Work package

19. Assumptions generally involve:

- A degree of risk

- Financial control

- Historical information

- Lesson learned

20. Receivers in the communications model filter their information through all of the following except:

- Culture

- Knowledge of subject

- Conflict

- Language

Quiz Solution:

1- The presence of which of the given factors is mandatory in a quality assured software

a)       Change adaptive

b)       Faulty

c)       Correctness

d)      Both Change adaptive and Correctness

2- Which of the following testing technique is followed to ensure that the software user requirements are being met?

a)       White box

b)       Gray box

c)       Blue box

d)      Black box

3- Which of the following testing techniques is usually used during implementation of individual modules?

a)      White Box

b)       Black Box

c)       Integration testing

d)       None of given

4- How do the dynamic testers confirm that the executions of a program (other than the expected execution of a program) are running accurately?

a)      Some important program input are selected from the set of all and executed

b)       It is hard to confirm that

c)       The execution of the program other that the intended execution is useless to test

d)       None of given

5- The execution of a program is tested by a model based approach in-case of

a)       Formal testing

b)       Dynamic testing

c)       Static testing

d)       Unit testing

6- What is the difference between formal methods and testing?

a)      Formal methods aim at verification and proving correctness, while testing can only show the presence of errors.

b)       Testing is done only in the third phase of SDLC whereas Formal methods are done in all the phases of SDLC except Testing phase

c)       There is no big difference between the both

d)       Testing can only be done after the requirements gathering phase of SDLC whereas Formal methods can be applied before that.

7- The main idea behind symbolic execution is to use symbolic values, instead of actual data, as input values, and to represent the values of program variables as symbolic expressions.

a)      True

b)       False

8- The purpose of mutation testing is

a)       to help the tester develop effective tests or

b)       to locate weaknesses in the test data used for the program never accessed during execution

c)       to locate weaknesses in the test data used in sections of the code that are seldom  accessed during execution

d)      All of given

9- Which of the following is the example of mutation operators?

a)       Replace each boolean sub expression with true and false.

b)       Replace each arithmetic operation with another one, e.g. + with *, - and /.

c)       Replace each boolean relation with another one, e.g. > with >=, == and <=.

d)      All of given

10- Which of the following testing approach is used to test the software functionality that previously worked as desired, stops working or no longer works in the same way that was previously planned?

a)       Integration testing

b)       Unit testing

c)       Regression testing

d)       Dynamic testing

11- Which of the following can be a type of regression?

a)       Local - changes introduce new bugs.

b)       Unmasked - changes unmask previously existing bugs.

c)       New feature regression

d)      All of given

12- Which of the following testing is required when it needs to test the software after combining the modules into a group?

a)       Unit

b)       Regression

c)       White box

d)      Integration

13- SQA encompasses the entire software development process

a)      True

b)       False

14- The process of software quality assurance (SQA) is designed to prevent software defects and inefficiencies

a)      True

b)       False

15- There is no difference between software quality assurance and software testing

a)       True

b)      False

Question # 2 of 10

The distinguishing characteristics of a software product are _________

Select correct option:

Cyclomatic complexity and cohesion

Function points and lines of code

all of the given

None of given

The distinguishing characteristics of a software product are the cyclomatic

complexity, cohesion, function points, and lines of

Question # 3 of 10

Insufficient identification is a

Select correct option:

Technology-related problems

Process-related problems

People-related problems

Product-related problems

Insufficient identification: Unidentified, partially identified, and unplanned

risks pose a threat to the success of a software project. You need to intensively

identify risks and evolve a risk management plan such that the project is

completed successfully, on time.

Question # 4 of 10

________of the system is an effort to better understand data and control flow, functional processing, operational behavior, and information content

Select correct option:

Specifications

Design

Model

Evaluation and Synthesis

During the evaluation and solution synthesis activity, the analyst

creates models of the system in an effort to better understand data and

control flow, functional processing, operational behavior, and

information content. The model serves as a foundation for software

design and as the basis for the creation of specifications for the

Software. The customer may be unsure of precisely what is required.

The developer

http://vuzs.net/

Question # 5 of 10

These all are Product Transition Factors except

Select correct option:

Interoperability

Configurability

Expandability

Testability

Question # 6 of 10

Inefficient project management style is a

Select correct option:

Product-related problems

Technology-related problems

Process-related problems

People-related problems

Inefficient project management style: the project manager needs to lead by

example. The team members absorb the work culture, work ethic, and attitude

of the project manager and implement it in their work style. If you display a

lack of leadership qualities and weak ideals, the motivation levels decrease

across software team.

Question # 7 of 10

Finally, the specification includes a ________

Select correct option:

Bibliography

Appendix

Both Bibliography and Appendix

Reference

Finally, the specification includes a Bibliography and Appendix.

http://vuzs.net/

Question # 8 of 10

Software design is actually a multi step process that focuses on distinct attributes of a program, these are

Select correct option:

Data structure, and Software architecture

Interface representations, and procedural detail

Both of given

None of given

Software design is actually a multi step process that focuses on four

distinct attributes of a program:

–        Data structure,

–        Software architecture,

–        Interface representations, and procedural (algorithmic) detail.

Question # 9 of 10

Software requirements analysis may be divided into______ areas of effort

Select correct option:

4

5

6

7

Software requirements analysis may be divided into five areas of effort:

(1) Problem recognition,

(2) Evaluation and synthesis,

(3) Modeling

(4) Specification, and

(5) Review

http://vuzs.net/

Question # 10 of 10

McCall (MCC77) and his colleagues proposed some software quality factors based on _________ most important aspects of a software product:

Select correct option:

4

3

6

5

There are a number of factors that determine the quality of a software product.

These factors can be measured either directly or indirectly. McCall (MCC77) and

his colleagues proposed some software quality factors based on three most

important aspects of a software product:

1. Product operation

2. Product revision and

3. Product transition

Question # 1 of __________contains an analysis of what went wrong, what went right, and what you could have done better in the software project.

Select correct option:

Prepare closedown report

Identify learning

Identify reusable software components

Create reference material:

Prepare closedown report: The project closedown report contains the results of

the causal analysis that you do for the project. This contains an analysis of what

went wrong, what went right, and what you could have done better in the software

project. contains an analysis of what went wrong, what went right, and what

Question # 2 of 10

Project Quality Management includes the --------------- required to ensure that the project will satisfy the needs for which it was undertaken

Select correct option:

Time

Cost

Processes

None of the given

Project Quality Management includes the processes required to ensure that the

project will satisfy the needs for which it was undertaken. It includes “all

activities of the overall management function that determine the quality policy,

objectives, and responsibilities and implements them by means such as quality

planning, quality assurance, quality control, and quality improvement, within the

quality system.

Question # 3 of 10

--------------completion and settlement of the contract, including resolution of any open items.

Select correct option:

Contract Administration

Source Selection

None of the given

Contract Closeout

Contract Closeout—completion and settlement of the contract, including

resolution of any open items

Question # 4 of 10 ( Start time: 11:31:37 PM ) Total M a r k s: 1

---------------managing the relationship with the seller.

Select correct option:

Source Selection

None of the given

Contract Closeout

Contract Administration

Contract Administration—managing the relationship with the seller.

Question # 5 of 10

Decisions also have a --------------------- element to them—the “right” decision may not be the “best” decision if it is made too early or too late.

Select correct option:

Cost

Quality

Time

None of the given

Decisions also have a time element to them—the “right” decision may not

be the “best” decision if it is made too early or too late.

Question # 6 of 10

-----------is the ability to encourage by "push or pull" technical people to produce to their best ability.

Select correct option:

Evaluating

Motivation

None of the given

Monitoring

Motivation: The ability to encourage (by "push or pull") technical people to

produce to their best ability.

Question # 7 of 10

Unproductive work environment is a

Select correct option:

Technology-related problems

Process-related problems

People-related problems

Product-related problems

Unproductive work environment: The work environment is a major factor

that affects the productivity of the development team. For example, a noisy or

cramped workspace decreases the motivation levels of the employees.

Similarly, unfriendly organizational policies also lower the motivation of the

team members. As the project manager, you need to ensure that the team is

protected from harmful external make the workspace friendly to work in.

Question # 8 of 10

Most software project manager’s practice a lot of management techniques that are of doubtful authenticity are called

Select correct option:

Project management tools

Project management myths

Project management thumb rules

Project management fundamentals

Project Management Myths

In most cases, you learn the skills required to manage a software project while on

the job. As a result, most software project managers practice a lot of management

techniques that are of doubtful authenticity. Many software project managers

learn about the so-called management skills and concepts that are actually myths.

Question # 9 of 10

Strong leadership motivation may sound an obvious trait for a ---------------------.

Select correct option:

Leader

Manager

Specialist

None of the given

Strong leadership motivation may sound an obvious trait for a leader. After all,

only those who want the weighty responsibilities and grueling pressures of

leadership are likely to strive for it.

Question # 10 of

We can classify the problems that affect software projects into _________ categories

Select correct option:

3

4

5

6

You can classify the problems that affect software projects into the following four

categories:

• People-related problems

• Process-related problems

• Product-related problems

• Technology-related problems

Question # 1 of 10

Insufficient identification is a

Select correct option:

Technology-related problems

Process-related problems

People-related problems

Product-related problems

Question # 2 of 10

Technology-related problems include _______

Select correct option:

Overestimated savings from reusable components and new tools and methods

Switching tools in mid way

Integrating different software products in cross-platform implementation

All of given

Question # 3 of 10

What is one of the problems with project management software?

Select correct option:

The project manager manages the software instead of the project

Project duration calculations are sometimes approximate

You can not override the project management software decisions regarding schedules

It’s expensive and difficult to use

Question # 4 of 10

The check-in and checkout facilities provide___________

Select correct option:

Best control

Component control

SCI control

Synchronization control

Question # 5 of 10

McCall (MCC77) and his colleagues proposed some software quality factors based on most important aspects of a software product:

Select correct option:

Product operation

Product revision and

Product transition

All of the given

Synchronization control helps to ensure that parallel changes performed by two different people do ___________.

Select correct option:

http://vuzs.net/

Not overwrite one another

Overwrite one another

May overwrite one another

None of given

The code generation step performs the task

Select correct option:

Translated specification into a machine-readable form

Translated design into a machine-readable form

Translated requirements into a machine-readable form

Translated user data into a machine-readable form

Question # 8 of 10

Before requirements can be analyzed, modeled, or specified they must be gathered through a/an _________

Select correct option:

Elicitation process

Interviewing

Meeting

None of given

http://vuzs.net/

Question # 9 of 10

The quality of software is said to be high if it meets the

Select correct option:

Standards, defined for the product

Procedures, defined for the product

Standards and procedures, defined for the product

Design defined for product

Question # 10 of 10

A review of the Software Requirements Specification is conducted by ________

Select correct option:

Software developer

Customer

Both the software developer and the customer

Top level management

Question # 1 of 10

The British Standards Institution (1986) has stated the quality as

Select correct option:

•           The ability of a software product to satisfy its specified requirements

•           "An inherent or distinguishing characteristic or a property"

•           “Quality is in the eye of the beholder, a matter, of the client's judgment.”

•           All of the given

The distinguishing characteristics of a software product are the cyclomatic

complexity, cohesion, function points, and lines of code. These characteristics of

a software product define the quality of the product.

• The US DOD (1988) defines software quality rather simply as:

– The ability of a software product to satisfy its specified requirements.

• The British Standards Institution (1986) has stated that:

– “Quality is in the eye of the beholder, a matter, of the client's judgment.”

Question # 2 of 10

The check-in and checkout facilities provide___________

Select correct option:

•           Best control

•           Best control

•           SCI control

Synchronization control

The check-in and checkout facilities provide synchronization control. Synchronization control helps to ensure that parallel changes

Question # 3 of 10 A baseline version __________

Select correct option:

•           Have a short life

•           Can be assigned version numbers 3.2

•           Tested and certified version of a system

•           Survive only during bug fixing

Question # 4 of 10

You can use the Item Traceability Matrix to identify _______ at the end of each phase

Select correct option:

•           SCIs

•           SCM

•           Design

•           Construction

You can use the Item Traceability Matrix to identify SCIs at the end of each phase

Question # 5 of 10

Defined scope is a

Select correct option:

•           Technology-related problems

•           Product-related problems

•           Process-related problems

•           People-related problems

Question # 6 of 10 ( Start time: 09:33:13 AM )             Total M a r k s: 1

Software requirements engineering is a process of all except

Select correct option:

•           Discovery

•           Refinement

•           Design

•           Specification

Software requirements engineering is a process of discovery, refinement,

modeling and specification.

Question # 7 of 10

The model serves as the basis for the creation of ________ for the Software.

Select correct option:

•           Design

•           Maintenance

•           Testing

•           Specifications

The model serves as a foundation for software design and as the basis for the creation of specifications for the Software.

Question # 8 of 10

Most software project manager’s practice a lot of management techniques that are of doubtful authenticity are called

Select correct option:

•           Project management tools

•           Project management myths

•           Project management thumb rules

•           Project management fundamentals

Question # 9 of 10

The Introduction of the software requirements specification states the

Select correct option:

•           Goals

•           Objective

•           Design

•           Goals and objectives of the software

Solution is provided by vuZs Solution Team.You are free to distribute and use it. In case you wanted to host or re-distribute it. Please don’t remove the links of group and website

Question # 1

Using PERT and CPM, -----------------------, helps you complete a project on time. By using these techniques, you can determine the latest time by when an activity should start to be completed on time

- Individually

- Combine

- Individually and combine

- None of the above

Using PERT and CPM, individually or in combination, helps you complete a project on time. By using these techniques, you can determine the latest time by when an activity should start to be completed on time. (P# 296)

Question # 2

Each …………. can be subdivided into sub tasks.

- Program

- Task

- Project

- None of the above

Each task can be subdivided into sub tasks. Fro example, in a general software project, a task is to perform project analysis. You may also consider studying the organizational objectives and preparing a project proposal to present to the client. (P# 275)

Question # 3

Predecessor activities need to ------------ before the next can begin. After a predecessor activity is completed, the successor activity becomes the predecessor for another activity

- Both start and end

- End

- Start

- None

Predecessor activities need to end before the next can begin. After a predecessor activity is completed, the successor activity becomes the predecessor for another activity (P# 297)

Question # 4

Efficiency with which a program runs on different platforms or operating systems is Reusability
► True
► False

Portability Efficiency with which a program runs on different platforms or operating systems

Reusability Extent to which the program can be used in more than one program or system (P# 121 )

Question # 5

Which of the items listed below is not one of the software engineering layers?

► Process

► Manufacturing

► Methods

► Tools

Software engineering layers (P# 130)

Process

A quality focus

Method

Tools

Question # 6

-------------------is a software engineering task that bridges the gap between system level requirements engineering and software design.
►Cost Analysis
►Design analysis
►Risk analysis
►Requirements analysis

Requirements analysis is a software engineering task that bridges the gap between system level requirements engineering and software design (P# 93)

Question # 7
---------- is path finding,----------- is path following

► Leadership, Management
► Leader, Leadership
► Management, Leadership
► Manager, Management

Leadership is path finding

Management is path following

Management is about doing things right

Leadership is about doing the right things (P# 45)

Question # 8

Discrete portions of the project that can be charged to a single organization are called -----------------

► Work packages

► Deliverables

► Tasks

► Activities

Work packages are:

Discrete portions of the project that can be charged to a single organization (P# 250)

Question # 9

The first step in project planning is to --------------------

► Determine the budget

► Select a team organizational model

► Determine the project constraints

► Establish the objectives and scope

Question # 10

The software quality assurance activity which is performed to check errors in logic, function, or implementation for any representation of the software is called :

► Inspection

► Formal technical review(s)

► Walkthrough

► Auditing

Q 1. All of the following are types of project closures or endings except:

- Addition

- Integration

- Verification

- Extiction

Q 2. The primary focus of _______________ is to ensure that the final software product offers all the functionality and performance that the customer wanted

- Training test

- User acceptance test

- Implementation test

- Support test

The primary focus of user acceptance test is to ensure that the final software product offers all the functionality and performance that the customer wanted. Therefore, the customer tests the software product for issues such as aesthetics, user friendless, and scalability.

Q 3. Technology-related problems include _______

- Overestimated savings from reusable components and new tools and methods

- Switching tools in mid way

- Integrating different software products in cross-platform implementation

- All of given

Technology-related problems

1. Overestimated savings from reusable components and new tools and methods:

2. Switching tools in mid way

3. Integrating different software products in cross-platform implementation

Q 4. Most software project manager’s practice a lot of management techniques that are of doubtful authenticity are called

- Project management tools

- Project management myths

- Project management thumb rules

- Project management fundamentals

Project Management Myths

In most cases, you learn the skills required to manage a software project while on the job. As a result, most software project managers practice a lot of management techniques that are of doubtful authenticity. Many software project managers learn about the so-called management skills and concepts that are actually myths.

Q 5. Ineffective project sponsorship by management is a

- Technology-related problems

- Process-related problems

- People-related problems

- Product-related problems

People-related problems are

• Low motivation

• Problem employees

• Unproductive work environment

• Inefficient project management style:

• Lack of stakeholder interest

Ineffective project sponsorship by management

Q 6. Unproductive work environment is a

- Technology-related problems

- Process-related problems

- People-related problems

  - Product-related problems

People-related problems are

• Low motivation

• Problem employees

• Unproductive work environment

• Inefficient project management style:

• Lack of stakeholder interest

Ineffective project sponsorship by management

Q 7. Before requirements can be analyzed, modeled, or specified they must be gathered through a/an _________

- Elicitation process

  - Interviewing

  - Meeting

  - None of given

Requirements Elicitation for Software

Before requirements can be analyzed, modeled, or specified they must be gathered through an elicitation process. A customer has a problem that may be amenable to a computer-based solution. A developer responds to the customer's request for help.

Q 8 .  ________of the system is an effort to better understand data and control flow, functional processing, operational behavior, and information content

- Specifications

- Design

- Model

- Evaluation and Synthesis

During the evaluation and solution synthesis activity, the analyst creates models of the system in an effort to better understand data and control flow, functional processing, operational behavior, and information content.

Q 9 Both the software engineer and customer take an active role in software requirements engineering-a set of activities that is often referred to as

- Analysis

  - Specification

  - Design

  - System acceptance

Both the software engineer and customer take an active role in software requirements engineering-a set of activities that is often referred to as analysis.

Q 10. A review of the Software Requirements Specification is conducted by ________

- Software developer

- Customer

- Both the software developer and the customer

  - Top level management